Task List-LRS White Light Housing

Monday, August 27, 2001

System Engineering
Resource Man-Days
Comment

Define Requirements
5


Identify risky elements



Conceptual Design (With BOM)





Preliminary Design



Develop preliminary design
8


Test reports
1


PDR
1




Detailed design



Finish design
4


Test plan
1


CDR
1


Mech Eng Drawings
2 




Fabrication



Monitor fabrication
As required
On going

As-built drawing revisions
1




Laboratory Testing



System integration & Q.A
1


Subsystem and system testing
1


Test report
1




Deployment and Field Test



Mobilize for field test
1


Test
1 


Field test report
1




Documentation & training



Archive Design
1










TOTAL
31


