DORISS / PUP Mtg Notes - February 11th, 2004 
Next Meeting - February 19th - 2 PM - Surface Commons

Attendees - Bill Kirkwood, Sheri White, Mark Brown, Alana Sherman, Rich Henthorn, Peter Walz, Ed Peltzer, Karen Salamy 

1) [Task 1] Hans (from support engineering) is working on the Ventana ethernet connection issues. craig and the Ventana pilots are also replacing components they suspect might be part of the problem. Action: We need to support Hans as needed, Alana (Alan to some) or Sheri will coordinate as needed. 

2) [Task 2] Rich is focusing on the PC Anywhere installation to fix the LRS client. Karen is going to help with the installation. Action: Rich and Karen to install PCAnywhere on bottom side computer. 
3) [Task 6] Alana reported the camera cable repair is delayed waiting on the correct connector from the vendor. New connector is 6 weeks out, so we will not dive with the new shielded camera cable (this is not a problem, signal is no worse than what we've done previously) Action: Alana will maintain vendor contact and coordinate with technicians for build once it arrives. 
4) [Task 131] PUP GUI work delayed till after PCAnywhere installed. Action: None until TASK 2 is completed. 
5) [Task 13] Okuda is working with Alana, Mark and Sheri on fixing the limit switch issues. Current status is no failures occurred during lab testing as had been previously observed. Alana is asking to buy a minimum number of switches for the upcoming dive since Okuda will be gone the week of 2/16 - 2/20 and we possibly won't solve this before the next dive series. the team is having the new motor wired to see if the switches in that one will act as previously observed. Action: Alana will purchase the minimum number of limit switches required to make the march dives. Mark and Alana will see that the new motor is ready for testing the week after next for Okuda. 
6) [Task 24] Mark is continuing with the design of the theta axis. Several items need to be addressed including connector penetrations, bearing specifics, and so forth. Team discussed purchase of the new sphere for the new a connector hole or sending the current one to Benthos for drilling. Bill asked the team to look at the connector pin-outs and see if we could purchase a couple new connectors with the current hole pattern to solve the problem. Bill was particularly concerned that when we add the next two axes this would require an additional new sphere which has other problem with controller spacing internally. Action: Alana is going to review connector options with Mark to see if the current sphere can be used to support the Theta Axis. Mark is going to detail out the bearings and design further with a goal of a design review on April 1st. Mark will confirm that date prior to the March dive series. 
7) [Task 32] Alana talked with Dale G about the new light for PUP using the older DMO design for LEDS lighting. We will proceed with this board and use the ultra-bright LEDS as previously demonstrated by Scott Jensen. Action: Alana will order the LED components. 
8) [Task 36] Mark is going to start the new probe head mount on 2/12. Sheri asked Mark to meet with her first before doing a design (which will go to Johnny for build) so that details for the mounting position are understood and agreed to. Action: Mark to meet with Sheri, agree on the mount dimensions and location, Mark will do the design accordingly. 
9) [Task 46] Mark's design of the new connector mount was determined to be very good and in fact desired for all of the motors to protest the connectors. Action: Mark will have multiple parts made to his design so that all of the motors are upgraded to the new connector configuration. 
10) [Task 51] Johnny is still waiting on swing arm components to finish the Tiburon toolsled upgrade for PUP. Action: Mark will monitor progress and advise as needed. 
11) [Task 61 and 63] Sheri has ordered the new 532 nm laser and the new probe head. Delivery is 16-20 weeks out but Sheri will track these at regular intervals and advise if anything changes. 
Sheri is making arrangements for the local sales rep to visit MBARI and understand our needs. Action: Sheri will check on sales rep availability for the 26th of March.
12) [Task 65] New task to have a fiber optic risk mitigation plan. Sheri is outlining what we will do if a fiber cable is broken. Bill has talked with Mark Chaffey and he will act as a consultant if and when we need one. Action: Team to begin discussions with Sheri about options in case of breaking a cable on DORISS. 
13) [Task 77] Karen has ordered the Parvus fan card for the new CPU stack. It is scheduled to arrive on the 26th. Karen ordered all of the PC-104 stand-offs required to build the unit, she mentioned it was a minimum order condition so we have plenty of spares. She also checked on the compact flash card compatibility with the CPU vendor and as far as they know the card we are using should have no problems. Action: Karen will track delivery and build computer as the parts become available. 
14) [Task 124] Ed checked with DMO and the September cruise is on the books properly. Ed explained how the two Brewer/Peltzer programs had been combined time wise in March which is what brought the concern up. Action: None. 
Side note: Several typos were pointed out and corrected on the latest WBS ver 6.  Special thanks to Alan for pointing these out. 
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