DORISS / PUP Virtual Mtg Notes – March 4th, 2004

1) [Task 1]  The Ventana networking problem seems to be fixed.  The short version is that we can now communicate with DORISS/PUP on Ventana at 100BaseT and while the tether drum is spinning.  The long version goes like this… Hans Thomas help us on March 3rd to troubleshoot our communications problems.  We did everything with DORISS/PUP on the deck in front on the vehicle.  Slowly but surely we stepped through the various connections (including opening VIC) until the problem was isolated to the short CAT 5 cable in the FO can between our BCR connector and the media converter.  In order to fix some previous problems, terminating resistors were put in there and some wires were shorting out.  After removing them, everything worked great.  We then went back to today (after the Pt. Lobos was weathered out) and did a harbor dive wet test.  All worked beautifully.  DJ will clean up that wiring a bit before our dive, but basically that seemed to be the last component of our networking problems.  A huge amount of thanks go to Hans, Pete Braccio (who helped out with some network testing hardware), Craig Dawe, and DJ Osborne.  

2) [Tasks 2 &4]  We will be using VNC for the March dive.  This is working fine.  We are still running LRS Client on the bottom side computer. 
3) [Task 13]  The new limit switches have arrived, and the capacitors are here and pressure tested (successfully).  Installation of the new switches and capacitors will occur March 8-10.  Mark and Alana will take the motors apart on Monday morning.  Tom will do the wiring (his schedule is tight but it looks like he will be able to do it).
4) [Task 24]  Mark is still working on the modular pivot design for the third axis.
5) [Task 32]  The new LED light is finished and functioning.  We are also purchasing some spare LED clusters that will fit our connector.  
6) [Task 36]  No progress on the new probe head mount.  Sheri and the science team need to think more about deployment at Gorda.

7) [Task 47]  Larry Bird is making the U-shape manifolds.  They will be done in time to be installed March 8-10.  

8) [Task 77]  The Environmental II Fan card for the new PC104+ computer is here.  Karen contacted Lippert, and the remaining cards should arrive March 12th.  

9) [Task 121]  We will be diving to Extravert Cliff on the first two days to analyze bacterial mats.  Sheri continues to gather information about the area and is making sure that we will not harm any experiments that are currently there. 

10) Bryan Bowie of Kaiser had to postpone his visit to March 30th (or there about).

11)  DORISS and PUP were weighed (wet and dry) today.  Next week cold testing will be on the 11th and wet testing will be on the 12th (so as not to conflict with Alan’s swim call in the tank).

