DORISS / PUP Mtg Notes - March 11th, 2004

Attendees - Sheri White, Mark Brown, Alana Sherman, Rich Henthorn, Peter Walz, Ed Peltzer, Karen Salamy 

1) [Task 1] Thanks to Hans for finding and correcting the Ventana network issues. 
2) [Tasks 2, 4 & 6] With regard to LRS Client, it is still on hold to prevent any impact on the upcoming dives.  Regarding alternatives to NetMeeting, PCAnywhere was problematic so Rich installed VNC and it is working very well.  The camera cable repair is also on hold until after the March cruise.
3) [Task 129 and related subtasks] Vic wiring and PUP GUI modes completed by Rich and team. 
4) [Task13 and related subtasks] The Z-axis switches are fixed and in testing for the cruise. Some capacitors were added as preventative measures on the suspected motor noise cause of failure but no failures have been observed for some time now in testing. 
5) [Task 23] Mark has gone through the various options for the new Theta Axis (bearings versus flexures for example) and has come to a single concept within the parameters the team set. Namely to use the same motor and electronics we've established of the other electronics and to make the full sweep of 15 centimeters without upsetting the balance of the system. We will review the concept at the next meeting (scheduled for March 25th) and set an engineering design review date to continue with this upgrade. Mark checked with Benthos and verified that would drill the new hole for us to accommodate the new connector for the Theta Axis motor. We will need to ship this out fairly quickly after the March dives to ensure it is back in time for build of the theta Axis and will support the planned testing schedule through most of June. 
6) [Task 32 and related subtasks] The new led light was completed by Alana and ready for the dive series. We have two sets of LEDs if we want to test for a different mix and brightness. 
7) [Task 36] After reviewing the possible sites for dives this summer it was determined that the science team needs to think some more before settling on the new probe mount. This task will be delayed until after the March dive series. 
8) [Task 47] The new Rt. Angle manifolds are at the phase of tech installation. Alana and Mark were unsure if the tech would complete all of them for the dives series due to MOOS using most of the resources. Nothing is holding up the Ventana dives coming up so this is not a critical path item. 
9) [Task 49] The swing arm for Tiburon is still proceeding but slowly due to MOOS impacts on the shop. The longest lead motor components are in house now so it is not critical path. This is also only a monitoring task for Mark, no direct impact on DORISS/PUP. 

10) [Task 54] The rigid lift frame, also due this summer for Tiburon, will be address after the Theta Axis review by Mark.  This is a simple weldment and will be predominantly worked with Johnny F and Mark B consulting. 
11) [Tasks 60, 61, 62, 63, & new Task 63b] The orders have been placed with Kaiser for all of the components outlined in the project plan. Some due dates are not defined yet by the vendor as these are all build to order components. One component, the Neon Calibration Bulb, has arrived already.  The outstanding item is the new Camera. This is a critical item to get specs and delivery on since it impacts the linear bench concepts. Sheri is trying to get answers from Kaiser and Andor about this new product. 
12) [Task 64 and support tasks] Bill had brought up the fiber optic cables as a worry since we have no spares. Sheri stated that for this next dive series there is nothing we can do in time to protect us other than being very careful. This will be further discussed after the March dive series. 
13) [Task 121] For the next two weeks the team will focus on the upcoming science dives and do cold room testing, tank testing, and mob to support the dive series. Sheri mapped out a dive schedule and team support for each dive. (Special thanks to Sheri for taking care of this). Bill stated the team will meet in two weeks, after the dives, since the dives are taking place at the usual meeting time and if all goes well people will be on the ship. 
Bill mentioned that due to Mulitbeam ramping up into a build he would be concentrating on that program for the next few weeks. Sheri mentioned that she would miss some of the dive time due to a health issue and some minor surgery required to clear it up. 

NEXT MEETING THE 25th of MARCH - SURFACE COMMONS

