DORISS / PUP Meeting Minutes - April 22, 2004
Attendees: Sheri White, Mark Brown, Alana Sherman, Peter Walz, Karen Salamy,  Rachel Dunk, Ed Peltzer, Peter Brewer, Rich Henthorn, Bill Kirkwood

1) PUP Papers in process: 

DSR - Abstract and outline started


Oceans - Abstract submitted, waiting on acceptance reply


Peter, Ed, and Sheri finishing Bubble paper (? Journal - I think I heard DSR)
2) Sheri will be checking with Andor further on their desire to highlight the DORISS/ PUP system in a company brochure or some other internal publication. 

3) Bill sent pictures to Kaiser (Ian) and some materials about DORISS / PUP for them to review as potential input for their internal company publication. Ian was requested to let Bill know which images and text he would like to use so ITD can be informed and the proper approval process followed. 

4) Alana, Sheri, and Bill will attempt to arrange a meeting with Mark Chaffey about fiber Optic connectors and where we'd like to insert them in the system. This is part of the risk mitigation plan for the current penetrators which are a critical path item that could severely impact future dives if they are damaged. 

5) Benthos has the sphere for PUP and is opening up one of the holes for a larger hole to accommodate the theta axis penetrator. The light wiring will be moved to extra wires on another penetrator. Mark checked and was told the sphere would ship no later than weeks end and should be in-house (at MBARI) Monday or so of next week (April 20th at the latest). 

6) Alana discussed the failed light and is going to go back to the original concept based on a DMO potted set of LEDs. Alana will report progress at the next meeting on this topic. It is not a pacing item for the cruise in July but science staff are asking for it to be on PUP and working for testing in June. 

7) Mark went over the final details of his bearing design for the theta axis. He has incorporated most of the comments from the technical review.  He went over how it would work with the PUP team and is proceeding with the design. We discussed schedule and came to the conclusion that we need this by early June for testing purposes. Mark agreed to the schedule. Mark also mentioned that he was making a new frame versus chopping up the old one and modifying it. This was considered a safer move since the dive prep has to start in late June or early July to make ship loading. 
8) Shier asked about the swing arm for Tiburon. Mark mentioned that nothing had happened on it, Johnny had been dominated by MOOS work. The parts are in house and some machining then assembly is all that is needed. It is based on the Ventana swing arm, so there is no design work. Mark will monitor this for update purposes. 

9) Mark was asked if we had the U- shaped connector modification part for the theta axis. Mark said it is made and can be installed anytime. 
10) Mark said he would call the vendor on the connectors to support the theta axis upgrade. It was decided that if certain parts were ready he'd asked for a partial shipment to support the EE technician's work waiting on specific pieces to complete a cable. 
11) Tom (EE Tech) is working on the new camera cable. Alana will give an update next week on the status. 

12) Electronics for the new axis are mostly in the new sphere. There are a few components that need to be installed and wired but the work is considered to be relatively straightforward. 

13) Karen said her workload is such she won't be able to bring up the PC-104 stack by end of April. Bill asked if mid-May would work and Karen agreed. Bill asked Rich to help out with the porting of the software. 

14) Ed asked some cruise questions for the summer expedition: 

A) Are we doing anything about the heater for the gas cube to go to Hydrate Ridge? Peter


     Walz said he is getting the parts together and will be ready. 


B) Will there be a new box based on the new heater? Peter responded affirmative. 

15) Bill asked everyone to think about the upcoming Day of Science and Technology. We will discuss what we'd like to present to the board at the next meeting. Bill suggested that we want to push the results aspect with publications and all the press the DORISS / PUP system has been getting. To Bill this was demonstration of meeting the success criteria previously set out by the board of MBARI having impact on the external community. Peer Brewer agreed but no details of how to structure the DOST materials were specifically outlined. 
16) Bill asked the question about the Probe head stage and its impact possibilities for Hydrate Ridge? Bill expressed the belief that this was no longer an issue but wanted to check with the science team. Sheri explained that with PUP the stage isn't as relevant as in previous dives and that horizontally it works anyway, it was only vertically it has a problem in the up direction. Sheri also stated that with the immersion probe this is not an issue at all. So, from her perspective this is no longer an action item to be tracked or have time focused on. Bill noted he would remove it from the task list for the foreseeable future. 

Next meeting Thursday April 29th - Surface Commons

