
PUP Meeting Notes

May 22nd, 2003   2:00 p.m.

ShipsView Conference Room

Attendees:
Sheri White, Mark Brown, Rich Henthorn, Bill Kirkwood, Peter Brewer, Ed Peltzer, Karen Salamy

The Laser Raman Spectrometer (LRS) is now DORISS – Deep Ocean Raman In Situ Spectrometer.  It’s all in the name…

PUP Update:


Wiring is being done by Tom (EE Tech) as we speak.


MB still has about a week of ME work to do:

· Mechanical assembly and testing

· Load testing of the ways (actual components)

· Full up testing of the integrated system in the lab

· Pressue testing of some components


RH could also use another week:

· More testing need of integrated system in the lab

· Configuration file needed

· Logging data function needed

· Homing function needed

Test tank testing will be pushed back one week (to June 2nd – 6th)

Test Plan Update:

· The test plan is approximately ¾ done

· KS still needs some sections and details

· We are in good shape and will focus on this again after the DoST poster is done

DoST Poster Update:

· The deadline is May 30th so that Jim Bellingham can look it over before his vacation

· Needs more text and images

· We will meet to go over a draft of it Wednesday 28th at 10:30 am (Ocean View)
Oceans 2003 Paper Udate:

· The deadline is June 13th (BK will see about getting an extension)

· BK is taking the lead on this and will come up with an outline and assignments

· Everyone must contribute to be listed as an author

Schedule:

· The LRS Team meeting to discuss the Gulf of California cruise and the future of the project will be on Monday (June 2nd) at 10:00 a.m. in Harbor View Conference Room.     

· An updated calendar will be emailed out to everyone.

· The LRS (DORISS) will not be available for integrated testing with PUP July 7th.
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