
PUP Meeting Notes

June 19th, 2003   1:00 p.m.

ShipsView Conference Room

Attendees:
Sheri White, Mark Brown, Rich Henthorn, Scott Jensen, Peter Brewer, Ed Peltzer

PB noted that DORISS and PUP were well received by the Board during DoST.  

PUP Update:


Software (RH)

· The GUI is usable, but it isn’t homing consistently, and some data is being logged

· RH will fix the homing and will check the Data Requirements (in the Functional Requirements) to see what data needs to be logged

· RH should focus on this next week


Electrical (SJ)

· The burned out environmental sensor board was sent back to be inspected

· Once the source of the problem is determined, we can figure out what the operational limits are for that component

· SJ also has an idea he is working on for the Tiburon power issue

· The faulty laser will be returned to the vendor, we have a spare in the lab


Mechanical (MB)

· The PUP is basically put together

· MB is working on a way to clamp the probe head into the PUP mount (w/ John)

· The interface bottle needs to be made (this is necessary for DORISS/PUP testing)

· MB is watching his time and will use a tech to help with upcoming testing

· SW asked MB to think about how to mount the probe head in a horizontal orientation

Testing Update:

· We will need to have a PUP demo so that everyone can learn how to operate the PUP via the GUI (testing will be done using the GUI)

· This will be June 26th at 1:00 pm at the test tank

· Karen will perform PUP testing (using the GUI) with John to help with set-up

· This should start the week after the PUP demo

· SW will perform integrated DORISS/PUP testing (probably starting July 21st)

· MB noted that the actuators and sphere must be pressure tested

· The PUP/DORISS system should be tested on Ventana prior to MOB day (Aug 19th)

· They have a maintenance week July 17-25

· PB suggested we see if Ventana will be in the test tank

Cruise Update:

· PUP Testing cruise is Aug 20 & 21 (MOB day is Aug 19)

· PB will look for suitable sites to visit

· We want to get everyone out on the cruise for at least one day

Oceans2003 Paper must be done by July 11th – PLEASE get BK your text before this date
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