
PUP Meeting Notes

October 24, 2002   1:00 p.m.

Ships View Conference Room

Attendees: Sheri White, Martin Lee, Peter Brewer, Ed Peltzer, Bill Kirkwood, Mark Brown, Danelle Cline, Rich Henthorn, Scott Jensen

We have down-selected to a 5 DOF concept (ZθR with pan & tilt at the sensor head) 

The are two open issues with the design:

1)  Legs – these have not yet been decided on (actuators, spring-loaded with electrical locks, magnetic, etc.)

2) Cable management – we have three concepts on the table

1) Swing-arm: nice and simple, we like it but the pilots don’t

2) Pinch-roller

3) Drum coil – coiling the cable (or a sheathed group of cables inside a drum

*  Weight is a BIG issue

The next step is the Concept Design Review (target date is Nov 7th)

SW passed out an outline for what to cover at the ConDR and what the System Spec document will look like for team input.

Schedule Issues:


The holidays, AGU, and a Western Flyer LRS cruise are coming up.


SW handed out a calendar showing dates through Jan 24th

Nov 7th is too early for the ConDR.


NEW TARGET DATE:  December 4th (with a rehearsal on November 25th)



We can push this back if necessary to December 19th 



This will not affect the PDR target date (Jan 23rd) 

Suggestions were given on slight restructuring of the Concept Design Review outline and the Systems Spec document.  SW will maintain the documents and post updated versions to Polarbear.  Team members will be responsible for overseeing different sections (although the work needs to be done by the team):


SW – Intro, and Top Level Specs


ML – Overall Specs, and Test Requirements


MB – Mechanical Specs, and Cable Management


SJ – Electrical Specs


DC, RH – Software Specs


BK – Analysis, and Cable Management

By next meeting we need an integrated systems block diagram and outlines for each section.

· The next meeting will be Thursday (October 31st) at 1:00 p.m. in Ships View.              

· Email SW your schedule to put on the team calendar
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