PUP/DORISS Meeting Notes

November 20th, 2003  1:30 p.m.

Surface Commons

Attendees:
Sheri White, Bill Kirkwood, Scott Jensen, Alana Sherman, Mark Brown, Rich Henthorn, Karen Salamy, Peter Brewer, Ed Peltzer, Peter Walz, John Ferreira

DORISS Update:

Tested DORISS in the 4C cold room.  All functions worked and comms were solid.  However, the focus stage is not driving in the positive direction the full number of counts it is commanded to do.  More testing will be done both warm and cold to check this out.  It is still driving in both directions, though, so this is not a critical issue.

DORISS needs to be testing on 240 VDC before integration with Tiburon.  

PUP Update:

Actuators – The R axis was pressure tested (in oil) and worked fine.  Both actuators were opened.  Faulty wiring in the Z axis seems to be the cause of the limit switch issue – this wiring has been fixed.  The R axis looked fine inside.  Grease grooves have been cut in the ways and an assembly procedure has been developed.  If the problem is related to misalignment during assembly or stiction, these should help

Power supply – The new power board for PUP works with 110 VAC, needs to be tested with 240 VDC.

Cables – The long cable has been repaired.  All wires are connected, but not all of the shields are connected as they were initially.  All pins do connect through.

Software – Logging functions have been upgraded and all of the software required to run PUP have been installed on Ramandesktop.

Tiburon Integration Update:

Tiburon will be put on the Flyer on Tuesday morning, November 25th.

DORISS/PUP integration testing can be done Tuesday afternoon, and all day on Wednesday (Nov. 26th), Monday (Dec. 1st), and Tuesday (Dec. 2nd).  Pete Braccio will be available to help with Ethernet/communications issues.  We can do a moonpool dive to test the system wet.

The new toolsled is ready and Buck thinks weight will be good (better than he last thought).

Other Issues:

VIC wiring – The VIC still needs to be rewired such that PUP turns DORISS on.  This will be done after the December cruise.

PUP AGU poster – And initial draft (PUP_AGU_Fall03b_10.cdr) is in folder Tornado\ProjectLibrary\600045.DORISS\600045.PUP\Presentations\AGU_2003.

Karen will work on the poster and get text/images from the team as needed.
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