## Sheet1
| Institution | Tasks | Personnel
|  | 1. Characterize swimming speeds, behavioral response to light and other behavioral data of selected specimens at MBA (pending approval). These data will be used to help define and validate the mobility and imaging specificaitons of the Mesobot | Katija
|  | 2. Implement and test MBARI's baseline bio-target tracking algorithm at MBA. These teses will involve processors and cameras supplied by WHOI and mounted inside tanks with artificial or biological targets. | Katija, Risi
Year 1 | MBARI | 3. Identify improvements required for the baseline algorithm to achieve a long-term (e.g. 24 hr) bio-tartet tracking capability. | Risi
|  | 4. Implement the baseline bio-target tracking system on the MiniROV and demonstrate its performance in the test tank using artificial targets | Risi
|  | 5. Transfer the LRAUV real-time computing infrastructure and variable buoyancy system design to WHOI (e.g. existing hardware and software documentation, engineering drawings, initial board set suitable for bench testing). | Hobson, Stanway
|  | 6. Support the integration of the LRAUV computing infrastructure and variable buoyancy system design to WHOI and Mesobot (e.g. participate in telecons with WHOI engineers). | Hobson, Stanway
| Stanford | 1. Suport all of MBARI's implementation and testing of the bio-targtet tracking system and its refinements at MBA, in MBARI's seawater test tank and in the field.
2. Develop extensions to the bio-target tracking alsorithm (e.g. shape-changing targets and robustness) to enable long-duration tracking of animals based on results of MBA tests.
3. Siupport the intration of the bio-trarget tracking algorithm on the MiniROV and Venana including its integration with the ROV's control laws.
1. Design vehicle and integrate components for the Mesobot.
2. Provide imaging hardware to MBARI for in-water testing on targets.
| WHOI | 3. Engineer an interface to the LRAUV motherboard that will enable an exyternal processor to provide real-time commands to the vehicle. The deliverable would include the interface specificaiton, the corresponding code running on the LRAUV motherboard to interact with the external processor, and a GPU runing a simulation for testing.
4. Develop and test a modified version of MBARII'l LRAUV code for the Mesobot.
5. Provide documentation to MBARI for any modificaitons made to LRAUV's code and variable buoyancy system for Mesobot implementation.
6. Integrate Stanford/MBARI's bio-target tracking algorithm on the Mesobot.
|  | 1. Implement updates to the baseline bio-target gtracking algorithm for testing on both the MiniROV and Ventana. These updates will be based on refinements developed by Stanford (e.g. to improve robustness and adaptive frame rates). | Risi
Year 2 |  | 2. Test updates to the bio-target tracking algorithm using the MiniROV in MBARI's seawater test tank facility using both artificial and biological targets. | Katija, Risi
| MBARI | 3. Test updates to the bio-targtet tracking algorithm in Monterey Bay (in deep water) on both ROV Ventana and MiniROV (pending availability of ship days). | All
|  | 4. Assist WHOI in the impolementation and validation of the bio-target tracking algorithm on the Mesobot hardware. | Risi
|  | 5. Support LRAUV integraiton to Mesobot | Hobson, Stanway
| Stanford | 1. Continue to support all of MBARI's implementation and testing of the bio-target tracking system and its refinements MBA, in MBARI's test tank, and in the field.
2. Continue to improve the bio-target tracking algorithm to enable long-duration tracking of animals based on the resultes of tank and field testing.
| WHOI | 1. Integrate improvements to bio-target tracking algorithm and imaging system on Mesobot.
2. Test Mesobot improvments in the test tank and shallow water (at WHOI or MBARI depending on animal and ship availability).
3. Train staff at WHOI and MBSARI in Mesobot operations.
| MBARI | 1. Continue to refine and test the bio-target tracking algorithm. | Katija, Risi
|  | 2. Support WHOI's implementation of the algorithm on the Mesobot. | All
|  | 3. Support field-testing of the Mesobot. | All
Year 3 | Stanford | 1. . Support field-testing of the Mesobot.including modificaitons to the tracking algorithm.
1. Integrate improvements to the Mesobot.
| WHOI | 2. Test Mesobot improvments in the test tank and shallow water (at WHOI or MBARI depending on animal and ship availability).
3. Test the Mesobot in deep waters of Monterey Bay Canyon (pending ship availability).
4. Train staff at WHOI and MBSARI in Mesobot operations.