## Mesobot
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
To Do | Ask Steve Haddock about bioluminescence of larvaceans, illumination, etc. |  |  |  | KK | in progress,past due,partially completed | 3 | https://trello.com/c/IN6mBG9r
To Do | Incorporate world frame vs. only vehicle frame for identifying/tracking targets |  |  |  | MR | in progress,partially completed,in progress | 8 | https://trello.com/c/qOYSo6JN
To Do | follow up on optical budget for HD stereo cameras |  |  |  | MR | completed | 31 | https://trello.com/c/6qseJFwj
Ongoing | Work on simulation to test logic for tracking algorithms |  |  |  | MR | in progress | 7 | https://trello.com/c/cVFwMbuW
Ongoing | find out if requirement is needed for bandwidth/closed-loop control and latency |  |  |  | MR |  | 20 | https://trello.com/c/jDNHednC
Ongoing | Determine minimum target pixel size for effective tracking; work to decouple target size and intensity for imaging configuration determination, why the bump? |  |  |  | MR | curiosity,completed | 6 | https://trello.com/c/lnmr0eKn
Ongoing | Confirm 10 Hz control at the motors via load test on the existing LRAUV bench system using the backseat driver interface |  |  |  | BK | in progress | 1 | https://trello.com/c/erqy0ngZ
Ongoing | camera discussion notes |  |  | 2017-10-18 12:00 |  |  | 18 | https://trello.com/c/8KamTzHN
Completed | ask Jon whether he'd integrate CUDA optimized commands in OpenCV to speed up image processing |  |  |  | BH | completed | 21 | https://trello.com/c/IOFsjLwz
Completed | ask Jon to come up with benchmark given HD camera feed (larvacean x 2)/TX2 to ensure we can do real-time processing |  |  |  | BH | completed | 22 | https://trello.com/c/1YNbGsl8
Completed | Query Caltech contacts to find out who does Machine Learning and could advertise/provide postdocs |  |  |  | KK | completed | 4 | https://trello.com/c/xu61xiRR
Completed | send machine learning motion applications to Steve |  |  |  | KK | completed | 30 | https://trello.com/c/DAFHWV2T
Upcoming Goals | Track targets for 4 hr durations during Spring Mesobot cruises with MiniROV | [5 empty] | 13 | https://trello.com/c/fmSBX9U1
Needs from WHOI | What's the nominal vehicle configuration? Need to know before testing. Need opportunity to comment | [5 empty] | 9 | https://trello.com/c/hOqvw83r
Needs from WHOI | What's the nominal camera/lighting configuration? MBARI wants two wide-angle, monochrome cameras for stereo | [5 empty] | 10 | https://trello.com/c/RuV4qbau
Needs from WHOI | How are they importing video to TX2? | [5 empty] | 11 | https://trello.com/c/qaL1QbPG
Functional Requirements | CG and CB alignment such that thrust and vehicle pitch are decoupled | [5 empty] | 12 | https://trello.com/c/5AeIx6Bx
Meeting Notes | 171101 Meeting Notes | what are they wanting to use VARS for? questions about science camera - pan/tilt/zoom how is that controlled? heavy battery housings on bottom of vehicle for stability? science camera on roll axis and as close to straight-pointing (non-canting) stereo camera move gulper to a “payload” configuration diverter for rear thruster wash dive tentatively on november 12 deep sea project - fiber optic towsled that carries broadband (including high frequency) acoustics, video (28MB allied GT660 color and monochrome, max frame are 3.7 fps, LED orthogonal to image plane, imaging plane ~1 m from camera), c-scan LIST-HOLO integration btwn data and video for Mesobot, not facility-financed annotation services, where is the data stored?? petabyte storage system at WHOI |  |  |  |  | 28 | https://trello.com/c/zfb87X2g
Meeting Notes | 171108 Meeting Notes | lighting? batteries: 31 to 37, WHOI needs to do development since LRAUV is only 31 what is in the battery housings? lighting configuration - are we committed? send to MBARI to test - KK |  |  |  |  | 29 | https://trello.com/c/XMNCcu7q

## Archived Mesobot
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Completed | [archived] Get quotes on camera/light hardware |  |  |  | BH | completed | 5 | https://trello.com/c/AqivxMEK
Completed | [archived] Determine monies available in Mesobot project to purchase stereo cameras |  |  |  | KK | completed | 14 | https://trello.com/c/yOk5snkD
Completed | [archived] send HD video to Jon Howland to run on TX2 |  |  |  | MR | completed | 15 | https://trello.com/c/6UJnhOWR
Completed | [archived] Email Kandace with brief description of postdoc project |  |  |  | KK | completed | 2 | https://trello.com/c/EAo95jt2
Completed | [archived] ask video lab to add water mark to larvacean videos in mesobot folder |  |  |  | KK | completed | 23 | https://trello.com/c/5wVrgf56
Completed | [archived] tell Dana about November cruise date and what his planned test schedule might look like |  |  |  | KK | completed | 16 | https://trello.com/c/aGm1iZCK
Completed | [archived] write and submit NSF-EAGER with postdoc mentoring plan to OTIC and Kandace Binkley |  |  |  | KK | past due,in progress,completed | 17 | https://trello.com/c/hXwydCZM
Completed | [archived] make decision on test hardware for near-term MBARI deployments |  |  |  |  | completed | 19 | https://trello.com/c/WLY5lTex
Completed | [archived] how fast do we want the vehicle to move? use larvacean swimming speed as standard - come up with estimate |  |  |  | KK | completed | 24 | https://trello.com/c/GxXg6jsw
Completed | [archived] are new HDSDI cameras sensitive to red/near-IR light? |  |  |  | MR | completed | 26 | https://trello.com/c/TlyeI4As
Completed | [archived] do we need to buy another IR light for testing? query WHOI about lighting and test needs. |  |  |  | KK | completed | 27 | https://trello.com/c/xwrge1Fx
Completed | [archived] what are the barriers to getting 2xHDSDI cameras on Ventana in March? |  |  |  | MR | in progress,completed | 25 | https://trello.com/c/RP8qrOb3