## ^^Cover Page^^
Performance Report - Quantitative (PRQ)
Instructions:
Please fill out the Required Inputs with General Information and Schedule Information below. Some of this information will auto-populate the headers on each tab as well as additional data fields throughout the forms.
Each tab will have additional instructions to assist in the completion of each form.
Required Inputs
Select Reporting Period | 07/01/2024 to 09/30/2024 |  | ← Select Reporting Period Here
General Information
Recipient Name: | MBARI
Agreement # (CID): | EE0009444 |  | Mod #: | 5
Project Title: | Open Wave-Energy Control System Development Platform
Period of Performance Start Date: | 2021-10-01
Principal Investigator Name: | Andrew Hamilton
PI Email: | hamilton@mbari.org |  | PI Phone:
TRL (or N/A): | N/A
If the recipient is a Hydroelectric Incentive Selectee, please select yes from the drop-down.
Schedule Information
| Budget Period 1 | Budget Period 2 | Budget Period 3 | Budget Period 4 | Budget Period 5
Budget Period Start Date: | 2021-10-01 | 2024-04-01
Budget Period End Date: | 2024-03-30 | 2026-03-31
26 Depends on Status or do we want a proposed date ??
Select Project Type |  |  |  | All Other Projects
Infrastructure Work Status:
Start Date of Infrastructure work:
End Date of Infrastructure work:
Start Date of Operations:
What date will the project reach 100% of site hires for construction/operation?:
Starting what date (month,day,year) would be ideal for DOE leadership to visit?
Please describe why that date would be ideal.:
Comments or Concerns about this form can be submitted at the following link: |  |  | BIL Reporting Template Feedback
Template Version: 4
End of Table
Do not submit Protected Personally Identifiable Information (Protected PII) to DOE. For more information on Protected PII, see Appendix A of the BIL Federal Assistance Reporting Checklist.
Note on F10: If applicable
Note on B15: Technology Readiness Levels (TRLs): Identify the readiness level of the technology associated with the project as well as the planned progression during the course of project execution. provided. Specific entry criteria for the next higher technology readiness level should be identified. The following definitions apply: TRL-1. Basic principles observed and reported: Scientific problem or phenomenon identified. TRL-2. Technology concept and/or application formulated: Applied research activity. TRL-3. Analytical and experimental critical function and/or characteristic proof of concept. TRL-4. Component and/or process validation in laboratory environment- Alpha prototype component. TRL-5. Component and/or process validation in relevant environment- Beta prototype component. TRL-6. System/process model or prototype demonstration in a relevant environment- Beta prototype (system). TRL-7. System/process prototype demonstration in an operational environment- Integrated. TRL-8. Actual system/process completed and qualified through test and demonstration. TRL-9. Systems are operational.
Note on B22: Definition of infrastructure project: An individual endeavor (pilot, demonstration or deployment) that is funded, in part or in its entirety, through BIL-funded financial assistance award(s) that takes place at a specific location and involves the construction, modernization, or major alteration and renovation of structures, facilities, and equipment in the United States, including: • roads, highways, and bridges • public transportation • dams, ports, harbors, and other maritime systems • intercity passenger and freight railroads • freight and intermodal facilities • airports • water systems (including drinking water and wastewater systems) • electrical transmission facilities and systems • utilities • broadband infrastructure • buildings and real property
Note on B23: Planned (Post Award) - Project has not initiated construction yet, in preparation phase. In Progress - Construction activities have commenced and are actively being conducted. Completed - Construction activities have concluded.

## I. Organizations
Organizations
Recipient Name: | MBARI |  |  | Agreement # (CID): |  | EE0009444
Reporting Period: | 07/01/2024 to 09/30/2024
Instructions:
Use this table to identify ALL subrecipients, contractors, partners, collaborating organizations, CBP partner, and U.S. National Laboratories associated with this award. Once completed, these organizations will be available for auto-selection on the "Task, Milestones, Deliverables", "Contractual Cost Summary", and "Participants" tabs. DO NOT delete approved contractors and do not add contractors to this tab until approved by the G/AO/CO. This is a cumulative report that will be used throughout the lifecycle of the project, DO NOT delete previously entered organizations.
Column B: Input the name of the Partner Organization.
Column C: Enter the partner organization's UEI (Unique Entity ID) number (this can be found at SAM.GOV). If there is NO UEI for your organization you MUST complete Column O.
Column D: Indicate if the partner organization is a Minority Serving Institution (the MSI Category definitions e-link is provided in the header if you are unsure).
Columns E-F: Should reflect the 5-Digit Zip Code +4 Digits of the partner organization (use the Zip Code Lookup e-link provided in the header if you are unsure).
Columns G-H: Input Latitude and Longitude for Foreign Locations outside of the U.S. or locations not defined by a zip code (use the Latitude/Longitude Finder e-link provided in the header if you are unsure).
Column I: Select the Partner Type (organization's role) on the award (prime, subrecipient, contractor, partners, collaborating organizations, CBP partner, and U.S. National Laboratories. If the partners role is exclusive to CBP activities, please select CBP partner. If you are a subrecipient (or other role) please select that role not CBP partner.)
Column J: Identify the selected Partner Organization's Contribution to the Project. If the options in the dropdown selection do not apply, please specify the type of contribution is being provided in Column K.
Columns L-M: Input Start and End Dates for Organization's partnership; if they are still currently performing in their role indicate N/A for the End Date.
Columns N-R: Input which of these organizations are part of your DEIA plan based on information provided in the CBP Objectives Summary signed at Award. Include any other organizations added to the DEIA in the process of the project who are not listed in the CBP Objectives Summary. Only complete Column O if the organization does not have a UEI number in Column C.
Note:For additional rows, be sure to 'Copy' existing rows and 'Insert Copied Cells' for the drop-downs and conditional formatting to function properly.
Organizations | [11 empty] | DEIA Plan Partners
|  | MSI Categories | Zip Code Lookup |  | Latitude & Longitude Finder | [6 empty] | Indicate if this organization is part of your DEIA plan
Organization Name | Organization UEI | MSI (Yes/No) | 5-Digit Zip Code | Zip Code +4 | Latitude | Longitude | Partner Type | Role in the Project | Contribution to the Project | Partnership Start Date | Partnership End Date | Is this Partnership part of your DEIA plan? | Organization Type | If Other, Specify Organization Type | Ownership Type | If Other, Specify Ownership Type
Open Source Robotics | [12 empty] | For Profit
Cooley | [12 empty] | For Profit
Monterey Canyon Research Vessels | [12 empty] | Non-Profit​ (Not University)
End of Table

## II. Task_Milestone_Deliverable
Tasks, Milestones, Deliverables
Recipient Name: |  |  |  |  | MBARI | Agreement # (CID): |  | EE0009444
Reporting Period: |  |  |  |  | 07/01/2024 to 09/30/2024
Instructions:
This is a cumulative report that will be used throughout the lifecycle of the project, DO NOT delete completed line items or revise line items unless there has been an approved modification to your award impacting your SOPO/SOW or CBP.
Columns B-G: These columns should mirror your Statement of Project Objectives (SOPO), Statement of Work (SOW) or Community Benefits Plan (CBP) for each task or milestone for the entire project duration.
Column H: No Entry Required! This column will auto-populate from your inputs in the previous columns. Use this Unique Task Identifier where applicable to mirror in your CBP and CBR.
Column I: Provide a brief description of the work, task, milestone or deliverable.
Column J: Should reflect the Organization responsible for performing the task (this pick-list is auto-populated from the inputs on the Organizations tab).
Column K: Input the month and year of the Planned project START Date, this should mirror the SOPO/SOW/CBP "Anticipated Date" for each task or milestone.
Column L: Input the month and year of the Planned project DUE Date for each line item.
Column M: Input the month and year of the Revised project DUE Date for each line item.
Column N: If a planned due date is missed, provide a brief Status Summary of why the date was missed, the impact on the project, as well as what actions are being taken to achieve the milestone and back on track. A complete description of project status should be included in the PRN.
Column O: Input the Physical Percent of Completion per each instance of work, task, milestone, or deliverable. Physical percent complete is an estimate of the actual amount of progress made toward the final objective (rather than the % of money or time spent on the task or milestone).
Column P: Input the month and year of the Actual Month Completed Date for each line item.
Note: If you need additional rows, be sure to 'Copy' existing rows and 'Insert Copied Cells' for the drop-downs and conditional formatting to function properly.
Task/Milestone/Deliverable Schedule
Task/Milestone/Deliverable Description | [6 empty] | Task/Milestone/Deliverable Timelines
Budget Period # | Task Type | CBP Task Kind | Task # | Subtask # | M or D # | Task Unique Identifier | Description of Work, Task, Milestone, or Deliverable | Performing Organization | Planned START Date | Planned DUE Date | Revised DUE Date | Status Summary/Notes | Physical Percent Complete | Actual Project Month Completed
1 | T |  | 1 | 0 | 0 |  | ROS integration into buoy controller |  | 2021-10-01 | 2022-03-31
1 | ST |  | 1 | 1 | 0 |  | System architecture planning |  | 2021-10-01 | 2021-11-30
1 | ST |  | 1 | 2 | 0 |  | Create ROS Package defining message data structures |  | 2021-12-01 | 2022-02-28
1 | ST |  | 1 | 3 | 0 |  | Create ROS package that publishes CANbus data |  | 2021-12-01 | 2022-02-28
1 | ST |  | 1 | 4 | 0 |  | Create ROS package that publishes AHRS/GPS data |  | 2021-12-01 | 2022-02-28
1 | ST |  | 1 | 5 | 0 |  | Create ROS package that logs data on the buoy |  | 2021-12-01 | 2022-02-28
1 | ST |  | 1 | 6 | 0 |  | Create ROS package that provides streaming telemetry |  | 2021-12-01 | 2022-02-28
1 | ST |  | 1 | 7 | 0 |  | Test on Buoy Computer |  | 2022-03-01 | 2022-03-31
1 | M |  | 1 | 7 | 1 |  | ROS Running on MBARI WEC Computer |  | 2022-03-01 | 2022-03-31
1 | T |  | 2 | 0 | 0 |  | Integrate wave-energy simulator into ROS environment |  | 2021-12-01 | 2022-05-31
1 | ST |  | 2 | 1 | 0 |  | Planning |  | 2021-12-01 | 2022-01-31
1 | ST |  | 2 | 2 | 0 |  | Evaluate simulation tools |  | 2022-01-01 | 2022-01-31
1 | M |  | 2 | 2 | 1 |  | Simulator selected |  | 2022-02-01 | 2022-02-28
1 | ST |  | 2 | 3 | 0 |  | Integrate selected simulation into ROS package |  | 2022-01-01 | 2022-02-28
1 | ST |  | 2 | 4 | 0 |  | PTO and power system simulation |  | 2022-01-01 | 2022-02-28
1 | ST |  | 2 | 5 | 0 |  | Implement Heave Cone simulation |  | 2022-01-01 | 2022-01-31
1 | ST |  | 2 | 6 | 0 |  | Develop Simulation Inputs |  | 2022-02-01 | 2022-04-30
1 | ST |  | 2 | 7 | 0 |  | Develop visualization tools |  | 2022-01-01 | 2022-04-30
1 | ST |  | 2 | 8 | 0 |  | Test code interoperability with buoy hardware |  | 2022-04-01 | 2022-05-31
1 | M |  | 2 | 8 | 1 |  | Simulator integrated |  | 2022-05-01 | 2022-05-31
1 | T |  | 3 | 0 | 0 |  | Publish Simulated Environment |  | 2022-05-01 | 2022-06-30
1 | ST |  | 3 | 1 | 0 |  | Publically release software from task 1 and 2 |  | 2022-05-01 | 2022-06-30
1 | ST |  | 3 | 2 | 0 |  | Create example tutorial |  | 2022-05-01 | 2022-06-30
1 | ST |  | 3 | 3 | 0 |  | Test example tutorial |  | 2022-05-01 | 2022-06-30
1 | ST |  | 3 | 4 | 0 |  | Export example tutorial to website/portal |  | 2022-05-01 | 2022-06-30
1 | M |  | 3 | 4 | 1 |  | All packages are published publically |  | 2022-06-01 | 2022-06-30
1 | T |  | 4 | 0 | 0 |  | Port existing MBARI control to ROS system |  | 2022-03-01 | 2022-06-30
1 | ST |  | 4 | 1 | 0 |  | Transfer current logging and control features to ROS system |  | 2022-03-01 | 2022-05-31
1 | ST |  | 4 | 2 | 0 |  | Transfer current system control features to ROS system |  | 2022-03-01 | 2022-05-31
1 | ST |  | 4 | 3 | 0 |  | Run standard performance/logging tests with ROS system |  | 2022-05-01 | 2022-06-30
1 | M |  | 4 | 3 | 1 |  | MBARI control running in ROS system |  | 2022-06-01 | 2022-06-30
1 | T |  | 5 | 0 | 0 |  | Develop website/portal for user access/outreach |  | 2022-04-01 | 2022-06-30
1 | ST |  | 5 | 1 | 0 |  | Planning and toolchain selection |  | 2022-04-01 | 2022-04-30
1 | ST |  | 5 | 2 | 0 |  | Establish communication channel for online community |  | 2022-04-01 | 2022-05-31
1 | ST |  | 5 | 3 | 0 |  | Create website entry-point |  | 2022-05-01 | 2022-06-30
1 | M |  | 5 | 3 | 1 |  | Portal ready to launch |  | 2022-06-01 | 2022-06-30
1 | T |  | 6 | 0 | 0 |  | Launch of simulation capabilities to beta group |  | 2022-06-01 | 2022-12-31
1 | ST |  | 6 | 1 | 0 |  | Planning and identification of beta users |  | 2022-06-01 | 2022-06-30
1 | ST |  | 6 | 2 | 0 |  | Prepare and hold webinar |  | 2022-06-01 | 2022-07-31
1 | M |  | 6 | 2 | 1 |  | Webinar completed |  | 2022-08-01 | 2022-08-31
1 | ST |  | 6 | 3 | 0 |  | User Support |  | 2022-07-01 | 2022-12-31
1 | ST |  | 6 | 4 | 0 |  | Website and data management |  | 2022-07-01 | 2022-12-31
1 | ST |  | 6 | 5 | 0 |  | Results review |  | 2022-09-01 | 2022-12-31
1 | T |  | 7 | 0 | 0 |  | Buoy deployment, recovery and maintenance #1 |  | 2022-12-01 | 2023-06-30
1 | ST |  | 7 | 1 | 0 |  | Pre-deployment assembly and test |  | 2022-12-01 | 2023-01-31
1 | ST |  | 7 | 2 | 0 |  | Deployment |  | 2022-12-01 | 2023-01-31
1 | M |  | 7 | 2 | 1 |  | Buoy deployed |  | 2023-01-01 | 2023-01-31
1 | ST |  | 7 | 3 | 0 |  | At-sea monitoring |  | 2023-01-01 | 2023-06-30
1 | ST |  | 7 | 4 | 0 |  | Recovery, cleaning and refurbishment |  | 2023-06-01 | 2023-06-30
1 | T |  | 8 | 0 | 0 |  | Support of on-buoy operations for beta group |  | 2023-02-01 | 2023-06-30
1 | ST |  | 8 | 1 | 0 |  | Safety review of controller behaviors in simulation |  | 2023-02-01 | 2023-02-28
1 | ST |  | 8 | 2 | 0 |  | User support during on-buoy operations |  | 2023-02-01 | 2023-06-30
1 | M |  | 8 | 2 | 1 |  | Successful on-buoy use of user code |  | 2023-06-01 | 2023-06-30
1 | ST |  | 8 | 3 | 0 |  | Data management |  | 2023-02-01 | 2023-06-30
1 | ST |  | 8 | 4 | 0 |  | Assistance with results analysis and publication |  | 2023-05-01 | 2023-06-30
1 | T |  | 9 | 0 | 0 |  | Marketing and outreach |  | 2022-10-01 | 2023-09-30
1 | ST |  | 9 | 1 | 0 |  | Documentation and workshop or online training preparation |  | 2022-10-01 | 2022-12-31
1 | M |  | 9 | 1 | 1 |  | Workshop or online training completed |  | 2023-01-01 | 2023-01-31
1 | ST |  | 9 | 2 | 0 |  | Advertising |  | 2022-10-01 | 2023-09-30
1 | ST |  | 9 | 3 | 0 |  | Website/portal maintenance |  | 2022-10-01 | 2023-09-30
1 | ST |  | 9 | 4 | 0 |  | Workshop or online training |  | 2023-03-01 | 2023-03-31
1 | ST |  | 9 | 5 | 0 |  | Conference attendance |  | 2022-10-01 | 2023-09-30
1 | ST |  | 9 | 6 | 0 |  | Coordination with MERC |  | 2022-10-01 | 2023-09-30
1 | T |  | 10 | 0 | 0 |  | Support of simulation capabilities for all interested parties |  | 2022-12-01 | 2023-09-30
1 | ST |  | 10 | 1 | 0 |  | User support |  | 2022-12-01 | 2023-09-30
1 | ST |  | 10 | 2 | 0 |  | Code maintenance |  | 2022-12-01 | 2023-09-30
1 | ST |  | 10 | 3 | 0 |  | Results review |  | 2022-12-01 | 2023-09-30
1 | T |  | 11 | 0 | 0 |  | Go/No-Go Review |  | 2023-05-01 | 2023-09-30
1 | ST |  | 11 | 1 | 0 |  | Continuation application and presentation |  | 2023-05-01 | 2023-07-31
1 | D |  | 11 | 1 | 1 |  | Continuation Application and Presentation |  | 2023-07-01 | 2023-07-31
1 | M |  | 11 | 1 | 2 |  | Receipt of GNG Decision |  | 2023-08-01 | 2023-08-31
1 | ST |  | 11 | 2 | 0 |  | Negotiation or Project Closeout |  | 2023-08-01 | 2023-09-30
2 | T |  | 12 | 0 | 0 |  | Marketing and outreach |  | 2023-10-01 | 2025-07-31 | 2026-03-01 | Ongoing until end of project
2 | ST |  | 12 | 1 | 0 |  | Documentation and workshop or online training preparation |  | 2023-10-01 | 2024-01-31 | 2024-07-31 | Completed
2 | ST |  | 12 | 2 | 0 |  | Advertising |  | 2023-10-01 | 2025-07-31 | 2026-03-01 | Ongoing until end of project
2 | ST |  | 12 | 3 | 0 |  | Website/portal maintenance |  | 2023-10-01 | 2025-07-31 | 2026-01-31 | Ongoing
2 | ST |  | 12 | 4 | 0 |  | Workshop or online training |  | 2024-01-01 | 2024-03-31 | 2024-09-30 | Completed
2 | ST |  | 12 | 5 | 0 |  | Conference attendance |  | 2023-10-01 | 2024-09-30 | 2025-03-30 | Completed
2 | M |  | 12 | 5 | 1 |  | Attend conference or seminar |  | 2024-09-01 | 2024-09-30 | 2025-03-30 | Completed
2 | ST |  | 12 | 6 | 0 |  | Coordination with MERC |  | 2023-10-01 | 2025-07-31 | 2026-01-31 | Completed
2 | T |  | 13 | 0 | 0 |  | Support of simulation capabilities |  | 2023-10-01 | 2025-09-30 | 2026-03-01 | Ongoing until end of project
2 | ST |  | 13 | 1 | 0 |  | User support |  | 2023-10-01 | 2025-09-30 | 2026-03-01 | Ongoing until end of project
2 | ST |  | 13 | 2 | 0 |  | Code maintenance |  | 2023-10-01 | 2025-09-30 | 2026-03-01 | Ongoing until end of project
2 | ST |  | 13 | 3 | 0 |  | Results review |  | 2023-10-01 | 2025-09-30 | 2026-03-30 | Ongoing
2 | T |  | 14 | 0 | 0 |  | Buoy deployment, recovery and maintenance #2 |  | 2023-12-01 | 2024-06-30 | 2024-12-30 | Completed
2 | ST |  | 14 | 1 | 0 |  | Pre-deployment assembly and test |  | 2023-12-01 | 2024-01-31 | 2024-07-31 | Completed
2 | ST |  | 14 | 2 | 0 |  | Deployment |  | 2023-12-01 | 2024-01-31 | 2024-07-31 | Completed
2 | M |  | 14 | 2 | 1 |  | Buoy Deployed |  | 2024-01-01 | 2024-01-31 | 2024-07-31 | Completed
2 | ST |  | 14 | 3 | 0 |  | At-sea monitoring |  | 2024-01-01 | 2024-06-30 | 2024-12-30 | Completed
2 | ST |  | 14 | 4 | 0 |  | Recovery, cleaning and refurbishment |  | 2024-06-01 | 2024-06-30 | 2024-12-30 | Completed
2 | T |  | 15 | 0 | 0 |  | Support of on-buoy operations for deployment #2 |  | 2024-02-01 | 2024-06-30 | 2024-12-30 | Completed
2 | ST |  | 15 | 1 | 0 |  | Safety review of controller behaviors in simulation |  | 2024-02-01 | 2024-02-29 | 2024-08-29 | Completed
2 | ST |  | 15 | 2 | 0 |  | User support during on-buoy operations |  | 2024-02-01 | 2024-06-30 | 2024-12-30 | Completed
2 | M |  | 15 | 2 | 1 |  | Successful on-buoy use of user code |  | 2024-06-01 | 2024-06-30 | 2024-12-30 | Completed
2 | ST |  | 15 | 3 | 0 |  | Data management |  | 2024-02-01 | 2024-06-30 | 2024-12-30 | Completed
2 | ST |  | 15 | 4 | 0 |  | Assistance with results analysis and publication |  | 2024-05-01 | 2024-06-30 | 2024-12-30 | Completed
2 | T |  | 16 | 0 | 0 |  | Addition of specialized buoy capabilities |  | 2024-07-01 | 2024-11-30 | 2026-03-01 | Ongoing, with respect to BIL Funding
2 | ST |  | 16 | 1 | 0 |  | Identification of practical and effective modifications |  | 2024-07-01 | 2024-07-31 | 2026-03-01 | Ongoing, with respect to BIL Funding
2 | ST |  | 16 | 2 | 0 |  | Design work to implement modifications |  | 2024-08-01 | 2024-08-31 | 2026-03-01 | Ongoing, with respect to BIL Funding
2 | ST |  | 16 | 3 | 0 |  | Mechanical and electrical integration |  | 2024-08-01 | 2024-11-30 | 2026-03-01 | Ongoing, with respect to BIL Funding
2 | ST |  | 16 | 4 | 0 |  | Software integration and test |  | 2024-08-01 | 2024-11-30 | 2026-03-01 | Ongoing, with respect to BIL Funding
2 | T |  | 17 | 0 | 0 |  | Buoy deployment, recovery and maintenance #3 |  | 2024-12-01 | 2025-06-30 | 2025-12-30 | Completed
2 | ST |  | 17 | 1 | 0 |  | Pre-deployment assembly and test |  | 2024-12-01 | 2025-01-31 | 2025-07-31 | Completed
2 | ST |  | 17 | 2 | 0 |  | Deployment |  | 2024-12-01 | 2025-01-31 | 2025-07-31 | Completed
2 | M |  | 17 | 2 | 1 |  | Buoy Deployed |  | 2025-01-01 | 2025-01-31 | 2025-07-31 | Completed
2 | ST |  | 17 | 3 | 0 |  | At-sea monitoring |  | 2025-01-01 | 2025-06-30 | 2025-12-30 | Completed
2 | ST |  | 17 | 4 | 0 |  | Recovery, cleaning and refurbishment |  | 2025-06-01 | 2025-06-30 | 2025-12-30 | Completed
2 | T |  | 18 | 0 | 0 |  | Support of on-buoy operations for deployment #3 |  | 2025-02-01 | 2025-06-30 | 2025-12-30 | Completed
2 | ST |  | 18 | 1 | 0 |  | Safety review of controller behaviors in simulation |  | 2025-02-01 | 2025-02-28 | 2026-03-01 | Ongoing
2 | ST |  | 18 | 2 | 0 |  | User support during on-buoy operations |  | 2025-02-01 | 2025-06-30 | 2026-03-01 | Ongoing
2 | M |  | 18 | 2 | 1 |  | Successful on-buoy use of user code |  | 2025-06-01 | 2025-06-30 | 2026-03-01 | Ongoing
2 | ST |  | 18 | 3 | 0 |  | Data management |  | 2025-02-01 | 2025-06-30 | 2026-03-01 | Ongoing
2 | ST |  | 18 | 4 | 0 |  | Assistance with results analysis and publication |  | 2025-03-01 | 2025-06-30 | 2026-03-01 | Ongoing
2 | T |  | 19 | 0 | 0 |  | Final report preparation |  | 2025-07-01 | 2025-09-30 | 2026-03-30
2 | ST |  | 19 | 1 | 0 |  | Final report preparation |  | 2025-07-01 | 2025-09-30 | 2026-03-30
2 | D |  | 19 | 1 | 1 |  | Final report |  | 2025-09-01 | 2025-09-30 | 2026-03-30
End of Table
Formulas:
Revised DUE Date = +EDATE([Planned DUE Date],6)
Note on C22: BP Budget Period T TASK T (CBP) TASK (Community Benefits Plan) ST Subtask ST (CBP) Subtask (Community Benefits Plan) M Milestone M (CBP) Milestone (Community Benefits Plan) D Deliverable FD Final Deliverable BT Bridge Task GNG Go/No-Go ICDP Internal Critical Decision Point PM Project Management
Note on D22: Jobs - Direct/Quality Jobs J40 - Justice 40 DEIA - Diversity, Equity, & Inclusion CE- Community Engagement
Note on H22: This Unique Identifier should be mirrored in your CBP where applicable.
Note on I22: Abrv Title Description Assigned to BP Budget Period . . . . . . . . . . . . . . . . . . Title describing top level phase of work . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . None, top level T Task . . . . . . . . . . . . . . . . . . . . . . . . .A logical subdivision of major efforts to complete a budget period . . . . . . . . . . . . .Budget Period T (CBP) Task (Community Benefits Plan). . . . . . A logical subdivision of major efforts to complete a budget period . . . . . . . . . . . . .Budget Period ST Subtask . . . . . . . . . . . . . . . . . . . . . . An as needed logical subdivision of efforts to complete a task . . . . . . . . . . . . . . . . Task / Budget Period pair ST (CBP) Subtask (Community Benefits Plan) . . . An as needed logical subdivision of efforts to complete a task . . . . . . . . . . . . . . . . Task / Budget Period pair M Milestone . . . . . . . . . . . . . . . . . . . . . A significant event in a project that occurs at a point in time . . . . . . . . . . . . . . . . . Budget Period, a Task, or a Subtask M (CBP) Milestone (Community Benefits Plan) . . A significant event in a project that occurs at a point in time . . . . . . . . . . . . . . . . . .Budget Period, a Task, or a Subtask D Deliverable . . . . . . . . . . . . . . . . . . . . An input/output term that refers specifically to the unique and individual . . . . . . . . . Budget Period, a Task, or a Subtask products, elements, results, or items that are produced for delivery at the conclusion of a specific project WBS item, or at the conclusion of the project as a whole FD Final Deliverable . . . . . . . . . . . . . . . . Deliverables delivered at the conclusion of the project . . . . . . . . . . . . . . . . . . . . . Final Budget Period BT Bridge Task . . . . . . . . . . . . . . . . . . . . Recommended as a task that can be worked on while GNG is in process . . . . . . . . .Budget Period GNG Go/No-Go. . . . . . . . . . . . . . . . . . . . . . Project evaluation process that takes approximately 60 days . . . . . . . . . . . . . . . . .Budget Period DS Down Select . . . . . . . . . . . . . . . . . . . A competitive project review process during which a group of projects . . . . . . . . . .Budget Period are reviewed and down-selected to one project to continue to the next . . . . . . . . . .Budget Period ICDP Int. Critical Decision Point . . . . . . . . . . Internal Critical Decision Points are recommended when a formal . . . . . . . . . . . . . .Budget Period GNG budget split is not necessary, but a project review is necessary PM Project Management . . . . . . . . . . . . . Planning, verification, and controlling work done to support and complete project work (Deliverables need to show up under associated tasks) Project Management and Reporting is Section D in the SOPO

## III. Contractual Cost Summary
Contractual Cost Summary
Recipient Name: | MBARI | Agreement # (CID): |  |  | EE0009444
Reporting Period: | 07/01/2024 to 09/30/2024
Instructions:
FFRDC expenses should be excluded from quarterly reporting and reported directly to DOE by the lab(s).
Row 19-20: No Entry Required: Budget Periods dates are auto-populated from the Cover Page.
Column B: Should reflect the Organization or Individual responsible for performing the task (this pick list is auto-populated from your inputs in the Organizations tab)
Column C: Input a brief description about the purpose and basis of cost; this should mirror your Budget Justification.
Columns D-H: $ Amounts should mirror Budget Justification and stay static after initial inputs unless the Budget Justification is changed. Total amounts should mirror totals for same Budget Periods on Cost Summary tab (Column I will auto-calculate).
Column I: NO Entry Required. This column will auto-calculate total Budget Period inputs for Project Total.
Column J: Should be updated for the current reporting period (quarter) to reflect Quarterly Costs for each category.
Column K: Should be updated for the current reporting period (quarter) to reflect Cumulative Amounts for each category.
Column L: No Entry Required. This column will auto-calculate based on the actual quarterly costs and cumulative expenses.
Note: If you need additional rows, be sure to 'Copy' existing rows and 'Insert Copied Cells' for the drop-downs and conditional formatting to function properly.
Contractual Details |  | Approved Budget | [5 empty] | Actual Expenses
Budget Period Start Date: |  | 2021-10-01 | 2024-04-01 | 0 | 0 | 0
Budget Period End Date: |  | 2024-03-30 | 2026-03-31 | 0 | 0 | 0
Organization Name | Purpose and Basis of Cost | Budget Period 1 | Budget Period 2 | Budget Period 3 | Budget Period 4 | Budget Period 5 | Project Total | This Quarter | Cumulative | %
Open Source Robotics | Perform ROS integration, test, and export. Cost estimate based on personnel hours. | 509405 | 0 |  |  |  | 509405 |  | 509405 | 100%
Cooley | Legal counsel, terms of use agreement. Basis = Past costs | 7500 | 0 |  |  |  | 7500 |  | 0 | 0% | Not ever needed
Monterey Canyon Research Vessels | Buoy Deployment Ship time. Basis = Past costs | 6000 | 12000 |  |  |  | 18000 |  | 18000 | 100% | All Cost Shared deployments completed
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
[7 empty] | 0 |  |  | %
| TOTALS | 522905 | 12000 | 0 | 0 | 0 | 534905 | 0 | 527405 | 98.6%
End of Table

## IV. Cost Summary
Cost Summary
Cost Summary
Recipient Name: | MBARI |  |  |  | Agreement # (CID): |  | EE0009444
Reporting Period: | 07/01/2024 to 09/30/2024
Instructions:
Row 19-20: NO entry required: Budget Periods dates are auto-populated from the Cover Page .
Columns C-G: These column inputs should mirror the SF424A quarterly reporting and remain static after initial inputs (Column H will auto-calculate).
Row 32 of Columns C-G: Input Indirect Charge amounts for each Budget Period. The indirect rate should be applied to both the Federal and Recipient Cost Share. A Recipient who elects to employ the 10% de minimis Indirect Cost rate cannot claim resulting costs as a Cost Share contribution, nor can the Recipient claim "unrecovered indirect costs" as a Cost Share contribution. Neither of these costs can be reflected as actual indirect cost rates realized by the organization, and therefore are not verifiable in the Recipient records as required by Federal Regulation (§200.306(b)(1)).
Row 34 of Columns C-G: Input Recipient Share amounts for each Budget Period.
a. Cash Cost Share - encompasses all contributions to the project made by the recipient, subrecipient, or third party (an entity that does not have a role in performing the scope of work) for costs incurred and paid for during the project. This includes when an organization pays for personnel, supplies, equipment, etc. for their own company with organizational resources. If the item or service is reimbursed for, it is cash cost share. All cost share items must be necessary to the performance of the project. Contractors may not provide cost share. Any partial donation of goods or services is considered a discount and is not allowable. b. In Kind Cost Share - encompasses all contributions to the project made by the recipient, subrecipient, or third party (an entity that does not have a role in performing the scope of work) where a value of the contribution can be readily determined, verified and justified but where no actual cash is transacted in securing the good or service comprising the contribution. In Kind cost share items include volunteer personnel hours, the donation of space or use of equipment, etc. The cash value and calculations thereof for all In Kind cost share items must be justified and explained in the Cost Share Item section below. All cost share items must be necessary to the performance of the project. If questions exist, consult your DOE contact before filling out In Kind cost share in this section. Contractors may not provide cost share. Any partial donation of goods or services is considered a discount and is not allowable. c. Funds from other Federal sources MAY NOT be counted as cost share. This prohibition includes FFRDC sub-recipients. Non-Federal sources include any source not originally derived from Federal funds. Cost sharing commitment letters from subrecipients and third parties must be provided with the original application. d. Fee or profit, including foregone fee or profit, are not allowable as project costs (including cost share) under any resulting award. The project may only incur those costs that are allowable and allocable to the project (including cost share) as determined in accordance with the applicable cost principles prescribed in FAR Part 31 for For-Profit entities and 2 CFR Part 200 Subpart E - Cost Principles for all other non-federal entities. e. NOTE: A Recipient who elects to employ the 10% de minimis Indirect Cost rate cannot claim the resulting indirect costs as a Cost Share contribution. f. NOTE: A Recipient cannot claim "unrecovered indirect costs" as a Cost Share contribution, without prior approval.
Column H: NO Entry Required: This column will auto-calculate.
Column I: Should be updated for the current reporting period (quarter) to reflect Quarterly Costs for each category. Note: This column should mirror the SF-425.
Column J: Should be updated for the current reporting period (quarter) to reflect Cumulative Amounts for each category.
Column K: No Entry Required: This column will auto-calculate based on the actual quarterly costs and cumulative expenses.
Row 35-36: No Entry Required: This column will auto-calculate based on total charges, Federal and Recipient share amounts.
Cost Summary by Budget Category
Approved Budget per SF-424A | [6 empty] | Actual Expenses
Budget Period Start Date: | 2021-10-01 | 2024-04-01 | 0 | 0 | 0
Budget Period End Date: | 2024-03-30 | 2026-03-31 | 0 | 0 | 0
Budget Categories | Budget Period 1 | Budget Period 2 | Budget Period 3 | Budget Period 4 | Budget Period 5 | Total | This Quarter | Cumulative | %
a. Personnel | 160877 | 274394 |  |  |  | 435271 |  | 219066 | 50.33%
b. Fringe Benefits | 91941 | 148173 |  |  |  | 240114 |  | 118295 | 49.27%
c. Travel | 6480 | 6000 |  |  |  | 12480 |  | 0 | 0%
d. Equipment | [5 empty] | 0 |  |  | %
e. Supplies |  | 16000 |  |  |  | 16000 |  | 0 | 0%
f. Contractual | 522905 | 12000 | 0 | 0 | 0 | 534905 |  | 534905 | 100%
g. Construction | [5 empty] | 0 |  |  | %
h. Other | 0 | 0 |  |  |  | 0 |  |  | %
i. Total Direct Charges | 782203 | 456567 | 0 | 0 | 0 | 1238770 | 0 | 872266 | 70.41%
j. Indirect Charges | 156344 | 239697 |  |  |  | 396041 |  | 177115 | 44.72%
k. Total Charges | 938547 | 696264 | 0 | 0 | 0 | 1634811 | 0 | 1049381 | 64.19%
Recipient Share | 136892 | 127142 |  |  |  | 264034 |  | 164546 | 62.32%
Federal (DOE) Share | 801655 | 569122 | 0 | 0 | 0 | 1370777 | 0 | 884835 | 64.55%
Recipient Share Percentage | 14.59% | 18.26% | % | % | % | 16.15% | % | 15.68% | 97.09%
End of Table

## V. Spend Plan
Spend Plan
Recipient Name: |  |  | MBARI |  | Agreement # (CID): |  | EE0009444
Reporting Period: |  |  | 07/01/2024 to 09/30/2024
Instructions:
Columns B-E: No Entry Required; these columns are auto-populated (Cell D16) based on Project Start Date entered on Cover Page and reflect the Federal Fiscal Quarterly Calendar. Note: This is a cumulative report; these dates will remain static throughout the life of the project.
Column F: Input Initial Federal Share amounts with your planned spending for the entire project. Planned spend means when the project team anticipates incurring costs. Do NOT update Initial Fed Plan columns for each reporting period.
Column G: Input Actual Federal Share spend amounts for the current reporting period (quarter).Incentive Selectees, please input your actual spend amount for this reporting period.
Column H: No entry required: this column will auto-calculate.
Column I: Input Initial Recipient Share amounts with your planned spending for the entire project. Planned spend means when the project team anticipates incurring costs. Do NOT update Initial Recipient Plan columns for each reporting period. Incentive Selectees, please leave blank.
Column J: Input Actual Recipient Share spend amounts for the current reporting period (quarter). Incentive Selectees, please leave blank.
Columns K-L: No Entry Required, these columns will auto-calculate.
Project Spend Plan |  |  |  | Federal Share |  |  | Recipient Share/Project Costs |  |  | Cumulative
FY | FY-Q | From | To | Initial Fed Plan | Actual Federal | Federal Cumulative | Initial Recipient/Project Costs Plan | Actual Recipient/Project Costs | Recipient/Project Costs Cumulative | Cumulative Total Project Costs
2022 | Q1 | 2021-10-01 | 2021-12-31 |  |  | 0 |  |  | 0 | 0
2022 | Q2 | 2022-01-01 | 2022-03-31 |  |  | 0 |  |  | 0 | 0
2022 | Q3 | 2022-04-01 | 2022-06-30 |  |  | 0 |  |  | 0 | 0
2022 | Q4 | 2022-07-01 | 2022-09-30 |  |  | 0 |  |  | 0 | 0
2023 | Q1 | 2022-10-01 | 2022-12-31 |  |  | 0 |  |  | 0 | 0
2023 | Q2 | 2023-01-01 | 2023-03-31 |  |  | 0 |  |  | 0 | 0
2023 | Q3 | 2023-04-01 | 2023-06-30 |  |  | 0 |  |  | 0 | 0
2023 | Q4 | 2023-07-01 | 2023-09-30 |  |  | 0 |  |  | 0 | 0
2024 | Q1 | 2023-10-01 | 2023-12-31 |  |  | 0 |  |  | 0 | 0
2024 | Q2 | 2024-01-01 | 2024-03-31 |  |  | 0 |  |  | 0 | 0
2024 | Q3 | 2024-04-01 | 2024-06-30 |  |  | 0 |  |  | 0 | 0
2024 | Q4 | 2024-07-01 | 2024-09-30 |  |  | 0 |  |  | 0 | 0
2025 | Q1 | 2024-10-01 | 2024-12-31 |  |  | 0 |  |  | 0 | 0
2025 | Q2 | 2025-01-01 | 2025-03-31 |  |  | 0 |  |  | 0 | 0
2025 | Q3 | 2025-04-01 | 2025-06-30 |  |  | 0 |  |  | 0 | 0
2025 | Q4 | 2025-07-01 | 2025-09-30 |  |  | 0 |  |  | 0 | 0
2026 | Q1 | 2025-10-01 | 2025-12-31 |  |  | 0 |  |  | 0 | 0
2026 | Q2 | 2026-01-01 | 2026-03-31 |  |  | 0 |  |  | 0 | 0
2026 | Q3 | 2026-04-01 | 2026-06-30 |  |  | 0 |  |  | 0 | 0
2026 | Q4 | 2026-07-01 | 2026-09-30 |  |  | 0 |  |  | 0 | 0
2027 | Q1 | 2026-10-01 | 2026-12-31 |  |  | 0 |  |  | 0 | 0
2027 | Q2 | 2027-01-01 | 2027-03-31 |  |  | 0 |  |  | 0 | 0
2027 | Q3 | 2027-04-01 | 2027-06-30 |  |  | 0 |  |  | 0 | 0
2027 | Q4 | 2027-07-01 | 2027-09-30 |  |  | 0 |  |  | 0 | 0
2028 | Q1 | 2027-10-01 | 2027-12-31 |  |  | 0 |  |  | 0 | 0
2028 | Q2 | 2028-01-01 | 2028-03-31 |  |  | 0 |  |  | 0 | 0
2028 | Q3 | 2028-04-01 | 2028-06-30 |  |  | 0 |  |  | 0 | 0
2028 | Q4 | 2028-07-01 | 2028-09-30 |  |  | 0 |  |  | 0 | 0
Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0% |  | Federal Spend Plan total is less than the Cost Summary. |  |  | Recipient Spend Plan total is less than the Cost Summary. |  | 0%
End of Table
Formulas:
From = IF([To, row above]="", "", DATE(YEAR([To, row above]) + IF(MONTH([To, row above]) >= 10, 1, 0), IF(OR(MONTH([To, row above])={1,2,3}), 4, IF(OR(MONTH([To, row above])={4,5,6}), 7, IF(OR(MONTH([To, row above])={7,8,9}), 10, 1))), 1))
From = IFERROR(EDATE([From, row above],3),"")
To = IFERROR(DATE(YEAR([From]),((INT((MONTH([From])-1)/3)+1)*3)+1,1)-1,"")
To = IF(TRIM([From])="","",CHOOSE(MATCH(MONTH([From]),{1,4,7,10}),DATE(YEAR([From]),3,31),DATE(YEAR([From]),6,30),DATE(YEAR([From]),9,30),DATE(YEAR([From]),12,31)))

## VI. Products
Products
Recipient Name: |  | MBARI |  |  | Agreement # (CID): | EE0009444
Reporting Period: |  | 07/01/2024 to 09/30/2024
Instructions:
Table 1: Products
This is a cumulative report that will be used throughout the lifecycle of the project, DO NOT delete previously listed products, status changes can be made in their respective columns.
Acknowledgement of Federal Support is required. If acknowledgement was not included, recipients must remedy prior to publication/dissemination to the public (Column O) Legal disclaimer is required. If the legal disclaimer was not included, recipients must remedy prior to publication/dissemination to the public (Column P).
Column B: Select the Product type (if Other, please specify in Column C). Additional information can be found in the Column B table header.
Columns D-Y: Fill out each column based on your product type as applicable, required cells will be highlighted upon product type selection in Column B.
Columns: Z-AC: Be sure to make your official submissions using the links provided for each product.
Note: If you need additional rows, be sure to 'Copy' existing rows and 'Insert Copied Cells' for the drop-downs and conditional formatting to function properly.
For more information, please review the following FAQs: |  |  |  | Accepted Manuscripts FAQs | Conference Products FAQs | Invention Reporting FAQs
Follow-On Funding
Table 2: Follow-On Funding
Follow-on-funding should be tracked for research, commercialization, pilot, and demonstration projects. This data should include funding raised by spinoffs or startups from the original awardee if for the development of the same technology for which funding was provided.
Columns B/C: Select the Form of Investment (if Other, please specify in Column D).
Columns E-F: Input Investor's First and Last Name.
Column G: Please input the Investor's UEI (Unique Entity ID) number (this can be found at SAM.GOV). if applicable or indicate N/A
Column H: Input Invested $ Amount to Date.
Column I: Select Yes or No to appropriately identify if Public Disclosure has occurred. (if Yes, please specify where in Column J).
Note: If you need additional rows, be sure to copy and paste existing rows so that the drop-down menus and conditional formatting function properly.
Products
General Information | [9 empty] | Scientific, Technical, Manuals, Datasets, and Websites | Publications | [5 empty] | Conference Products |  |  |  | Inventions, Patents, & Licenses |  | Other | Where to Submit Products
Product Type | If Product is Other, Specify Product Type | OSTI ID | DOI/ISBN (if applicable) | Author/Speaker/Owner/Inventor (First Name) | Author/Speaker/Owner/Inventor (Last Name) | Author/Speaker/Owner(s) Title or Licensees (as applicable) | Author/Speaker/Owner Affiliation (Prime or Subrecipient) | Title of Product | Web URL (if applicable) | Description of Project Information | Publication Type (Abstract, Book, Dissertation, Journal Publication, Thesis, Other) | If Other, Specify Publication Type | Publication Date/ Date Issued | Status (Planned, In Development, Submitted, Accepted, Published) | Acknowledgement of Federal Support (Yes/No) | Legal Disclaimer Language (Yes/No) | Conference Name | Conference Date | Conference Product Type (Paper, Proceeding, Presentation, Other) | If Other, Specify Conference Type | Extramural Invention Report (EIR) or "S" Number | Patent Status (patent application filed, patent granted, patent not accepted) | Significance of Contribution to the Project | Submission Links
Software | [7 empty] | MBAR_WEC Entrypoint | https://osrf.github.io/mbari_wec/main/ | Entrypoint for using MBARI WEC Simulation Software | [12 empty] | This is one of the main software developments | OSTI Datasets | DOE CODE | OSTI | iEdison
Websites | [7 empty] | MBARI WEC Documentation | https://osrf.github.io/mbari_wec/main/ | MBARI WEC User Manual And Tutorials | [12 empty] | This is one of the main software developments | OSTI Datasets | DOE CODE | OSTI | iEdison
Software | [7 empty] | mbari_wec_gz | https://github.com/osrf/mbari_wec_gz | Gazebo Code for MBARI WEC implementation | [12 empty] | This is one of the main software developments | OSTI Datasets | DOE CODE | OSTI | iEdison
Software | [7 empty] | mbari_wec_utils | https://github.com/osrf/mbari_wec_utils | Utility Code for MBARI WEC implementation | [12 empty] | This is one of the main software developments | OSTI Datasets | DOE CODE | OSTI | iEdison
Software | [7 empty] | Free Surface Hydrodynamics | https://github.com/hamilton8415/FreeSurfaceHydrodynamics | Free Surface Hydrodynamics Library | [12 empty] | This is one of the main software developments | OSTI Datasets | DOE CODE | OSTI | iEdison
Publication |  |  |  | Andrew | Hamilton |  |  |  | https://www.mdpi.com/2076-3417/14/23/11169 | Journal Publication | Journal Publication |  | 2024-09-29 | Published | Yes | [7 empty] | An Overview of Simulation Capabilties are putlined here | OSTI Datasets | DOE CODE | OSTI | iEdison
Conference |  |  |  | Andrew | Hamilton |  |  |  | https://nps.edu/web/nps-video-portal/-/energy-harvesting-and-autonomous-underwater-vehicle-docking-to-power-a-persistent-presence-of-oceanographic-instrumentation | Seminar Presenation - Defense Industry Seminar | [6 empty] | Defense Industry Seminar | 2024-05-14 | Presentation |  |  |  |  | OSTI Datasets | DOE CODE | OSTI | iEdison
Conference |  |  |  | Andrew | Hamilton |  |  |  | https://www.youtube.com/watch?v=dDWNg4U4FoE | Online Seminar Presenation - Software Demo Days | [6 empty] | Sofware Demo Days | 2025-06-02 | Presentation |  |  |  |  | OSTI Datasets | DOE CODE | OSTI | iEdison
[24 empty] | OSTI Datasets | DOE CODE | OSTI | iEdison
[24 empty] | OSTI Datasets | DOE CODE | OSTI | iEdison
[24 empty] | OSTI Datasets | DOE CODE | OSTI | iEdison
[24 empty] | OSTI Datasets | DOE CODE | OSTI | iEdison
[24 empty] | OSTI Datasets | DOE CODE | OSTI | iEdison
[24 empty] | OSTI Datasets | DOE CODE | OSTI | iEdison
[24 empty] | OSTI Datasets | DOE CODE | OSTI | iEdison
[24 empty] | OSTI Datasets | DOE CODE | OSTI | iEdison
[24 empty] | OSTI Datasets | DOE CODE | OSTI | iEdison
[24 empty] | OSTI Datasets | DOE CODE | OSTI | iEdison
End of Table
Follow-On Funding
Form of Investment |  | If Other, Please Specify | Investor First Name | Investor Last Name | Investor UEI | Invested $ Amount to Date | Publicly Disclosed | If Yes, Please Specify How
End of Table
Note on B26: PUBLICATIONS: List peer-reviewed articles or papers that have been submitted for publication in scientific, technical, or professional journals or periodically published proceedings of a scientific society, or the like. Report any book, monograph, dissertation, abstract, or the like published or in a separate publication, rather than a periodical or series. Report any technical reports resulting from information or data produced under the award. CONFERENCES: Report any conference proceedings, papers, and/or presentations resulting from information or data produced under the award. SCIENTIFIC/TECHNICAL SOFTWARE, MANUALS, DATASETS, & WEBSITES: The prime recipient must submit all software, datasets or website deliverables created under the award, as well as any accompanying documentation or manuals to the DOE CODE submission E-link. Include a description of the information located on any internet sites that disseminate the results of the research. INVENTIONS, PATENTS, LICENSES: Submission of this information as part of an interim report or Final Technical Report is not a substitute for any other invention reporting required under the Terms and Conditions of an award. Recipients are required to report inventions and patents directly to iEdison in addition to listing here. For more information, see section I. D. Intellectual Property Reporting. OTHER: Identify any other significant products that were developed under this project. Describe the product and how it is contributing to this project. Examples of other products are: workshops, webinars, technical assistance, media mentions, private capital leveraged, databases, physical collections, audio or video products, NetWare; models; educational aids or curricula; instruments or equipment; research materials; clinical or educational interventions; new business creation; etc...

## VII. Participants
Participants
Recipient Name: | MBARI |  | Agreement # (CID): | EE0009444
Reporting Period: | 07/01/2024 to 09/30/2024
Instructions:
This is a cumulative report that will be used throughout the lifecycle of the project, DO NOT delete previously listed participants.
The following information on participants (individuals) was provided during award negotiations. On a quarterly basis, provide updates as needed. For most projects, recipients must identify and provide specific information for the following individuals at the prime and subrecipient level: (1) all senior and key personnel (including project director(s)/principal investigator(s); and (2) each person who has worked or is expected to work at least 160 hours on the project at least one person month per year on the project regardless of the source of compensation (a person month equals approximately 160 hours of effort). In limited circumstances, typically large-scale construction projects, recipients are only required to report on (1) senior and key personnel for the prime recipient and subrecipients. Please refer to the Participants and Other Collaborating Organizations Term in your award Terms and Conditions to determine what level of reporting is required for your specific award.
Column B: Should reflect the Organization responsible for performing the task (this pick-list is auto-populated from your inputs in the Organizations tab)
Columns C-D: Input First Name and Last Name of Participant.
Column E: Enter Job Title of Participant (ex: Professional, Technician, K-12 Teacher, Graduate Student)
Column F: Select the Participant's Role in the Project. If "Other" is selected, please specify in Column G.
Column G: Enter U.S. State or Territory of Residence of Participant.
Column H: Enter Country of Residence if NOT the United States of Participant.
Column I: Select Yes or No to identify if the Participant has collaborated with an Individual from a Foreign Entity during the period of performance.
Column J: Enter Associated Country(ies) of Foreign Collaborator.
Columns K-L: Input Start and End Dates for Participant's Partnership; if they are still currently performing in their role indicate N/A for the End date.
Note: If you need additional rows, be sure to 'Copy' existing rows and 'Insert Copied Cells' for the drop-downs and conditional formatting to function properly.
Participants
Participant Information | [5 empty] | Residence of Participant |  |  |  | Participant Dates
Organization | First Name | Last Name | Job Title | Role in the Project | If the Role in the Project is Other, Please Specify | U.S. State or Territory of Residence | Country of Residence if not the United States | Has this person collaborated with an Individual from a Foreign Entity? | Associated Country(ies) of Foreign Collaborator | Participant Start Date | Participant End Date
| Andrew | Hamilton | Engineering Division Chair | PD/PI |  | CA |  |  |  | 2021-10-01 | 2026-04-01
| Michael | Anderson | Software Engineer | Other | Software Engineer |  |  |  |  | 2021-10-01 | 2026-04-01
Open Source Robotics | Lousie | Poubel | Software Engineer | Other | Software Engineer | CA
Open Source Robotics | Tully | Foote | Software Engineer | PD/PI |  | CA
Open Source Robotics | Lousie | Poubel | Software Engineer | Other | Software Engineer | CA
Open Source Robotics | Lousie | Poubel | Software Engineer | Other | Software Engineer | CA
Monterey Canyon Research Vessels | Jim | Christman | Ship Captain | Other | Ship Captain | CA |  |  |  | 2021-10-01 | 2026-04-01
| Chris | Dizon | Post Doc | Student | Researcher - OSU | OR
End of Table

## EVM
Earned Value Management
Recipient Name: | MBARI | Agreement # (CID): | EE0009444
Reporting Period: | 07/01/2024 to 09/30/2024 | 0
Instructions:
Row 13: No entry required; this is auto-populated based on values entered in the cost summary tab.
Columns C-E, Rows 13-14: Enter the earned value, planned value and actual costs for the total project, federal share and recipient share. Incentive Selectees, Please leave columns D & E blank.
Rows 17-21: No entry required: The form will auto-calculate SPI, CPI and EAC based on the values included above.
Earned Value Management Reporting
| TOTAL $ | Fed Share $ | Recipient Share $
Total Budget | 1634811 | 1370777 | 264034
Earned Value
Planned Value
Actual Costs
Schedule Performance Index | % | % | %
Cost Performance Index | % | % | %
Estimated at Completion | $ | $ | $
EAC Variance | % | % | %
| will overspend | will overspend | will overspend
Note on B14: Budget * % of work completed (DOE$ + Costshares$) * (Completed Work / Total Work)
Note on B15: BUDGETED cost through the current calendar date SUM of: Planned Federal Share AND/OR Planned Recipient Share
Note on B16: ACTUAL cost through the current calendar date SUM of: Actual Federal Share AND/OR Actual Recipient Share
Note on B17: SPI measures progress achieved against progress planned SPI = EV/PV - An SPI <1.0 indicates less work was completed than planned - An SPI >1.0 indicates more work was completed than planned
Note on B18: CPI measures the value of work completed against the actual cost CPI = EV/AC - A CPI <1.0 indicates costs were higher than budgeted - A CPI >1.0 indicates costs were less than budgeted
Note on B19: A forecast of how much the total project will cost if current trends continue EAC = Total Project Budget / CPI

## Sources (hidden)
Tech Assistance Topics |  |  | Project Roles |  |  |  | Products |  | Task/Milestone Codes
Solar Installation |  |  | PD/PI |  |  |  | Conference |  | BP | BP Budget Period | ANNH_Alaska Native-Serving and Native Hawaiian
Finance |  |  | Co PD/PI |  |  |  | Datasets |  | T | T TASK | ANNHF_Alaska Native-Serving and Native Hawaiian
Procurement/Requests for Proposals |  |  | Faculty |  |  |  | Inventions |  | T (CBP) | T TASK (Community Benefits Plan) | AANAPISI_Asian American and Native American Pacific Islander
Policy Design (e.g. Virtual Net Metering) |  |  | Community College Faculty |  |  |  | Licenses |  | ST | ST Subtask | HSI_Hispanic-Serving Institution
Solar Market Status |  |  | Technical School Faculty |  |  |  | Manuals |  | ST (CBP) | ST Subtask (Community Benefits Plan) | HSISTEM(F)_Hispanic-Serving Institution
Zoning/Permitting/Planning |  |  | K-12 Teacher |  |  |  | N/A |  | M | M Milestone | MSEIP_Minority Science and Engineering Improvement Program
Other Item Not Listed (please provide descriptive text in next column) |  |  | Postdoctoral (scholar, fellow or other postdoctoral position) |  |  |  | Other |  | M (CBP) | M Milestone (Community Benefits Plan) | NASNTI_Native American Non-Tribal Institutions
|  |  | Other Professional |  |  |  | Patents |  | M (Cyber) | M Cybersecurity | NASNTIF_Native American Non-Tribal Institutions
|  |  | Technician |  |  |  | Publication |  | D | D Deliverable | PBIA_Predominantly Black Institutions
Degree Types | Follow-On Funding |  | Staff Scientist (doctoral level) |  |  |  | Software |  | FD | FD Final Deliverable | PBIF_Predominantly Black Institutions
BS | Venture Capital Series A |  | Statistician |  |  |  | Websites |  | BT | BT Bridge Task | PBIMDElig_Predominantly Black Institutions
MS | Venture Capital Series B |  | Graduate Student (research assistant) | [5 empty] | GNG | GNG Go/No Go | PPOHA_Promoting Postbaccalaureate Opportunities for Hispanic Americans
PhD | Venture Capital Series C |  | Non-Student Research Assistant | [5 empty] | ICDP | ICDP Internal Critical Decision Point | SIP_Strengthening Institutions Program
Postdoc | Private Equity |  | Undergraduate Student | [5 empty] | PM | PM Project Management | SIPFElig_Strengthening Institutions Program
Non-Degree Trainee | Debt |  | Technical School Student | [7 empty] | HBCU_Historically Black Colleges and Universities
| IPO (Initial Public Offering) |  | High School Student | [5 empty] | CBP Task Kind |  | HBGI_Historically Black Graduate Institutions
| Other |  | Community Representative | [5 empty] | Jobs |  | HBCUMasters_Historically Black Colleges and Universities
|  |  | Consultant | [5 empty] | J40 | Partner Type | TCCU_Tribally Controlled Colleges and Universities
|  |  | Research Experience for Undergraduates (REU) Participant | [5 empty] | DEIA | Prime
|  |  | Other (specify) |  |  |  | Participant Contribution |  | CE | Subrecipient
Reporting Periods |  |  | Community Stakeholder |  |  |  | PD/PI |  |  | Contractor
2018-07-01 | 2018-09-30 |  | Labor Stakeholder |  |  |  | Co PD/PI |  |  | Partners | Ownership Type
10/1/2018 | 2018-12-31 |  |  | Allowable Reporting Years |  |  | Business Contact |  | Project Type | Collaborating Organizations | Alaskan Native Corporation Owned Firm ​
2019-01-01 | 2019-03-31 | 01/01/2020 to 03/31/2020 |  | 2020 |  |  | Faculty |  | Infrastructure/Non-Construction | CBP Partner | Asian-Pacific American Owned​
2019-04-01 | 2019-06-30 | 04/01/2020 to 06/30/2020 |  | 2021 |  |  | Student |  | Infrastructure/Construction | U.S. National Laboratories | Black American Owned ​
2019-07-01 | 2019-09-30 | 07/01/2020 to 09/30/2020 |  | 2022 |  |  | Consultant |  | All Other Projects |  | Hispanic American Owned ​
2019-10-01 | 2019-12-31 | 10/01/2020 to 12/31/2020 |  | 2023 | State |  | Other |  |  | Organization Type | Native American Owned ​
2020-01-01 | 2020-03-31 | 01/01/2021 to 03/31/2021 |  | 2024 | AL |  |  |  |  | For Profit | Native Hawaiian Organization Owned Firm ​
2020-04-01 | 2020-06-30 | 04/01/2021 to 06/30/2021 |  | 2025 | AK | Month | Day | Year |  | Governmental | Subcontinent Asian (Asian-Indian) American Owned ​
2020-07-01 | 2020-09-30 | 07/01/2021 to 09/30/2021 |  | 2026 | AZ | 1 | 1 | 2020 |  | Non-Profit​ (Not University) | Tribally Owned Firm​
2020-10-01 | 2020-12-31 | 10/01/2021 to 12/31/2021 |  | 2027 | AR | 2 | 2 | 2021 |  | Other J40 Relevant Organizations | Veteran Owned Business ​
2021-01-01 | 2021-03-31 | 01/01/2022 to 03/31/2022 |  | 2028 | AS | 3 | 3 | 2022 |  | Small Business​ (For Profit) | Woman Owned Business​
2021-04-01 | 2021-06-30 | 04/01/2022 to 06/30/2022 |  | 2029 | CA | 4 | 4 | 2023 |  | University (MSI​) | OTHER
2021-07-01 | 2021-09-30 | 07/01/2022 to 09/30/2022 |  | 2030 | CO | 5 | 5 | 2024 |  | University (Non-MSI) | UNKNOWN
2021-10-01 | 2021-12-31 | 10/01/2022 to 12/31/2022 |  |  | CT | 6 | 6 | 2025 |  | UNKNOWN | Federal
2022-01-01 | 2022-03-31 | 01/01/2023 to 03/31/2023 |  |  | DE | 7 | 7 | 2026 |  |  | Local
2022-04-01 | 2022-06-30 | 04/01/2023 to 06/30/2023 |  |  | FL | 8 | 8 | 2027 |  |  | State
2022-07-01 | 2022-09-30 | 07/01/2023 to 09/30/2023 |  |  | FM | 9 | 9 | 2028 |  |  | Tribal Government​
2022-10-01 | 2022-12-31 | 10/01/2023 to 12/31/2023 |  |  | GA | 10 | 10 | 2029 |  |  | AbilityOne Non-Profit Agency​
2023-01-01 | 2023-03-31 | 01/01/2024 to 03/31/2024 |  |  | GU | 11 | 11 | 2030 |  |  | Community Development Corporation Owned Firm​
2023-04-01 | 2023-06-30 | 04/01/2024 to 06/30/2024 |  |  | HI | 12 | 12 |  |  |  | Housing Authorities Public/Tribal​
2023-07-01 | 2023-09-30 | 07/01/2024 to 09/30/2024 |  |  | ID |  | 13 |  |  |  | Small Agricultural Cooperative​
2023-10-01 | 2023-12-31 | 10/01/2024 to 12/31/2024 |  |  | IL |  | 14 |  |  |  | SBA Certified 8(a) Program Participant ​
2024-01-01 | 2024-03-31 | 01/01/2025 to 03/31/2025 |  |  | IN |  | 15 |  |  |  | Alaskan Native Servicing Institution​
2024-04-01 | 2024-06-30 | 04/01/2025 to 06/30/2025 |  |  | IA |  | 16 |  |  |  | Hispanic Servicing Institution​ (HSI)
2024-07-01 | 2024-09-30 | 07/01/2025 to 09/30/2025 |  |  | KS |  | 17 |  |  |  | Historically Black College or University (HBCU)
2024-10-01 | 2024-12-31 | 10/01/2025 to 12/31/2025 |  |  | KY |  | 18 |  |  |  | Native Hawaiian Servicing Institution​
2025-01-01 | 2025-03-31 | 01/01/2026 to 03/31/2026 |  |  | LA |  | 19 |  |  |  | Tribal College​ and University (TCU)
2025-04-01 | 2025-06-30 | 04/01/2026 to 06/30/2026 |  |  | ME |  | 20 |  |  |  | 4-year College
2025-07-01 | 2025-09-30 | 07/01/2026 to 09/30/2026 |  |  | MD |  | 21 |  |  |  | Technical/Community College
2025-10-01 | 2025-12-31 | 10/01/2026 to 12/31/2026 |  |  | MA |  | 22
2026-01-01 | 2026-03-31 | 01/01/2027 to 03/31/2027 |  |  | MH |  | 23
2026-04-01 | 2026-06-30 | 04/01/2027 to 06/30/2027 |  |  | MI |  | 24
2026-07-01 | 2026-09-30 | 07/01/2027 to 09/30/2027 |  |  | MN |  | 25
2026-10-01 | 2026-12-31 | 10/01/2027 to 12/31/2027 |  |  | MS |  | 26
2027-01-01 | 2027-03-31 | 01/01/2028 to 03/31/2028 |  |  | MO |  | 27
2027-04-01 | 2027-06-30 | 04/01/2028 to 06/30/2028 |  |  | MP |  | 28
2027-07-01 | 2027-09-30 | 07/01/2028 to 09/30/2028 |  |  | MT |  | 29
2027-10-01 | 2027-12-31 | 10/01/2028 to 12/31/2028 |  |  | NE |  | 30
2028-01-01 | 2028-03-31 | 01/01/2029 to 03/31/2029 |  |  | NV |  | 31
2028-04-01 | 2028-06-30 | 04/01/2029 to 06/30/2029 |  |  | NH
2028-07-01 | 2028-09-30 | 07/01/2029 to 09/30/2029 |  |  | NJ
2028-10-01 | 2028-12-31 | 10/01/2029 to 12/31/2029 |  |  | NM
2029-01-01 | 2029-03-31 | 01/01/2030 to 03/31/2030 |  |  | NY
2029-04-01 | 2029-06-30 | 04/01/2030 to 06/30/2030 |  |  | NC
2029-07-01 | 2029-09-30 | 07/01/2030 to 09/30/2030 |  |  | ND
2029-10-01 | 2029-12-31 |  |  |  | OH
2030-01-01 | 2030-03-31 |  |  |  | OK
2030-04-01 | 2030-06-30 |  |  |  | OR
2030-07-01 | 2030-09-30 |  |  |  | PA
PR
TRLS |  |  |  |  | PW
TRL 1 |  |  |  |  | RI
TRL 2 |  |  |  |  | SC
TRL 3 |  |  |  |  | SD
TRL 4 |  |  |  |  | TN
TRL 5 |  |  |  |  | TX
TRL 6 |  |  |  |  | UM
TRL 7 |  |  |  |  | UT
TRL 8 |  |  |  |  | VT
TRL 9 |  |  |  |  | VA
N/A |  |  |  |  | VI
WA
WV
WI
WY
Formulas:
Follow-On Funding = EDATE([Tech Assistance Topics],3)-1
Tech Assistance Topics = EDATE([Tech Assistance Topics, row above],3)