## Sheet1
Completion Month
| Milestone | Percent Completed | Scheduled | Actual
1.7.1 | ROS Running on MBARI WEC Computer | 100% | 6
2.2.1 | Simulator selected | 100% | 5 | 5
2.8.1 | Simulator integrated | 10% | 8
3.4.1 | All software packages are published publicaly | 0% | 9
4.3.1 | MBARI control running in ROS system | 100% | 9 | 4
5.3.1 | Portal ready to launch | 0% | 9
6.2.1 | Webinar completed | 0% | 11
7.2.1 | Buoy Deployed | 0% | 16
8.2.1 | Successful on-buoy use of user code | 0% | 21
9.1.1 | Workshop or online training completed | 0% | 16