## Y3 Estimates for Pete
USGS - L. Michigan
Updated: | 2023-03-16
Expenses for an extended deployment during summer 2023
First will be eastern L. Erie, then L. Michigan
Two LRAUV's
--one with bioacoustics nosecone
--one with Archival ESP
(second ESP provided so samples can be gathered in two lakes)
MBARI financial breakdown:
2023
|  |  |  | Yr 1 |  | Y3 SOW Assumptions:
SALARIES/WAGES |  |  |  | # Hours | Y1 Charge |  | -- Three, 9 day deployments in L. Erie, L. Michigan and L. Superior
-- two vehicles: Archive ESP and Bioacoustic nosecone (Ahi & Aku)
| Research Technician (Weinstock) |  |  | 40 |  |  | -- USGS recovers and transports vehicles
| Research Specialist (Preston) |  |  | 72
| Software Engineer (Kieft) |  |  | 104 |  | Deployment 'Tasks' | Action | People | Nights | person/nights |  | Kieft | Hobson | Preston | Weinstock | Shemet | total hrs
| Mechanical Engineer (Hobson) |  |  | 64 |  | 1 | Trip 1 - unpack, prep and test in Ann Arbor | 2 | 4 | 8 |  | 40 |  | 40 |  |  | 80
| Research Engineer (Shemet) |  |  | 140
| Total Reg Salary |  |  | 420 | 41175 | 2 | Trip 2 - Assist launch of bioac into Lake Superior | 1 | 3 | 3 |  |  | 32 |  |  |  | 32
[7 empty] | piloting assist in Lake Superior | [8 empty] | 27
| BENEFITS | (Rate-Reg) | 57.15% |  | 23531.5125 | 3 | Trip 3 - Assist launch of bioac and eDNA into Lake Michigan | 1 | 3 | 3 |  | 32 |  |  |  |  | 32
[7 empty] | piloting assist in Lake Michigan | [8 empty] | 27
| TOTAL SAL & BEN |  |  |  | 64706.5125 | 4 | Trip 4 Service ESP at GLERL | 2 | 3 | 6 |  |  |  | 32 |  | 32 | 64
Supplies | [5 empty] | 5 | Trip 5 Assist with launch of bioac and eDNA into L. Erie | 1 | 3 | 3 |  |  | 32 |  |  |  | 32
| Reagents, filters, o-rings, cartridge parts, |  |  |  | 1000 |  | piloting assistance in Lake Erie | [8 empty] | 27
| LRAUV parts for upgrade |  |  |  | 13000 |  | piloting assistance in Lake Huron | [8 empty] | 27
Travel | [5 empty] | 6 | Trip 6 - pull cartridges and pack up | 2 | 3 | 6 |  | 32 |  |  | 40 |  | 72
| Deployment Travel/Lodging |  |  |  | 19084 | [11 empty] | 0
Shipping
| Shipping (both directions) |  |  |  | 9500 |  | Contingency | [9 empty] | 0
| Subtotal Expenses |  |  |  | 42584 |  |  |  |  | 29 |  | 104 | 64 | 72 | 40 | 140 | 312
Total Direct Costs |  |  |  |  | 107290.5125 |  |  | Lodging | @ $200/night | 27 | 5800
[8 empty] | Food/Incidentals | @ $69/day | 36 | 2484
Total Indirect Costs |  | Rate: | 52.5% |  | 56328 |  |  | Car Rental | 3 wks @ $600/wk |  | 1800
[8 empty] | Airfare | 9 flights @ $1000 |  | 9000
TOTAL DIRECT & INDIRECT COSTS |  |  |  |  | 163618.5125 | [5 empty] | 19084

## Sheet1
1 | Truck picks up container at GLERL on 6/12
2 | Truck delivers container to GLEERL on 6/19 | Y1
3 | Trip 1, Brian and Chris Preston fly to Detroit 6/19 unpack, prep and test the vehicles, at GLERL and Lake Erie
4 | USGS moves the the bioac vehicle up to Grand Marais, Lake Superior
5 | Trip 2: I go out to help them deploy into Lake Superior on Aug. 5th . Fly in/out of Green Bay (?)
6 | We help pilot the vehicles from here, charging 3 hrs/day to the project for the 9 day deployment
7 | USGS recovers the vehicles on 9/14 after their 9 day operation and drives them down to Manistique MI in northern Lake Michigan.
8 | USGS moves ESP/LRAUV from GLERL to Manistique
9 | Trip 3: Brian goes out for the deployment on 9/18, flying in/out of Green Bay. Deploy ESP and Bioac
10 | We help pilot the vehicles from here, charging 3 hrs/day to the project for the 9 day deployment
11 | USGS recovers the vehicles in Glen Arbor on 8/28 and moves them back to Ann Arbor.
12 | Trip 4: Quinn and Chris P. fly out to Ann Arbor to exchange the ESP cartridges and check/prep both vehicles.
13 | USGS drives the vehicles out to eastern Lake Erie
14 | Trip 5: I fly out to Cleveland and help them deploy both vehicles at Breeze Point PA on 9/5. Maybe Quinn goes with me
15 | We help pilot the vehicles from here, charging 3 hrs/day to the project for the 9 day deployment
16 | USGS recovers the vehicles at Breeze Pt on 9/15 and moves them back to Ann Arbor
17 | Optionally, USGS moves bioac vehicle to Burchville TWP. Park and deployes into Lake Huron on 9/18
18 | Optionally, USGS recovers vehicoles on 9/27 and returns them to GLERL
19 | Trip 6: Brian and Chloe fly out to Detroit and unload the ESP and pack up the shipment on 9/28
20 | Truck picks up container at GLERL on 10/3
Brett and Quinn will join Brian in Michigan for NOAA operations off Muskegon - paid for my NOAA. Quinn will likely help unpack and prep ESP the previous week.