## List of all deployment
List of wave energy buoy deployments
Updated: | 2017-11-07
Deployment | Start Date | End date | Duration (days) | Description
1 | 2009-08-11 | 2009-08-11 | 1 | Deployment with simple buoy, heave plate, and load cell
2 | 2011-01-25 | 2011-01-27 | 3 | Deployment with Oceangen PTO. No energy capture. Buoy was free drifting.
3 | 2011-02-17 | 2011-02-17 | 1 | Deployment with Oceangen PTO. No energy capture. Buoy was free drifting. Very large swell and windy. Difficult recovery. Seals where badly damaged as a result of side load
4 | 2011-11-08 | 2011-11-11 | 3 | First deployment with MBARI PTO and with tether guide. Buoy was free drifting | New seal kit
5 | 2012-01-05 | 2012-01-05 | 2 | MBARI PTO, with tether guide, free drifting. Was basically a repeat of the previous deployment, but in larger waves.
6 | 2012-06-26 | 2012-07-10 | 14 | First anchored deployment. Deployment ended after one legs of the steel wire bridle broke.
7 | 2012-11-13 | 2012-12-19 | 36 | Durability test deployment. Deployment ended when tether broke during powerful storm.
8 | 2013-04-25 | 2013-05-20 | 25 | Durability test deployment. Deployment ended oil leaked out of PTO | New seal kit (harder seal)
9 | 2013-09-03 | 2013-10-16 | 43 | Durability test deployment. Deployment ended when bridle broke.
10 | 2014-09-04 | 2015-01-14 | 132 | First test with compliant plate. | New seal kit
11 | 2016-02-09 | 2016-03-11 | 31 | Second test with compliant plate. Test ended when leg of bridle broke and compliant plate disintegrated and fell to the seafloor. | New seal kit (opposing seals)
12 | 2017-03-17 | 2017-03-24 | 7 | First deployment with flapping foil device and PTO
13 | 2017-10-02 | 2017-10-10 | 8 | Deployment with flapping foil device, without PTO
14 | 2018-10-04 | 2018-12-03 | 60 | Deployment with heave cone. Deployment ended when there was an oil leak caused by a loose fitting.
15 | 2019-02-28 | 2019-03-14 | 14 | Deployment with heave cone. Deployment ended when the rods seperated and the heave cone sank to the seafloor | New seal kit (opposing seals)
16 | 2021-08-20 | 2021-11-12 | 84 | Deployment with heave cone. Sucessful deployment except for wear on tether causing tear and loss of comms to heave cone. | Complete remodel of PTO and electronics
17 | 2022-04-18 | 2022-06-20 | 63 | Deployment with heave cone. Hydraulic motor and all hydraulic seals not replaced after previous deployment.
18 | 2022-09-01 | 2022-12-06 | 96 | Deployment with heave cone. Hydraulic motor and all hydraulic seals not replaced after previous deployment. Comm to Heavec one failed after 2 months
| 2023-04-27 | 2023-12-15 | 232 | Deployment with heave cone. Hydraulic motor and all hydraulic seals not replaced after previous deployment. New tether
| 2024-05-10 | 2024-09-25 | 138 | Deployment with heave cone. Hydraulic motor and all hydraulic seals not replaced after previous deployment. New tether. PTO stopped generating power on 9/16
| 2025-05-01 | 2025-10-16 | 168
|  | Total | 1156

## 1st Hydraulic motor deployments
List of powerbuoy deployments with hydratech PTO and parker hydraulic motor
Updated feb 2014
Deployment | Start Date | End date | Duration
1 | 2011-11-08 | 2011-11-11 | 3
2 | 2012-06-26 | 2012-07-10 | 14
3 | 2012-11-13 | 2012-12-19 | 36
4 | 2013-04-25 | 2013-05-20 | 25
5 | 2013-09-03 | 2013-10-16 | 43
6 | 2014-09-04 | 2015-01-14 | 132
|  | Total | 253