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Prototype and Testing – TimeLine  
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Notes:

· Battery-charging test deployment delayed until May due to power electronics issues.

· AUV Docking activities still require six month program extension for two reasons:

· Failure analysis and re-commissioning of vehicle still on-going.  Vehicle loss event incurred approximately 3 month delay in all AUV activities, pushing the docking schedule into conflict with other, previously scheduled, AUV commitments

· Benthos is going to require some time (and possibly money) to resolve USBL calibration issues.
	Activity
	Date
	Labor (weeks)
	Material Cost
	Ship Costs
	Total Cost (burdened)

	At-Sea Test of Battery Charging
	May 2012
	2
	$0
	$8,000
	$23,632

	AUV Dock Design and Fabrication
	April 2012
	2
	$4,000
	 
	$17,592

	AUV Dock Test to Stationary Mooring
	Dec 2012
	14
	$4,000
	$8,000
	$98,981

	AUV Dock Test to Wave-Energy Buoy
	Jan 2013
	12
	$15,000
	$8,000
	$104,039

	Propulsion Testing
	July 2012
	8
	$12,000
	$8,000
	$76,406

	Two-week Demonstration Deployment
	Jan 2013
	8
	$8,000
	$8,000
	$70,366

	Analysis and final report preparation
	Mar 2013
	6
	 
	 
	$43,318

	10% Contingency
	 
	 
	 
	 
	$39,101

	Total
	 
	52
	 
	 
	$473,434

	
	
	
	
	
	

	Additional Funds Required
	
	
	
	
	

	Activity
	Date
	Labor (weeks)
	Material Cost
	Ship Costs
	Total Cost (Burdened)

	USBL Calibration
	 
	2
	$10,000
	 
	$23,850

	Six month extension of funds to support Francois
	 
	24
	 
	 
	$105,000

	Numerical Model Packaging for General Use
	 
	4
	 
	 
	$28,879

	10% Contingency
	 
	 
	 
	 
	$12,885

	
	
	
	
	
	$170,614
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