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Prototype and Testing – TimeLine Summary

Time-Line
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	Activity
	Completion Date
	Notes

	At-sea testing of electrical generation - 2nd test
	January 2012
	Complete:  Data analysis underway

	Power Converter Design, buld, integration, and test
	March 2012
	Final configuration testing in lab underway, final PCB will be boards ordered next week.

	Dock Stabilization and Power Pass-Through
	June 2012
	Power-Pass through design complete, PTO being dissasembled for modifications.

	AUV Homing
	8-Nov-11
	Testing at sea on-going.  Calibration issues with USBL causing problems.

	AUV Dock Design and Fabrication
	March 2012
	Critical Design Review complete January 6th.  Fabrication underway.  Connectors are long leadtime items

	AUV Dock Test to Stationary Mooring
	April 2012
	Pending Completion of Dock Fabrication

	AUV Dock Test to Wave-Energy Buoy
	July 2012
	Pending successful docking to stationary mooring

	Propulsion Testing
	June 2012
	Plans to-be determined

	Two-week Demonstration Deployment
	August 2012
	 

	Numerical Model Packaging for General Use
	TBD
	Not yet scheduled.

	Analysis and final report preparation
	25-Sep-12
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