Power producing buoy for strategic applications:   

HR0011-09-2-0002
 


Prototype and Testing – TimeLine

Current Plan:  No longer feasible.
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	Activity
	Date
	Labor (weeks)
	Material Cost
	Ship Costs
	Total Cost (burdened)

	At-Sea Test of Battery Charging
	March 2012
	4
	$2,500
	$8,000
	$41,268

	AUV Homing
	8-Nov-11
	2
	 
	 
	$12,707

	AUV Dock Design and Fabrication
	March 2012
	4
	$5,000
	 
	$32,963

	AUV Dock Test to Stationary Mooring
	April 2012
	16
	$16,000
	$8,000
	$137,893

	AUV Dock Test to Wave-Energy Buoy
	June 2012
	12
	$15,000
	$8,000
	$110,970

	Propulsion Testing
	June 2012
	8
	$12,000
	$8,000
	$81,027

	Two-week Demonstration Deployment
	August 2012
	8
	$8,000
	$8,000
	$74,987

	Numerical Model Packaging for General Use
	TBD
	4
	 
	 
	$28,879

	Analysis and final report preparation
	25-Sep-12
	6
	 
	 
	$43,318

	10% Contingency
	 
	6
	 
	 
	$52,069

	Total
	 
	70
	 
	 
	$616,081

	
	
	
	
	
	

	
	
	
	
	
	

	AUV Docking SubTotals
	
	
	
	
	

	Activity
	Date
	Labor (weeks)
	Material Cost
	Ship Costs
	Total Cost (Burdened)

	AUV Homing
	8-Nov-11
	2
	 
	 
	$12,707

	AUV Dock Design and Fabrication
	March 2012
	4
	$5,000
	 
	$32,963

	AUV Dock Test to Stationary Mooring
	April 2012
	16
	$16,000
	$8,000
	$137,893

	AUV Dock Test to Wave-Energy Buoy
	June 2012
	12
	$15,000
	$8,000
	$110,970

	Total
	 
	34
	 
	 
	$294,533
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