Power producing buoy for strategic applications:   

HR0011-09-2-0002
 


Prototype and Testing – TimeLine  

Option 1:  Curtail docking activities, expand power-buoy propulsion exploration and testing (for instance).  
Notes:  

- No Extension Required

- Money currently planned for docking activities would be absorbed by more work on implementation of propulsion and the design/build of the required battery pack.
- Docking results to date would be included in final report.
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	Activity
	Date
	Labor (weeks)
	Material Cost
	Ship Costs
	Total Cost (burdened)

	At-Sea Test of Battery Charging
	March 2012
	4
	$2,500
	$8,000
	$41,268

	Propulsion Testing
	May 2012
	12
	$12,000
	$8,000
	$106,440

	Fabrication of Battery Pack
	June 2012
	8
	$30,000
	 
	$96,127

	Propulsion Testing Deploy #2
	June 2012
	12
	$12,000
	$8,000
	$106,440

	Two-week Demonstration Deployment
	August 2012
	8
	$8,000
	$8,000
	$74,987

	Numerical Model Packaging for General Use
	TBD
	4
	 
	 
	$28,879

	Analysis and final report preparation
	25-Sep-12
	6
	 
	 
	$43,318

	10% Contingency
	 
	5
	 
	 
	$45,414

	Total
	 
	59
	 
	 
	$542,872
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