Power producing buoy for strategic applications:   

HR0011-09-2-0002
 


Prototype and Testing – Option 1

Option 1:  Docking to stationary mooring completed by the end of 2012.
Notes:  

- 
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	Energy Buoy Activities
	
	
	
	
	

	Activity
	Date
	Labor (weeks)
	Material Cost
	Ship Costs
	Total Cost (burdened)

	Two Week At-Sea Test of Battery Charging
	June 2012
	12
	$8,000
	$8,000
	$100,400

	Aux Deployment
	Aug 2012
	8
	$4,000
	$8,000
	$68,947

	Numerical Model Packaging for General Use
	TBD
	4
	 
	 
	$28,879

	Analysis and final report preparation
	Dec 2012
	6
	 
	 
	$43,318

	10% Contingency
	 
	3
	 
	 
	$24,154

	Total
	 
	33
	 
	 
	$265,698

	
	
	
	
	
	

	Funds Remaining
	
	
	
	
	$342,000

	Unallocated Funds Without Docking Activities
	
	
	
	
	$76,302

	
	
	
	
	
	

	
	
	
	
	
	

	AUV Docking Activities
	
	
	
	
	

	Activity
	Date
	Labor (weeks)
	Material Cost
	Ship Costs
	Total Cost (Burdened)

	AUV Dock Final Integration
	May 2012
	2
	$2,500
	 
	$16,482

	USBL  Installation Modifications
	Sept 2012
	4
	$4,000
	 
	$31,453

	Docking Algorithm mods to include sonar performance knowledge
	Oct 2012
	4
	 
	 
	$25,413

	AUV Homing Re-Testing
	.Nov 2012
	6
	$2,000
	$8,000
	$53,220

	AUV Dock Test to Stationary Mooring
	April 2012
	10
	$10,000
	$8,000
	$90,713

	10% Contingency
	 
	 
	 
	 
	$21,728

	Total
	 
	16
	 
	 
	$239,010

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	Unallocated Funds Remaining
	
	
	
	
	$76,302

	Cost of Remaining Docking Activities
	
	
	
	
	$239,010

	Additional Funds Required
	
	
	
	
	$162,707
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