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Prototype and Testing – TimeLine Summary

Time-Line
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	Activity
	Scheduled Date Complete
	Status

	June Deployment Analysis
	Aug 30, 2012
	Analysis complete, write-up underway

	November Deployment Preparations
	Oct 31, 2012
	Underway, maintenance after last deployment complete and system returned to testing configuration in lab

	Control Algorithm Development
	Oct 26, 2012
	Underway via numerical modeling

	Control Algorithm Implementation
	Nov 2, 2012
	Framework for implementation in on-buoy computer complete, final programming will be performed after algorithm finalization

	Buoy draft sensor specification and installation
	Oct 26, 2012
	Sensor identified and ordered, will be integrated upon arrival.

	November Deployment 
	Nov 8, 2012
	Planned for one month duration.
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