## Sheet1
|  |  | Labor (Hours) | [13 empty] | Material | Outside Srv | Ship Time |  |  | Sub-totals |  | Notes
Task |  |  | Hamilton | Cazenave | Erickson | ME | Jensen | Martin | Klimov | EE | Henthorn | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost | Expense | Labor
Station Keeping Developments
| Refine 2016 design as needed |  | 16 | 40 | 40 |  | 16 | 16 | 16 |  | 20 |  | 16 |  | 40 |  | 10000
| Develop adjustable stop hardware |  | 16 | 40 | 40 |  | 16 | 16 |  |  | 20 |  |  |  | 40 |  | 10000
| Integrate adjustable stop |  | 8 | 16 | 16 | [7 empty] | 16 | 8 |  |  | 2000
| Add buoy controller navigation and control features |  | 16 | [7 empty] | 40
| Integation and test (in Lab) |  | 40 | 40 | 40 | [5 empty] | 16
| Prepare report/presentation for LRI |  | 16
| Work with LRI on future plans as needed |  | 16
Task Total |  |  | 128 | 136 | 136 | 400 | 32 | 32 | 16 | 80 | 96 | 96 | 32 | 8 | 80 | 0 | 22000 | 0 |  |  |  | 22000 | 696
Flapping Foil Test Deployments (2)
| Deployment Preparation |  | 16 | 32 | 16 |  | 8 | 8 | 8 |  | 8 |  | 32 | 8 |  |  | 2000 | [6 empty] | Rebuild items: Seals, motor, zincs. Replace items: Filter, tether guide.
| Deployment |  | 16 | 16 | 16 |  |  | 16 |  |  | 8 |  | 32 |  |  | 16 |  |  | Shana Rae | 4 Days | 8000
| Monitoring/Servicing |  | 8 | 8 | [8 empty] | 8 |  |  | 8 |  |  | Paragon | 2 Half Days
| Recovery |  | 16 | 32 | 16 |  |  | 16 |  |  | 8 |  | 32 |  |  | 16 |  |  | Shana Rae | 4 Days | 8000
| Cleanup after Recovery |  | 8 | 16 | [8 empty] | 16
| Deployment Data Analysis |  | 16
Task Total |  |  | 80 | 104 | 48 | 232 | 8 | 40 | 8 | 56 | 24 | 24 | 120 | 8 |  | 40 | 2000 | 0 |  |  | 16000 | 18000 | 480
Develop Bi-directional Power Electronics
| Build second power converter for lab |  | 8 |  |  |  | 16 | 8 | [5 empty] | 16 | 8 |  | 1000
| Modify power electronics as needed |  | 16 |  |  |  | 80 | [6 empty] | 8 |  |  | 2000
| Modify power converter firmware as needed |  | 100 |  |  |  | 16 |  |  |  | 16 |  |  | 4
| Testing in Lab |  | 40 |  |  |  | 40 |  |  |  | 16
| Implement buoy controller commands |  | 8 | [7 empty] | 16
| Modify deployed power electronics as needed |  | 8 |  |  |  | 16 | [6 empty] | 16 |  |  | 500
| PTO Testing on test-machine |  | 40 | 8 |  |  | 16 | [6 empty] | 8
Task Total |  |  | 220 | 8 | 0 | 228 | 184 | 8 | 0 | 192 | 48 | 48 | 0 | 52 | 8 | 0 | 3500 | 0 |  |  |  | 3500 | 528
Rebuild Compliant Plate
| Fabricate needed components |  | 4 | 8 | 12 | [9 empty] | 40 |  | 5000 | 10000
| Assembly |  |  | 8 | 8 | [7 empty] | 16
Task Total |  |  | 4 | 16 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 40 | 0 | 5000 | 10000 |  |  |  | 15000 | 96
[5 empty] | 20 |  |  |  | 40 |  | 0
2017-2018 Winter Deployment
| Deployment Preparation |  | 8 | 16 | 8 |  | 4 | 4 | 4 |  | 16 |  | 16 | 4 |  |  | 2000 | [6 empty] | Rebuild items: Seals, motor, zincs. Replace items: Filter, tether guide, tether
| Build New Tether |  | 8 | 8 | [13 empty] | 2000
| Deployment |  | 8 | 16 | 8 |  | 8 | 8 |  |  | 8 |  | 16 |  |  | 8 |  |  | Shana Rae | 2 Days | 4000
| Monitoring/Servicing |  | 12 | 12 |  |  |  | 8 |  |  |  |  | 8 |  |  | 12 |  |  | Paragon | 4 Half Days
| Deployment Data Analysis |  | 8
Task Total |  |  | 44 | 52 | 16 | 112 | 12 | 20 | 4 | 36 | 24 | 24 | 40 | 4 |  | 20 | 2000 | 2000 |  |  | 4000 | 8000 | 236
Lithium Battery Investigations
| Evaluation of Commercially Available Options |  | 8 |  |  |  | 40 |  | 40 |  |  |  | 16 | 4 |  |  | 3000
| Prototyping |  | 8 |  |  |  | 40 |  | 40 |  |  |  | 8
Task Total |  |  | 16 | 0 | 0 | 16 | 80 | 0 | 80 | 160 | 0 | 0 | 24 | 4 |  |  | 3000 |  |  |  |  | 3000 | 204
|  |  | Labor (Hours) | [13 empty] | Material | Outside Srv | Ship Time
[6 empty] | ME |  |  |  | EE |  | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost
Totals |  |  | 492 | 316 | 220 | 1028 | 316 | 100 | 108 | 524 | 192 | 192 | 232 | 76 | 128 | 60 | 37500 | 12000 |  |  | 20000 | 69500 | 2240
[6 empty] | 1028 |  |  |  | 524 |  | 192 | 232 | 76 | 128 | 60 | [5 empty] | 69500 | 2240
1744
2016 Totals |  |  | 392 | 396 | 276 | 1104 | 244 | 156 | 112 | 512 | 300 | 380 | 340 | 202 | 136 | 56 | 47000 | 7400 | 0 | 0 | 8000 | 62400 | 2730
1996
Milestone
| 1 | 1st Deploy | 88 | 120 | 92 |  | 20 | 36 | 12 |  | 60 |  | 76 | 8 | 40 | 20
| 2 | Power+Battery | 236 | 8 | 0 |  | 264 | 8 | 80 |  | 48 |  | 24 | 56 | 8 | 0
| 3 | 2nd Deploy | 88 | 120 | 92 |  | 20 | 36 | 12 |  | 60 |  | 76 | 8 | 40 | 20
| 4 | LRI Report | 32 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
| 5 | Winter Deployment | 48 | 68 | 36 |  | 12 | 20 | 4 |  | 24 |  | 56 | 4 | 40 | 20
|  |  | 492 | 316 | 220 |  | 316 | 100 | 108 |  | 192 |  | 232 | 76 | 128 | 60 | 2240
[5 empty] | 1028 |  |  |  | 524 |  | 192 |  | 232 | 76 | 128 | 60 | 2240