## Sheet1
|  |  | Labor (Hours) | [14 empty] | Material | Outside Srv | Ship Time |  |  | Sub-totals |  | Notes
Task |  |  | Hamilton | Cazenave | Erickson | ME | Jensen | Martin | Klimov | EE | McEwen | Henthorn | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost | Expense | Labor
System Numerical Modelling
| Exploration of CFD approaches |  | 40
| Development of quasi-static flapping foil model |  | 40 | [7 empty] | 40
| Comparison of test data to model results |  | 40 | [7 empty] | 40
Task Total |  |  | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 200
Advanced Control Development
| Linear and Nonlinear Model developments |  | 40 | [7 empty] | 40 | [13 empty] | Rebuild items: Seals, motor, zincs. Replace items: Filter, tether guide.
| State Estimation |  | 40 | [7 empty] | 40
| Wave-Exciting Force Prediction |  | 40 | [7 empty] | 40
| Comparison to Test Data |  | 40 | [7 empty] | 40
| Model Implementation on Buoy Computer |  | 40 | [8 empty] | 80
| Refinements between tests |  | 40 | [7 empty] | 40 | 40
Task Total |  |  | 240 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 200 | 120 | 320 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 560
Electronics Modifications
| Battery System | [16 empty] | 4000
| Circuit Board Modifications | [5 empty] | 80 | 16 | [6 empty] | 40 | 8 |  | 10000
| Firmware Modifications |  | 60 |  |  |  | 20 | [7 empty] | 8
| Lab Testing |  | 20 |  |  |  | 20 | [6 empty] | 20 | 20 |  |  | 1000
| Mechanical Modifications |  | 20 |  | 40 |  | 20 | [6 empty] | 20 |  |  |  | 1000
| PTO Integration |  | 20 |  | 20 |  | 20
| PTO Testing on test-machine |  | 40 | 20 |  |  | 40 | [7 empty] | 16
Task Total |  |  | 160 | 20 | 60 | 240 | 200 | 16 | 0 | 216 |  | 0 | 0 | 40 | 84 | 8 | 0 | 12000 | 0 |  |  |  | 12000 | 588
TreFoil Construction
| Design |  |  | 80 | 40 |  |  | 40 | [5 empty] | 40 | 20 | 40
| Mechanical Constuction |  |  | 80 | 20 |  | 20 | 40 | 20 |  |  |  |  | 40 |  |  |  | 8000
| Bearing Assembly | [16 empty] | 7000
| Drive Motor/Electronics | [16 empty] | 2000
| Drive Motor Housing | [16 empty] | 2000
| Tether Termination | [17 empty] | 1000
Task Total |  |  | 0 | 160 | 60 | 220 | 20 | 80 | 20 | 120 | 0 | 0 | 0 | 80 | 20 | 40 | 0 | 19000 | 1000 |  |  | 0 | 20000 | 480
Deployment
| Integration and Testing |  |  | 80 | 20 |  | 20 | 40 | 20 |  |  |  |  | 40
| Deployment |  |  | 40 |  |  | 20 | 20 | 20 |  |  | 20 |  | 40 |  |  | 8 |  |  | Shana Rae | 3 | 6000
| Results Analysis |  | 40 | [7 empty] | 40 | [8 empty] | Paragon | 4 Half Days
Task Total |  |  | 40 | 120 | 20 | 180 | 40 | 60 | 40 | 140 | 40 | 20 | 60 | 80 | 0 | 0 | 8 | 0 | 0 |  |  | 6000 | 6000 | 468
|  |  | Labor (Hours) | [14 empty] | Material | Outside Srv | Ship Time
[6 empty] | ME |  |  |  | EE |  |  | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost | 38000 | 2296
Totals |  |  | 560 | 300 | 140 | 1000 | 260 | 156 | 60 | 476 | 320 | 140 | 460 | 200 | 104 | 48 | 8 | 31000 | 1000 | Paragon | 3 Days | 6000 | 38000 | 2296
[6 empty] | 1000 |  |  |  | 476 |  |  | 140 | 200 | 104 | 48 | 8 | [5 empty] | 38000 | 1976
1936
2016 Totals |  |  | 392 | 396 | 276 | 1104 | 244 | 156 | 112 | 512 |  | 300 | 380 | 340 | 202 | 136 | 56 | 47000 | 7400 | 0 | 0 | 8000 | 62400 | 2730
1996
Milestone
| 1 | 1st Deploy | 180 | 0 | 0 |  | 0 | 0 | 0 |  |  | 60 |  | 0 | 0 | 0 | 0
| 2 | Power+Battery | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| 3 | 2nd Deploy | 180 | 0 | 0 |  | 0 | 0 | 0 |  |  | 60 |  | 0 | 0 | 0 | 0
| 4 | LRI Report | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| 5 | Winter Deployment | 40 | 280 | 80 |  | 60 | 140 | 60 |  |  | 20 |  | 160 | 20 | 40 | 8
|  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! |  |  |  | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!