## Sheet1
|  |  | Labor (Hours) | [14 empty] | Material | Outside Srv | Ship Time |  |  | Sub-totals |  | Notes
Task |  |  | Hamilton | Cazenave | Erickson | ME | Jensen | Martin | Klimov | EE | McEwen | Henthorn | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost | Expense | Labor
System Numerical Modelling
| Exploration of CFD approaches |  | 40
| Development of quasi-static flapping foil model |  | 40 | [7 empty] | 40
| Comparison of test data to model results |  | 40 | [7 empty] | 40
Task Total |  |  | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 200
Advanced Control Development
| Linear and Nonlinear Model developments |  | 40 | [7 empty] | 40 | [13 empty] | Rebuild items: Seals, motor, zincs. Replace items: Filter, tether guide.
| State Estimation |  | 40 | [7 empty] | 40
| Wave-Exciting Force Prediction |  | 40 | [7 empty] | 40
| Comparison to Test Data |  | 40 | [7 empty] | 40
| Model Implementation on Buoy Computer |  | 40 | [8 empty] | 80
| Refinements between tests |  | 40 | [7 empty] | 40 | 40
Task Total |  |  | 240 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 200 | 120 | 320 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 560
Power Electronics Modifications
| Electronic Modifications | [5 empty] | 80 | 16 | [6 empty] | 40 | 8 |  | 6000
| Firmware Modifications |  | 60 |  |  |  | 20 | [7 empty] | 8
| Lab Testing |  | 20 |  |  |  | 20 | [6 empty] | 20 | 20 |  |  | 2000
| Mechanical Modifications |  | 20 |  | 40 |  | 20 | [6 empty] | 20
| PTO Integration |  | 20 |  | 20 |  | 20
| PTO Testing on test-machine |  | 40 | 20 |  |  | 40 | [7 empty] | 16 |  |  | 500
Task Total |  |  | 160 | 20 | 60 | 240 | 200 | 16 | 0 | 216 |  | 0 | 0 | 40 | 84 | 8 | 0 | 8500 | 0 |  |  |  | 8500 | 588
Test Deployment #1
| Flapping Foil Modifications |  |  | 80 | 40 |  |  | 40 | [5 empty] | 40 | 20 | 40 |  | 10000 | 4000
| Integration and Testing |  |  | 80 | 20 |  | 20 | 40 | 20 |  |  |  |  | 40
| Deployment |  |  | 40 |  |  | 20 | 20 | 20 |  |  | 20 |  | 40 |  |  | 8 |  |  | Shana Rae | 4 | 8000
| Results Analysis |  | 40 | [7 empty] | 40 | [8 empty] | Paragon | 2 Half Days
Task Total |  |  | 40 | 200 | 60 | 300 | 40 | 100 | 40 | 180 | 40 | 20 | 60 | 120 | 20 | 40 | 8 | 10000 | 4000 |  |  | 8000 | 22000 | 728
Test Deployment #2
| Flapping Foil Modifications |  |  | 80 | 40 |  |  | 40 | [5 empty] | 40 | 20 | 40 |  | 5000 | [6 empty] | Rebuild items: Seals, motor, zincs. Replace items: Filter, tether guide, tether
| Integration and Testing |  |  | 80 | 20 |  | 20 | 40 | 20 |  |  |  |  | 40 |  |  |  |  | 2000
| Deployment |  |  | 40 |  |  | 20 | 20 | 20 |  |  | 20 |  | 40 |  |  | 8 |  |  | Shana Rae | 4 | 8000
| Results Analysis |  | 40 | [7 empty] | 40 | [8 empty] | Paragon | 4 Half Days
Task Total |  |  | 40 | 200 | 60 | 300 | 40 | 100 | 40 | 180 | 40 | 20 | 60 | 120 | 20 | 40 | 8 | 5000 | 2000 |  |  | 8000 | 15000 | 728
|  |  | Labor (Hours) | [14 empty] | Material | Outside Srv | Ship Time
[6 empty] | ME |  |  |  | EE |  |  | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost | 45500 | 2804
Totals |  |  | 600 | 420 | 180 | 1200 | 280 | 216 | 80 | 576 | 360 | 160 | 520 | 280 | 124 | 88 | 16 | 23500 | 6000 | Paragon | 3 Days | 16000 | 45500 | 2804
[6 empty] | 1200 |  |  |  | 576 |  |  | 160 | 280 | 124 | 88 | 16 | [5 empty] | 45500 | 2444
2296
2016 Totals |  |  | 392 | 396 | 276 | 1104 | 244 | 156 | 112 | 512 |  | 300 | 380 | 340 | 202 | 136 | 56 | 47000 | 7400 | 0 | 0 | 8000 | 62400 | 2730
1996
Milestone
| 1 | 1st Deploy | 180 | 0 | 0 |  | 0 | 0 | 0 |  |  | 60 |  | 0 | 0 | 0 | 0
| 2 | Power+Battery | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| 3 | 2nd Deploy | 180 | 0 | 0 |  | 0 | 0 | 0 |  |  | 60 |  | 0 | 0 | 0 | 0
| 4 | LRI Report | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| 5 | Winter Deployment | 80 | 400 | 120 |  | 80 | 200 | 80 |  |  | 40 |  | 240 | 40 | 80 | 16
|  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! |  |  |  | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!