## Sheet1
|  |  | Labor (Hours) | [13 empty] | Material | Outside Srv | Ship Time |  |  | Sub-totals |  | Notes
Task |  |  | Hamilton | Cazenave | Erickson | ME | Jensen | Martin | EE | McEwen | Henthorn | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost | Expense | Labor
Power Electronics Completion
| Board Layout and Build for Controller |  | 40 |  |  |  | 40 | 16 | [5 empty] | 16 |  |  | 3000
| Board Layout and Build for Volt/Curr Measurements |  | 40 |  |  |  | 40 | [6 empty] | 16 |  |  | 2000
| Mechanical Integration |  | 8 |  | 20 | [7 empty] | 16 |  | 32 |  | 2000
| Development and Test of Bridge Driver Board |  | 40 |  |  |  | 80 | [6 empty] | 16 |  |  | 3000
| Software integration |  | 20 | [7 empty] | 120
Task Total |  |  | 148 | 0 | 20 | 168 | 160 | 16 | 176 | 0 | 120 | 120 | 16 | 48 | 32 | 0 | 10000 | 0 |  |  |  | 10000 | 560
System Recovery, Analysis
| Recovery |  | 16 | 16 | 8 |  | 8 | [5 empty] | 16 |  |  | 8 |  |  | Shana Rae | 1.5 days | 3750 |  |  | Rebuild items: Seals, motor, zincs. Replace items: Filter, tether guide.
| Results Analysis |  | 60 | 16 | [5 empty] | 60 | 8
Task Total |  |  | 76 | 32 | 8 | 116 | 8 | 0 | 8 | 60 | 8 | 68 | 16 | 0 | 0 | 8 | 0 | 0 |  |  | 3750 | 3750 | 216
|  |  | 224 | 32 | 28 |  | 168 | 16 |  | 60 | 128 |  | 32 | 48 | 32 | 8
Refurb and Electronics Integration
| PTO Refurb |  | 8 | 40 | 8 | [7 empty] | 40 |  |  |  | 2500
| Tether Refurb |  |  | 8 | [9 empty] | 8 |  |  |  | 4500
| Buoy Refurb |  | 8 | 16 | 8 | [7 empty] | 20 | 8 |  |  | 2500
| Electronics Integration and Test |  | 40 | 24 | 8 |  | 40 | 20 |  |  | 40 |  | 20 | 20 |  |  | 2500
| Heave-Cone Refurb |  | 8 | 24 |  |  | 8 | [5 empty] | 8 |  |  |  | 2500
Task Total |  |  | 64 | 112 | 24 | 200 | 48 | 20 | 68 | 0 | 40 | 40 | 88 | 36 | 0 | 0 | 10000 | 4500 |  |  |  | 14500 | 432
Deployment
| Deployment Prep |  | 16 | 40 | 20 |  | 16 | 40 |  |  | 8 |  | 40 | 20 | 40
| Deployment |  | 8 | 8 | 8 |  | 8 | 8 |  |  |  |  | 8 |  |  | 8 |  |  | Shana Rae | 1.5 days | 3750
| System Monitoring |  | 16 | 16 |  |  | 16 | 16 |  |  | 8 |  |  |  |  | 16 | 2000 |  | Pargon | 4 Days
Task Total |  |  | 40 | 64 | 28 | 132 | 40 | 64 | 104 | 0 | 16 | 16 | 48 | 20 | 40 | 24 | 2000 | 0 |  |  | 3750 | 5750 | 384
|  |  | 104 | 176 | 52 |  | 88 | 84 |  | 0 | 56 |  | 136 | 56 | 40 | 24
AUV Docking Feasibility
| Line Capture Integration into LRAUV |  | 40 | 80 | 80 |  | 40 | 40 |  |  |  |  | 40 | 20 |  |  | 5000
| Test Setup Design and Assembly |  | 40 | 80 | 40 |  | 40 | 40 |  | 40 |  |  | 40 | 20 |  |  | 5000
| At-Sea Feasibility Testing |  | 40 | 80 | 40 |  | 40 | 40 |  | 40 |  |  | 40 | 20
Task Total |  |  | 120 | 240 | 160 | 520 | 120 | 120 | 240 | 80 | 0 | 80 | 120 | 60 | 0 | 0 | 10000 | 0 |  |  | 0 | 10000 | 1020
|  |  | Labor (Hours) | [13 empty] | Material | Outside Srv | Ship Time
[6 empty] | ME |  |  | EE |  |  | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost | 44000 | 2612
Totals |  |  | 448 | 448 | 240 | 1136 | 376 | 220 | 596 | 140 | 184 | 324 | 288 | 164 | 72 | 32 | 32000 | 4500 | Paragon | 4 Days | 7500 | 44000 | 2612
[6 empty] | 1136 |  |  | 596 |  |  | 184 | 288 | 164 | 72 | 32 | [5 empty] | 44000 | 2472
2056
2016 Totals |  |  | 392 | 396 | 276 | 1104 | 244 | 156 | 512 |  | 300 | 380 | 340 | 202 | 136 | 56 | 47000 | 7400 | 0 | 0 | 8000 | 62400 | 2730
1996
Milestone
| 1 | 1st Deploy | 112 | 16 | 14 |  | 84 | 8 |  |  | 64 |  | 16 | 24 | 16 | 4
| 2 | Power+Battery | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| 3 | 2nd Deploy | 112 | 16 | 14 |  | 84 | 8 |  |  | 64 |  | 16 | 24 | 16 | 4
| 4 | LRI Report | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| 5 | Winter Deployment | 160 | 304 | 188 |  | 160 | 184 |  |  | 16 |  | 168 | 80 | 40 | 24
|  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | [5 empty] | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
2580