## Sheet1
|  |  | Labor (Hours) | [13 empty] | Material | Outside Srv | Ship Time |  |  | Sub-totals |  | Notes
Task |  |  | Hamilton | Cazenave | Erickson | ME | Jensen | Martin | EE | McEwen | Henthorn | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost | Expense | Labor
1st Test Deployment And Recovery
| Pre-deployment integration and testing |  | 40 | 80 | 16 | 136 | 20 | 16 | 36 |  | 20 | 20 | 40 | 16 |  |  | 2000 | 2000 | [6 empty] | Misc, tether re-term
| Deployment |  | 8 | 8 |  | 16 | 8 |  | 8 |  | 8 | 8 | 8 |  |  | 8 |  |  | Shana Rae | 2 | 5000
| System monitoring |  | 40 | 40 |  | 80 | 20 | 8 | 28 |  | 40 | 40 | 8 |  |  | 20 |  | 1000 | Paragon | 6 half days |  |  |  |  | Cell Phone Costs
| Recovery |  | 8 | 8 |  | 16 | 8 |  | 8 |  | 8 | 8 | 8 |  |  | 8 | 100 |  | Shana Rae | 2 | 5000 |  |  |  | Food
| Post Recovery Inspection |  | 8 | 8 | 4 | 20 | 8 |  | 8 |  | 8 | 8 | 40
Task Total |  |  | 104 | 144 | 20 | 268 | 64 | 24 | 88 | 0 | 84 | 84 | 104 | 16 | 0 | 36 | 2100 | 3000 |  |  | 10000 | 15100 | 596
[6 empty] | 268 |  |  | 88 |  |  | 84
Inspection and Refurbishment
| Dissassembly and Inspection |  | 8 | 80 | 8 | 96 | 8 | 8 | 16 |  |  | 0 | 40 | 16
| Component Refurbishment |  | 8 | 8 |  | 16 | 8 |  | 8 |  | 8 | 8 | 16 |  |  |  | 5000 | 2000 | [6 empty] | Seals, shackles, etc, Tether re-term
| System Re-assembly |  | 8 | 36 | 8 | 52 | 8 | 8 | 16 |  |  | 0 | 40 | 16 |  |  | 1000 | [7 empty] | Misc
Task Total |  |  | 24 | 124 | 16 | 164 | 24 | 16 | 40 | 0 | 8 | 8 | 96 | 32 | 0 | 0 | 6000 | 2000 |  |  | 0 | 8000 | 340
[6 empty] | 164 |  |  | 40 |  |  | 8
2nd Test Deployment
| Pre-deployment integration and testing |  | 40 | 80 | 8 | 128 | 20 | 16 | 36 |  | 20 | 20 | 40 | 16 |  |  | 2000 | [7 empty] | Misc
| Deployment |  | 8 | 8 |  | 16 | 8 |  | 8 |  | 8 | 8 | 8 |  |  | 8 |  |  | Shana Rae | 2 | 5000
| System monitoring |  | 20 | 20 |  | 40 | 10 | 8 | 18 |  | 20 | 20 | 8 |  |  | 8 |  | 400 | Paragon | 4 half days |  |  |  |  | Cell Phone Costs
Task Total |  |  | 68 | 108 | 8 | 184 | 38 | 24 | 62 | 0 | 48 | 48 | 56 | 16 | 0 | 16 | 2000 | 400 |  |  | 5000 | 7400 | 382
[6 empty] | 184 |  |  | 62 |  |  | 48
Power Converter Upgrade
| Housings and Mechanical Integration |  | 24 | 24 | 80 | 128 | 16 | 16 | 32 |  | 16 | 16 | 16 | 16 | 60 |  | 5000 | [7 empty] | Materials
| Connectorization Review and Upgrade |  | 8 | 8 |  | 16 | 8 | 8 | 16 |  |  | 0 | 8 | 16 |  |  | 3000 | [7 empty] | Connectors
| Electrical Components and Integration |  | 8 | 8 |  | 16 | 80 |  | 80 |  | 8 | 8 | 8
| Lab Testing |  | 20 | 20 |  | 40 | 10 | 8 | 18 |  | 20 | 20
Task Total |  |  | 60 | 60 | 80 | 200 | 114 | 32 | 146 | 0 | 44 | 44 | 32 | 32 | 60 | 0 | 8000 | 0 |  |  |  | 8000 | 514
[6 empty] | 200 |  |  | 146 |  |  | 44
Battery System Upgrade
| Electrical Components and Integration |  | 24 | 24 | 8 | 56 | 120 | 16 | 136 |  | 16 | 16 | 16 | 40 |  |  | 20000 | [7 empty] | Batteries and Cicuitry
| Housings and Mechanical Integration |  | 16 | 16 | 40 | 72 | 8 |  | 8 |  | 8 | 8 | 8 |  |  |  | 4000 | [7 empty] | Materials
| Lab Testing |  | 20 | 20 |  | 40 | 40 | 8 | 48 |  | 20 | 20
Task Total |  |  | 60 | 60 | 48 | 168 | 168 | 24 | 192 | 0 | 44 | 44 | 24 | 40 | 0 | 0 | 24000 | 0 |  |  |  | 24000 | 468
[6 empty] | 168 |  |  | 192 |  |  | 44
Accelerated Life Testing
| Identification of service provider |  | 8 | 8 |  | 16 | 8 |  | 8 |  |  | 0 |  | 16
| Test Item Preperation |  | 16 | 16 |  | 32 | 16 |  | 16 |  | 0 | 0 | 16 | 16 |  |  | 1000 | [7 empty] | Misc
| Outside Testing |  | 8 |  |  | 8 | 8 |  | 8 |  |  | 0 | [5 empty] | 10000 | [6 empty] | Rough estimates
| Results Analysis and Mitigations |  | 8 | 8 |  | 16 | 8 |  | 8
Task Total |  |  | 40 | 32 | 0 | 72 | 40 | 0 | 40 | 0 | 0 | 0 | 16 | 32 | 0 | 0 | 1000 | 10000 |  |  |  | 11000 | 160
[6 empty] | 72 |  |  | 40 |  |  | 0
External Collaboration Explorations
| Meetings, Discussions, Proposal Writing |  | 80 | 8 |  | 88 | 8 | 8 | 16 |  | 40 | 40
Task Total |  |  | 80 | 8 | 0 | 88 | 8 | 8 | 16 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 144
[9 empty] | 16 |  |  | 40
|  |  | Labor (Hours) | [13 empty] | Material | Outside Srv | Ship Time
[6 empty] | ME |  |  | EE |  |  | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost | 73500 | 2604
Totals |  |  | 436 | 536 | 172 | 1144 | 456 | 128 | 584 | 0 | 268 | 268 | 328 | 168 | 60 | 52 | 43100 | 15400 |  |  | 15000 | 73500 | 2604
[6 empty] | 1144 |  |  | 584 |  |  | 268 | 328 | 168 | 60 | 52 | [5 empty] | 73500 | 2604
1996
2016 Totals |  |  | 392 | 396 | 276 | 1104 | 244 | 156 | 512 |  | 300 | 380 | 340 | 202 | 136 | 56 | 47000 | 7400 | 0 | 0 | 8000 | 62400 | 2730
1996
Milestone
| 1 | 1st Deploy | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| 2 | Power+Battery | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| 3 | 2nd Deploy | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| 4 | LRI Report | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| 5 | Winter Deployment | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | #REF! | [5 empty] | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
[6 empty] | 1144 |  |  | 584 |  |  | 268 | [10 empty] | 2604
[13 empty] | 152 | 48 | 0 | 16
[6 empty] | 436 |  |  | 118 |  |  | 96