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Jan 23 - Jan 26 (4 days)
Simulation and schematic capture of PWM Filter, PID Controller boards (Wayne)

New generator on order (Paul)

Jan 30 - Feb 3 (5 days, Andy gone)
Completion of Load Dump mechanical design, submit drawings to Machine Shop (François)
Order new Heat Sink material (François)

Simulation and schematic capture of PWM Generator (Wayne)
Layout of PWM Filter, PWM Generator, and PID Controller boards (Jose)
Build and test PWM Filter, PWM Generator, and PID Controller boards (EE Techs, Jose, Wayne)
Set up end-to-end test of PWM Filter, PWM Generator, and PID Controller boards (Wayne, Scott)

Mech design of COTS SMPS housing (François, Paul)

Schematic capture of Load Dump Limiter, Load Dump Module boards (Scott)
Layout of Load Dump Limiter board (Jose)
Fabrication of Load Dump Limiter, Load Dump Module PC boards by PCB house (Jose)

Detailed design of system wiring (Paul)
 
Feb 6 - Feb 9 (4 days)
Build and test Load Dump Limiter, Load Dump Module boards (EE Techs, Scott)


End-to-end test of PWM Filter, PWM Generator, PID Controller, COTS SMPS boards, MATLAB test harness testing of PID and PWM circuits (Wayne, Andy)

Load Dump modules (Wayne, Scott, Paul)

Schematic capture of COTS SMPS board (Paul)

Feb 13 - Feb 17 (5 days)
Layout of COTS SMPS board (Jose)
Fabrication of COTS SMPS PC board by PCB house (Jose)

System software mods to support new hardware (Wayne, Andy)

Build system cables (EE Techs)

Install new wiring for AUV Dock (EE Techs, François)
Install new generator, reassemble Test Machine (François, EE Techs)

Feb 21 - Feb 23 (3 days)
Build and test Load Dump (François, Scott, Paul)

Feb 27 - Mar 2 (5 days)
Build and test COTS SMPS board (EE Techs, Paul, Wayne)
Install COTS SMPS board into housing (EE Techs, Paul)

Install new housings on Buoy (François)

Mar 5 - Mar 8 (4 days)
Integrate and test COTS SMPS board and Load Dump in lab (Paul, Wayne, Scott)
Test COTS SMPS board and Load Dump on Test Machine (Paul, Wayne, Scott)

Assemble Buoy for deployment (François, Andy, ME Techs)

Mar 12 - Mar 16 (5 days)
At sea testing
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