## ImprovementList
| Item | Priority | Difficulty | Notes
Tether Reliability
| Improve Tether Guide attachment (flange) | 1 |  | Design in process
| Tether guide and tether wear guide | 2 |  | Completed
| Thicker Jacket on tether | 2 |  | Not for april deployment
| Material choice of tether guide | 3 |  | TBD
Buoy Changes/Improvements
| Relocate battery box on buoy to make it sit level | 2 |  | Not addressed yet
| Improve reliability and UV stability of battery box switches | 3 |  | ?
| Improve mounting of buoy-to-pto cable. | 2 |  | ?
| Investigate EOM universal to replace buoy-to-pto shackles | 2 |  | Dismissed, staying with shackles,
| Perform Longevity test of buoy-to-pto cable | 2 |  | not practical
Coil Cord Reliability
| Shorten upper rod to move Piston down and increase room for Coilcord | 2 |  | Done
| Lengthen coil-cord guard to come closer to top | 2 |  | In process
| Lengthen upper housing some, (requires coil cord to stretch a smaller %age) | 2 |  | Dismissed as not practical
| Move Pneumatic pump out of coil cord cylinder ,requires larger upper pipe. | 2 |  | No way.
| Move connectors off of cheese where possible to allow better inspection. | 2 |  | Solidworks model complete
| Slip ring fragility. Wire retention may help. | 2 |  | Addressed with new slip ring
Upgrade Power Electronics
| Add bi-directional power flow | 1 |  | Boards built next week
| More corrosion resistent housings | 1 |  | Insulation and Coating
| New controller board | 1 |  | Boards built next week
| Buoy logging software changes and new commands | 1 |  | To be done. Maybe not required
Gas Pump Reliability
| Perform longevity test on gas pump | 2 |  | Test Setup complete, need to investigate
| Repair gas pump | 1 |  | Done
| Test or investigate reliability of relief valve | 2
Refurbish Existing Components
| Refurb hydraulic components | 1 |  | Return Nov 20
| Refurb tether terminations | 1
General Electrical Reliability
| Eliminate as many connectors as possible. | 2 |  | Done
| Address debonding of all sub-sea connectors. | 1 |  | Junction box + bulkhead connectors
| Consolidate PTO-PowerConverter CAN and Power into one cable | 1 |  | Comes with new power electronics
| Switch to penetrators with in-line connectors? | 3 |  | Junction Box…
| Add temperature and humidity sensors to controller boards. | 2 |  | Comes with new power electronics
General Software Reliability
| Buoy Controller Stability. This is mostly OK, but the source of the re-boots is unkown. | 2
| Isolate CAN bus throughout. Requires new controller boards. | 2 |  | Comes with new power electronics
| Remove Esteem radio and replace with other short range connection. | 3
| Address spot tracker reliability | 1 |  | New Spot trackers obtained
General Mechanical Reliability
| Address corrosion of Power converter. Not clear if insulation or electrical leakage is this issue | 1 |  | Comes with new power electronics
| Re-mount laser rangefinder for easier installation | 2 |  | Dismissed
| Pneumatic spring penetrators. Upgrade all subject to back pressure to pave-tech design | 1 |  | Done
| Add pressure relief valve to oil compensator, address leaks and investigate reliability | 1 |  | Probably a good idea
| Address reliability of threads between rods. Loctite and/or secondary interference | 1 |  | Loctite and assembly control
| Perform load-path strength analysis | 1 |  | In process, fatigue analysis…
| Analyze load cell data | 2 |  | Feeding fatigue analysis
| Improve Power Converter mount, currently hose clamps. | 1 |  | Hose clamps OK?
| Investigate support for all cables exposed to seawater. (conduit?) | 1 |  | Considered
| Replace (or eliminate) load cell | 1 |  | Eliminate
| Address High-Vibration Environment. Develop secondary securements wherever possible | 1 |  | Ongoing
| Address plan for high-hydrogen percentages. | 1 |  | TBD
| Hydraulic Seal longevity. Essentially unkown and unknowable. | 3
| Improve battery box venting. | 2 |  | TBD
| Waterproof camera | 3 |  | TBD
| Improve seal fence? | 3 |  | TBD

## TaskList
2019-11-03
NSF Radar Project
| Determine Mechanical Mounting | Waiting on Radar Selection | Andy
| Determine Electrical/Software Connections | Waiting on Radar Selection | Andy
PTO Power Electronics
| Board Assembly | Boards/Parts on Order, assembled next week | Scott/Jose
| Board Bringup and Lab Test | Starting Oct 14 | Scott/Andy/Jose
| Implement firmware changes |  | Scott/Andy/Jose
| Mechanical Designs Complete and To Shop |  | Jon
| Fabrication |  | Jon/Shop
Assembly
Battery System
| Charge and Monitor |  | Scott/Jose/Denis
| Move Batteries on buoy |  | Jon/John
Controller Boards
| Layout | In process | Eric/Jose
| Procurment/Assembly/Test |  | Eric/Jose/Andy
| Implement firmware changes for new sensors |  | Andy
PTO Assembly
| CoilCord/Slip Ring testing | Ongoing, changing to new coil-cord | Francois
| Hydraulics Refurb | To be completed early November | Francois/Hydratech
| Coating/Painting as needed |  | Francois
| Set up in Bldg D |  | Francois/All
| Assemble hydraulics, wiring, sensors, top-hat electronics, etc |  | Francois/All
| Terminate Tether |  | Francois/TMT ($)
Set Pressures
Efficiency/Performance Testing
Software Integration
| Select new buoy computer |  | Eric/Andy/Rich
| Implement any new commands needed. None planned, but… |  | Andy/Rich
| Implement changes to data packets. Humidy/Temp for instance |  | Andy/Rich
System Integration
Buoy/PTO/Heave-cone wiring and test
Spot Tracker Testing
| Camera integration and Test | If implemented