## Sheet1
|  | Brett | Brian | Erik | Ben
a. Camera
| i. Integrate WHOI supplied camera and recorder system, which includes the design and fabrication of brackets, modification of wiring and LCB wiring. Write camera control drivers. A DeepSeaPower and Light HD Multi Seacam HDMSC-3085will feed HDSDI through a FleXlink bulkhead connector installed in the DMON port. Modify SCIPI camera drivers to trigger recorder using LANC. | 8 | 2 | 20 | 16
| ii. Install WHOI supplied Ethernet bulkhead connector in spare port on aft endcap and build offload cable. |  |  | 2
| iii. Mount WHOI supplied lights; Cut access hole in shell; Design and manufacturer light brackets; build wet side camera/light cabling | 2 |  | 16
b. LBL Navigation
| i. Work with IntuAware and create a new navigation mode to navigate using Long Base Line acoustic beacons. |  | 15 |  | 15
| ii. Conduct at-sea tests using WHOI supplied LBL transponders | 4 | 10 | 6 | 4
c. Oil plume tracking
| i. Help IntuAware modify existing MBARI plume tracking algorithm and LRAUV vehicle code to work for oil leak plumes |  | 10 |  | 5
| ii. Conduct at least two multi-day sea tests of plume tracking missions from Moss Landing using chlorophyll as the oil proxy. | 6 | 6 | 10
| iii. Pack up the WHOI/DHS LRAUV into shipping crates for WHOI to ship to Santa Barbara or TBD Gulf of Mexico location. | 10 |  | 10
| iv. Support five days of LRAUV operations offshore Santa Barbara or TBD Gulf of Mexico location with at least one person on-site plus vehicle remote piloting from MBARI. | 10 | 14 | 50
d. Under-ice
| i. Support a three-day deployment at a TBD frozen lake with one person on-site. | 10 | 45 | 40
| ii. Modify existing LRAUV missions to perform acoustic homing using the WHOI DUSBL. |  | 10
| iii. Implement acoustic abort and return home mission. |  | 8
Total: |  | 50 | 120 | 154 | 40
planned |  | 185 | 109
target |  | 80 | 120 | 120 | 40