## Sheet1
|  | Brett | Brian | Erik | Ben
a. Camera
| i. Integrate WHOI supplied camera and recorder system, which includes the design and fabrication of brackets, modification of wiring and LCB wiring. Write camera control drivers. A DeepSeaPower and Light HD Multi Seacam HDMSC-3085will feed HDSDI through a FleXlink bulkhead connector installed in the DMON port. Modify SCIPI camera drivers to trigger recorder using LANC. | [5 empty] | 8 | 8 | 20 | 24
| ii. Install WHOI supplied Ethernet bulkhead connector in spare port on aft endcap and build offload cable. | [7 empty] | 2
| iii. Mount WHOI supplied lights; Cut access hole in shell; Design and manufacturer light brackets; build wet side camera/light cabling | [5 empty] | 2 |  | 16
b. LBL Navigation | [8 empty] | 38
| i. Work with IntuAware and create a new navigation mode to navigate using Long Base Line acoustic beacons. |  | 8 |  | 8 | 16
| ii. Conduct at-sea tests using WHOI supplied LBL transponders | 4 | 24 | 5 | 16 | 49
c. Oil plume tracking
| i. Help IntuAware modify existing MBARI plume tracking algorithm and LRAUV vehicle code to work for oil leak plumes |  | 8 |  | 5 | 13
| ii. Conduct at least two multi-day sea tests of plume tracking missions from Moss Landing using chlorophyll as the oil proxy. | 9 | 40 | 30 | 20 | 99
| iii. Pack up the WHOI/DHS LRAUV into shipping crates for WHOI to ship to Santa Barbara or TBD Gulf of Mexico location. | 10 |  | 10 |  | 20
| iv. Support five days of LRAUV operations offshore Santa Barbara or TBD Gulf of Mexico location with at least one person on-site plus vehicle remote piloting from MBARI. | 12 | 14 | 60 |  | 86
d. Under-ice
| i. Support a three-day deployment at a TBD frozen lake with one person on-site. | 15 | 45 | 45 |  | 105
| ii. Modify existing LRAUV missions to perform acoustic homing using the WHOI DUSBL. |  | 10 |  |  | 10
| iii. Implement acoustic abort and return home mission. |  | 16 |  |  | 16
Total: |  | 50 | 165 | 150 | 49 | 414
40
165
0
49
165
419
Note on C30: Enter months of effort; salary will calculate automatically.