## Sheet1
|  | Brett | Brian |  | Ben | Carlos
a. Operations Support and Training
| i. Export and help setup LRAUV Dash infrastructure at WHOI |  | 20 |  |  | 80
| ii. Export and help setup LRAUV data processing pipeline and storage |  | 20 |  |  | 50
| iii. Conduct two tele-training sessions and support new operators |  |  |  | 40
b. Vehicle constrution and upgrade support
| i. Improve existing vehicle build documentation. Add detailed assembly instructions to existing assembly model documents | 60
| ii. Provide timely response to questions during remote vehicle assembly | 50
c. Instrument Integration
| i. Help draft requirements and select an appropriate multibeam sonar | 30
ii. Help with the mechanical, electrical integration and help develop the software drivers and data logging
ii.
d. Oil plume tracking
| i. Work to improve oil plume tracking algorithm and mission based on field trials |  |  |  | 80
| ii. Particpate and support 5-dayLRAUV operations in Santa Barbara oil seep fields in August 2019 with at least one person on-site plus vehicle remote piloting support from MBARI. | 20 | 70 |  | 40
e. Under-ice Operations
i. Modify LRAUV Default Mission to support under ice operations
| ii. Work with Intuaware to improve acoustic data telemetry and acoustic vehicle command |  | 60
| iii. Improve existing acoustic homing, line capture and long-term cable docking |  | 40 |  | 15
| iv. Participate in two 4 day experiments under ice in a small lake and Lake Michigan |  | 40
| v. | 15 | 100
Total: |  | 175 | 350 | 0 | 175 | 130
Note on C34: Enter months of effort; salary will calculate automatically.