Exhibit A
 Statement of Work #4 (year 7)

University of Alaska and WHOI will use reasonable research efforts to develop and demonstrate a system for conducting and reporting oceanographic measurements at high-latitudes across a spectrum of open water to ice-covered waters using an autonomous underwater vehicle. The system builds on an existing Tethys System Long Range Autonomous Underwater Vehicle (“LRAUV”) as it is well-suited for overcoming the many challenges faced, especially for under ice operations.

MBARI’s responsibilities towards reaching that goal during Year 7

To that end, on a schedule from July 2020 through June 2021, MBARI undertakes to perform 1175 hours of engineering work consisting of the following tasks:

- Plume mapping - 240 hours

  - Plume Model

    - Develop standalone application for a static model on BSC - 40 hrs

    - Augment SeaOwl component to ingest external LCM data in simulate hardware mode - 20 hrs

    - Port existing ocean data sim engine (subset of internal sim) to BSC- 20 hrs

    - Refine model for three different static plumes- 20 hrs

    - Refine model to change dynamically -20 hrs

  - On-board Plume Mapping

    - Refine existing plume mapping behavior - 20 hrs

    - Test in Monterey with model and upwelling- 60 hrs

  - Refine BSC environment for external users

  - Generate example BSC app + documentation - 40 hrs

- Upgrade vehicle systems - 300 hours

  - Multibeam sonar integraiton

    - Mechanical integration - 60 hrs

    - Software integration (power, , missions, behavior, timekeeping, automated wpt ingest from MB system) - 60 hrs

    - Develop mapping behavior with MB System input - 40 hrs

  - Inertial Navigation System (INS) integration

    - Mechanical integration - 10 hrs

    - Software integration (alignment behavior, power, depth, nav, ethernet, DVL, GPS ephemeris)- 40 hrs

  - Circular DUSBL

    - New double ping option, and some format changes - 50 hrs

    - Sea trials, testing and refinement - 40 hrs

- Operations Support

  - New England under ice

  - Prep, travel (3 engineers), operations - 240 hrs

  - Great Lakes under ice

  - Prep, travel (3 engineers), operations - 240 hrs

  - Barrow sea tests

  - prep -10 hrs