## Sheet1
YR5 LRAUV Test Deliverables
Compiled 3/20/2019
TASK #
| Priority High | Due Date | Details | Status | Task # | Priority Med | Due Date | Details | Task # | Priorty Low | Due Date | Details
1 | LRAUV USBL functionality with Arctic Buoy | May, want for Demo | vehicle needs a software objective for homing (MBARI) |  | 1 | LRAUV Acomms capability, what can we do and not do? Eg: interrogate vehicle with ship modem or buoy to get vehicle range? Request a status message that includes depth, dark counts, etc.? | within 30 June was what was stated in the YR5 SOW | are we using Gobysoft or is Mike rewriting?What is status?
2 | LRAUV LBL functionality with Arctic Buoy | May, want for Demo | Buoys need to replicate as transponders each having a unique address where position can be given to vehicle. Need a vehicle LBL navigation objective (MBARI) |  | 2 | Dock to line |  | proves robustness of capture nose and DUSBL
3 | Develop/refine oil mapping algorithm | May, want for Demo | MBARI |  | 3 | Send FDOM heat maps from vehicle to buoy or ship modem
4 | add ability for modem to act as transponder based on config settings | April 1, Sandipa | The modem, when configured as a transponder, will listen for its nav signal for a period determined by a timeout setting. It is proposed that this signal be compatible with the comms band detector, i.e. an FM probe that is currently used for sending FSK packets. This implies using the FSK comms channel for nav only. In this transponder mode, the reply can be set to be a DT4 compatible signal that can be received by a DUSBL system on the LRAUV
5 | on vehicle modem side, add capability to the existing $CCPGT command to ping a transponder using a FM mode. | April 1, Sandipa | With these added capabilities (Task 4,5), the modem can be used in different scenarios for providing navigational aid to a vehicle | For example: Homing to a DT4 dock with the LRAUV: An LRAUV, equipped with Micromodem-2 and DUSBL, homes on a dock equipped with a “Sellars” DT4 transponder. In this scenario, the modem uses the $CCPGT command to ping the dock with the appropriate REMUS nav code at 10 kHz. The dock sends a reply at 25 kHz that is heard by the DUSBL. And:
Homing to a Micromodem-2 dock with the LRAUV: In this scenario, the dock is a WHOI Micromodem-2. The dock can be configured to act as a transponder that listens for an FM probe centered at 10 kHz and sends a REMUS ping reply at 25 kHz that can be received by the DUSBL