## Sheet1
Item | Question | Answer | Part Number | Assembly Number
1 | Since the fins are cast, are there drawings for the mold of do I just use the find drawing and ask them to make the mold? Also, we have quite a few spares already that I believe are the older rev. Looks like the only change was a slight decrease in chord lenght so I assume we can still use our spares. | Fin molds are usually made from RTV silicone, which doesn't last very long (~6 months) so new molds are required for every order. | P-200617-08 | A-200618-08
2 | Is FR4 an acceptable substitue for G10? Ive quoted some parts to machine shops and they asked to substitute. The properties look very similar to me but i wanted to check before approving it. | Yes, FR4 is just a fire-resistant version | P-201772-15 | A-201904-17
3 | I've separately forwarded you the part that Nook asked to have replace the current screw ball assembly. Please let me know what you think of the substitute | The suggested replacement is a problem because the lead is 2.5m/turn, verses 1 mm/turn, which is a 2.5 times lower gear ratio that will yield 2.5 times less force and 2.5 time faster. Maybe we can fix this with a different Maxon gearmotor. | ESC-08010-RAEL-4L-270 / ENC-08010-RZN / S
4 | Missing Idler wheel assembly drawings. We have a part that clearly goes in that assembly (P-200563-08) and the idler wheel assembly is listed in the battery pack assembly, but theres no drawing for the idler wheel assembly itself. | OK, I'll create an assembly drawing for this | A-200xxx-07 | A-201906-17
5 | We are missing a part drawing for the maxon mounting board. We could probably laser cut it based on the cad but would be easier if we had a part drawing for material, etc. | This is the PCB otherwise known as Maxon10pinAdaptor | P-201923-17
6 | There is a Keller Series 6 Sensor listed in the Pressure hull main assembly drawing BOM but I could not find it in the CAD or the drawing itself. There is a Keller Series 6 sensor in the pressure hull sub-assembly, so I thought maybe it being listed in the pressure hull assembly bom was an accidental repeat, but wanted to check. | Yes, just one Keller pressure sensor so that must be a repeat. |  | A-201902-17
7 | Missing tail cone drawing |  | P-200517-08 | A-200751-09
8 | Missing G10 fiber nut plates drawing | saw these go out, so you must have found them… | P-201670-14 | A-200751-09