## Sheet1
|  |  | Labor (Hours) | [10 empty] | Material | Outside Srv | Ship Time |  |  | Sub-totals |  | Notes
Task |  |  | Hamilton | Nicholson | ME | Jensen | EE | Anderson | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost | Expense | Labor
System Requirement Development
| Refine Requiements Document |  | 16 | 8 | 24 | 16 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0
| Meet With Vendors |  | 16 | 16 | 32 | 16 | 16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | May require some travel
| Housing Concept Designs |  | 8 | 40 | 48 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Total |  |  | 40 | 64 | 104 | 32 | 32 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 144
[5 empty] | 104 |  | 32 |  | 8
Solicit Quotes
| Develop RFP |  | 8 | 4 | 12 | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| Release RFP |  | 4 | 4 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Answer Questions |  | 84 | 4 | 88 | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Task Total |  |  | 96 | 12 | 108 | 20 | 20 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 136
[5 empty] | 108 |  | 20 |  | 8
Select vendor
| Evaluate proposals |  | 4 | 4 | 8 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| Follow up |  | 4 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Selection |  | 4 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Refactor budget |  | 4 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Total |  |  | 16 | 4 | 20 | 16 | 16 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 40
[5 empty] | 20 |  | 16 |  | 4
Procurement and Supporting Design Work
| Interface electronics design work |  | 16 | 24 | 40 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Software integration |  | 16 | 8 | 24 | 8 | 8 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0
| Housing design |  | 16 | 120 | 136 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Total |  |  | 48 | 152 | 200 | 40 | 40 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 320
[5 empty] | 200 |  | 40 |  | 80
Assembly And Evaluation
| Intake and initial performance testing |  | 8 | 4 | 12 | 8 | 8 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0
| Integration with existing electronics and housings |  | 8 | 16 | 24 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| System testing |  | 40 | 8 | 48 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0
| Performance evaluation report |  | 40 | 8 | 48 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0
Task Total |  |  | 96 | 36 | 132 | 128 | 128 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 360
[5 empty] | 132 |  | 128 |  | 100
|  |  | Labor (Hours) | [10 empty] | Material | Outside Srv | Ship Time
[5 empty] | ME |  | EE |  | SE | ME Tech | EE Tech | Machinist | Divers |  |  | Ship | Time | Cost
Totals |  |  | 296 | 268 | 564 | 236 | 236 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 1000
[5 empty] | 564 |  | 236 |  | #REF! | 0 | 0 | 0 | 0 | [5 empty] | 0 | #REF!
1000
2016 Totals |  |  | 392 | 396 | 1104 | 244 | 512 |  | 380 | 340 | 202 | 136 | 56 | 47000 | 7400 | 0 | 0 | 8000 | 62400 | 2730
1996
Milestone
| 1 | 1st Deploy | #REF! | #REF! |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF!
| 2 | Power+Battery | #REF! | #REF! |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF!
| 3 | 2nd Deploy | #REF! | #REF! |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF!
| 4 | LRI Report | #REF! | #REF! |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF!
| 5 | Winter Deployment | #REF! | #REF! |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[10 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | 564 |  | 236 |  | 200 | [10 empty] | 1000