## WBS
|  |  | Labor (Hours) | [5 empty] | Material | Outside Srv | Other | Ship Time |  | Sub-totals |  | Notes
Task |  |  | Hamilton | Jensen | Bird | Machinist | E. Tech | MOT |  |  |  | Ship | Time | Expense | Labor (hrs)
Sampler Preliminary and Final Design Work
| Battery Housing Design |  | 20 |  | 20
| Motor Housing Design |  | 20 |  | 20
| Electronics Housing Design |  | 20 | 8 | 18
| Filter-Holder assembly design |  | 8 |  | 100
| Controller Electronics |  | 8 | 32
| Frame Design |  | 32
| Design Review |  | 16 | 2 | 2
Task Total |  |  | 124 | 42 | 160 | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 326
Electronics Acqusistion, Fabrication, and Assembly
| Battery Purchase |  |  | 4 |  |  |  |  | 1000 | [6 empty] | Rebuild items: Seals, motor, zincs. Replace items: Filter, tether guide.
| Charger Purchase |  |  | 4 |  |  |  |  | 1000
| Motor/Drive Purchase |  | 4 | 4 |  |  |  |  | 2000
| Pressure Sensor Purchase |  | 1 | 1 |  |  |  |  | 500
| Switch Electronics Purchase |  | 2 | 2 |  |  |  |  | 250
| Connector Purchase |  | 2 | 2 |  |  | 2 |  | 2000
| Misc. Component Purchases |  | 4 | 4 | 4 |  | 4 |  | 2000
| Controller Board Fabrication |  | 2 | 2 |  |  | 8 |  | 500
| Electronic Assembly and Test |  | 8 | 8 |  |  | 8
Task Total |  |  | 23 | 31 | 4 |  | 22 |  | 9250 | 0 |  |  |  | 9250 | 80
Mechanical Acqusistion, Fabrication, and Assembly
| Fabricate Battery Housings (2) |  | 4 |  |  | 36 | 8 |  | 4000
| Fabricate Electronics Housing |  | 4 |  |  | 18 | 8 |  | 2000
| Fabricate Motor Housing |  | 4 |  |  | 18 | 8 |  | 2000
| Fabricate Filter Holder Assembly |  | 4 |  | 100 | 13 |  |  | 6000
| Fabricate Frame |  | 4 |  | 60 | 20 |  |  | 1500
| Anodization |  |  |  | 8 |  |  |  |  | 4000
| Assembly |  | 8 |  | 40
Task Total |  |  | 28 | 0 | 208 | 105 | 24 |  | 15500 | 4000 |  |  |  | 19500 | 365
Testing
| Test Motor/Pump with filter holder |  | 5 | 4 | 8
| Total volume capability test |  | 4 | 5 | 8
| Self-contamination tests |  | 4 | 4 | 8
| At-Sea Engineering Tests (3) |  | 24 | 24 | 24 |  |  | 12 |  |  |  | Paragon | 6
Task Total |  |  | 37 | 37 | 48 | 0 | 0 | 12 | 0 | 0 |  | Paragon | 6 | 0 | 134
System Use
| Lab Supplies (Solvents, Glass Ware, filters, etc.) | [7 empty] | 7500
| Analysis of Collected Samples | [8 empty] | 20000
| At-Sea Use | [6 empty] | 12 |  |  |  | Paragon | 6
Task Total |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 7500 | 20000 |  | Paragon | 6 | 27500 | 12
Travel (International)
| Registration and Travel to present project results - for Choy | [9 empty] | 4500
Task Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 |  |  | 4500 | 0
Books & Subscriptions
| Books and Professional Membership for Choy | [9 empty] | 720
Task Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 |  |  | 720 | 0
|  |  | Hamilton | Jensen | Bird | Machinist | E. Tech | MOT |  |  |  | Ship | Time | Expense | Labor (hrs)
Totals |  |  | 212 | 110 | 420 | 105 | 46 | 24 | 32250 | 24000 | 5220 | Paragon | 12 | 61470 | 917
[6 empty] | 105 | 46 | [6 empty] | 61482 | #REF!
2016 Totals |  |  | 392 | 396 | 276 | 136 | 136 |  | 47000 | 7400 |  | 0 | 0 | 62400 | 2730
Milestone
| 1 | 1st Deploy | 49.5 | 35.5 | 81 | 0 | 11
| 2 | Power+Battery | #REF! | #REF! | #REF! | #REF! | #REF!
| 3 | 2nd Deploy | 49.5 | 35.5 | 81 | 0 | 11
| 4 | LRI Report | 48 | 2 | 2 | 0 | 0
| 5 | Winter Deployment | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
[5 empty] | #REF! | #REF! | #REF! |  | #REF!