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Preliminary Workplan and Budget for MARS Biological Survey

Prepared for MBARI

May 8 2007

ABA Consultants will provide the following services to MBARI as part of the MARS cable project. ABA Consultants will be the prime on the project, but will sub-contract some aspects of the work to individuals at Moss Landing Marine Labs. We will be happy to work closely with MBARI personnel as required. The budgets include data only. Data interpretation and report writing could be done on a time and materials basis, or we could provide a budget estimate when more details are known.

Task 1: Analysis of MBARI samples

ABA Consultants will sort and perform taxonomy on samples collected by MBARI. The samples are 7.5 cm in diameter and sieved through 0.3 mm screens. ABA will sort the samples, identify the macrofauna to the lowest feasible taxonomic level, and enter the data into a database. The QA/QC procedures used during the original MCI project will be followed. No interpretation or writeup of the data is included in the cost per sample.  Data will be provided to MBARI within 120 days of the receipt of samples.

	Samples collected by MBARI (2008)
	

	type
	sieve
	#
	cost/
	total

	 
	(mm)
	 
	 
	 

	7.5cm core
	0.3
	60
	$ 315
	$18,900


ABA Consultants


[image: image1.jpg]