## Cover
|  |  | © 2006 |  | Marine Operations Department
| Issue: PSR06 |  |  |  | DATE: 06 Nov 2006
AUTHORISATION
SIGNATORY |  | SIGNATURE |  | NAME |  | DATE
ORIGINATOR |  |  |  | A. Palmer-Felgate |  | 2006-11-06
CHECKED
PURCHASER
ACCEPTED
MARS
MOSS LANDING to NODE
ROUTE POSITION LIST

## RPL Abbreviations
ROUTE POSITION LIST (RPL) ABBREVIATIONS
RPL Naming Convention |  |  | RPL Issue
DESK TOP STUDY RPLs |  |  | DTS (1,2…)
SURVEY ROUTE RPLs - (Agreed survey route with subsequent changes, during survey ops) |  |  | SR (1, 2…)
POST SURVEY ROUTE RPLs - (incl. Slack, PLUP/DN, Bus, transitions and Repeaters etc) |  |  | PSR (1, 2…)
AS-BUILT RPL - (Manufactured lengths) |  |  | AB (1, 2…)
POST-LOAD RPLs - (Loaded cable lengths) |  |  | PL (1, 2…)
AS-LAID RPLs - (subsequent issue numbers reflect repairs/changes) |  |  | AL (1, 2…)
Abbreviation | Meaning | Typical Use in MakaiPlan | MakaiPlan Type
AB-xxx | As-Built
AC | Alter Course
AF | As Found (Cable) by MG / SS | CX China-US AF MAG | Ref
AL-xxx | As-Laid
BA | Beach Allowance | BA 50m | Cable
BAS | Burial Assessment Survey
BJ | Beach Joint |  | Body
BL | Baseline |  | Ref
BMH | Beach ManHole | BMH Porth Curno
BU-xxx | Branching Unit | BU-001 Abidjan | Body
CC | Cable Corridor | Enter CC | Ref
CR | Contract Route
CRS | Cable Route Study
CX | Cable Crossing | CX Old Cable OOS DB | Ref
CZ | Contiguous Zone |  | Ref
DA | Double Armour |  | Cable
DA1 | Double Armour 1 |  | Cable
DA2 | Double Armour 2 |  | Cable
DAH | Double Armour Heavy |  | Cable
DAM | Double Armour Medium |  | Cable
DB | Database position of cable | CX Old Cable OOS DB
DE | Duct End | DE | Ref
DS | Duct start | DS | Ref
DTS | Desk Top Study
DWA | Deep Water Armoured |  | Cable
DWP | Deep Water Protected |  | Cable
EEZ | Exclusive Economic Zone | EEZ Country MB | Ref
EOB | End of burial | PLUP EOB | Ref
EP | End pipe | EP | Ref
FS | Final Splice | FS Segment Name | Body
FSA | Final Splice Allowance |  | Cable
FSPL | Fibre Splice |  | Body
HA | Heavy Armour |  | Cable
IN | Information | IN Start of CC | Ref
IPM | Installation Project Manager
IS | Initial Splice | IS Segment Name | Body
JB-xxx | Joint Box | JB-001 Any other comment | Body
KP | Kilometre Point
LC | Land Cable (instead of Land) |  | Cable
LP | Landing Point | LP Porth Curno | Ref
LPM | Line Project Manager
LW | Lightweight |  | Cable
LWA | Light Wire Armoured |  | Cable
LWP | Lightweight Protected |  | Cable
LWS | Lightweight Screened |  | Cable
MB | Maritime Boundary | TW Country MB | Ref
MG | Magnetometer Identified Cable | CX Unidentified MG
MIG | Marine Installation Guide
OOS | Out of Service | CX Old Cable OOS DB
PEU-xxx | Passive Equaliser Unit | PEU-001 | Body
PLB | Post Lay Burial | PLB Start | Ref
PLDN | Plough Down | PLDN | Ref
PLI | Post-Lay Inspection
PLIB | Post Lay Inspection and Burial
PLUP | Plough Up | PLUP | Ref
PL-xxx | Post Load
PN | Planned cable | CX Planned cable name PN | Ref
PSCF | Pure Silica Core Fibre
PSR-xxx | Post Survey Route
PX | Pipeline Crossing | PX Pipeline name | Ref
RA | Rock Armour |  | Cable
RAH | Remote Amplifier Housing | RAH-001 | Body
RCLW | Reinforced Cable Lightweight |  | Cable
RCLWP | Reinforced Cable Lightweight Protected |  | Cable
REH | Route Engineering Handbook
RPL | Route Position List
RPTR-xxx | Repeater | RPTR-001 | Body
SA | Single Armour | TR SA/SAH | Cable
SAH | Single Armour Heavy | TR SA/SAH | Cable
SAL | Single Armour Light | TR SA/SAL | Cable
SC | Slack Change | SC 3% | Ref
SE | Shore End |  | Ref
SEQ-xxx | Shape Equaliser | SEQ-001 | Body
SJ-YYY-xxx | Ship Joint | SJ-OVK-001 | Body
SLD | Straight Line Diagram
SLLI | Shipboard Load & Lay Instructions
SOB | Start of burial | PLDN SOB | Ref
SP | Start pipe | SP | Ref
SPA | Special Applications |  | Cable
SPDA | Special Purpose Double Armour |  | Cable
SPEU-xxx | Super Passive Equaliser Unit | SPEU-001 | Body
SR-xxx | Survey Route
SS | Side Scan Identified Cable | CX Cable name AF SS | Ref
TEQA | Active Tilt Equaliser | TEQA-001 | Body
TEQP | Passive Tilt Equaliser | TEQP-001 | Body
TEQ-xxx | Tilt Equaliser | TEQ-001 | Body
TO | Tolerance | TO +350m/-25m | Ref
TP | Temperature
TPA | Traffic Precautionary Area | Enter TPA
TR | Transition | TR LWP-40/LW--40 | Body
TSS | Traffic Separation Scheme | Enter TSS
TSZ | Traffic Separation Zone | Enter TSZ
TW | Territorial Waters | TW Country MB | Ref
WD | Water Depth | WD 2300m | Ref
WK | Wreck | WK Wreck name | Ref

## Check List
ROUTE POSITION LIST (RPL) CHECKLIST | Yes | No | N/A
Contingency on planned transitions?
Final splice allowance included?
Branching Unit allowance included?
Cable on beach for joint and coil?
Is the landing point on the survey the same position as the manhole position?
Do the cable transitions follow logically?
Are plough up and plough down positions in agreement with cable types?
Check repeater positioning against:
Final & Initial splice, deep burial and PLUP/PLDN positions, etc
Does the slack change at the plough up and down positions?
Are the MakaiPlan bottom slack values conforming to the current "Route Engineering Handbook" guidelines?
Laying buffer required/not required?
Correct projection and central meridian?
Has the total distance changed since last issue?
Has the total cable length changed since last issue?
Has the RPL been printed in Mercator and courses checked?
Has the entire route been plotted on A0 paper?
Does all route engineering conform to the current "Route Engineering Guidelines"
Has a copy of this RPL been passed to Marine Engineering Management for database inclusion?

## Change List
RPL, SLD & Route Engineering - CHANGES & TRACKING SHEET
ISSUE | DOCUMENT | DATE | CHANGE
CRE | RPL |  | CRE route Route length: km Cable length: km
PSR-01 | RPL | 2006-02-08 | Post AUV survey RPL. Manufactures lengths applied - Note joint required to merge SA sections Route length: 52.100km Cable length: 52.362km
PSR-02 | RPL | 2006-02-09 | Re-engineered to allow 2.3 km spare SA Route length: 52.100km Cable length: 52.657km
PSR-03 | RPL | 2006-03-24 | Route reversed for eastward lay direction. FS replaced with ship joint and FS allowance removed Route length: 52.100km Cable length: 52.381km
PSR-04 | RPL | 2006-04-18 | Re-route off Duke Energy pipe to increase separation to >100m Route length: 52.121km Cable length: 52.396km
PSR-05 | RPL | 2006-05-11 | HDD exit point coordinate (landward end) updated to asbuilt coordinate (N4074054.4, E608118.8 WGS84, UTM Z10N). Route length: 52.121km Cable length: 52.396km
PSR-06 | RPL | 2006-11-06 | Route reversed for new lay direction. Cable lengths updated from tanking plan on Maersk Defender Route length: 52.121km Cable length: 52.396km

## RPL
Point No | Comment | Latitude |  |  | Longitude |  |  | Brg (°) | Depth (m) | Leg Dist (km) | Cum KP Dist (km) | Reverse KP Dist (km) | Leg Cable (km) | Cum Cable (km) | Comment | Auto Label | Bottom Slack (%) | Body | Cum Dist by Rptr (km) | Reverse Cable Dist (km) | Bottom RPL:
MARS
1 | HDD Start | 36 | 48.3695 | N | 121 | 47.2771 | W |  | 20 |  | 0 | 52.121 |  | 0 | 50m allowance Assy: 50 allowance |  |  |  |  | 52.396 | mars_rovsurvey_ab-06_06-nov-06
[8 empty] | 294.934 |  | 0 |  |  | 0.05 |  | Cable Allowance | Pt-Cable | N/A |  |  |  | 2006-11-06
2 | Cable Allowance | 36 | 48.3695 | N | 121 | 47.2771 | W |  | 20 |  | 0 | 52.121 |  | 0.05 | Start of cable allowance |  |  |  |  | 52.346 | 16:25
[8 empty] | 294.934 |  | 1.041 |  |  | 1.049 |  |  |  | 0.8
3 | HDD End | 36 | 48.6067 | N | 121 | 47.9116 | W |  | 20 |  | 1.041 | 51.08 |  | 1.099 | [5 empty] | 51.297
[8 empty] | 295.316 |  | 0.004 |  |  | 0.004 |  |  |  | 0.8
4 | SC 0.25% | 36 | 48.6077 | N | 121 | 47.9142 | W |  | 20 |  | 1.045 | 51.076 |  | 1.103 | [5 empty] | 51.293
[8 empty] | 295.316 |  | 0.005 |  |  | 0.005 |  |  |  | 0.25
5 | PLDN | 36 | 48.6088 | N | 121 | 47.917 | W |  | 20 |  | 1.05 | 51.071 |  | 1.108 |  | PLDN |  |  |  | 51.288
[8 empty] | 295.316 |  | 0.398 |  |  | 0.399 |  |  | Bury | 0.25
6 | AC | 36 | 48.7008 | N | 121 | 48.159 | W |  | 20 |  | 1.448 | 50.673 |  | 1.507 |  | AC1 |  |  |  | 50.889
[8 empty] | 316.681 |  | 5.257 |  |  | 5.271 |  |  | Bury | 0.25
7 | ENTER Naval Operating Area | 36 | 50.769 | N | 121 | 50.5851 | W |  | 25 |  | 6.705 | 45.416 |  | 6.778 | ng Area |  |  |  |  | 45.618
[8 empty] | 316.681 |  | 0.161 |  |  | 0.161 |  |  | Bury | 0.25
8 | AC | 36 | 50.832 | N | 121 | 50.659 | W |  | 26 |  | 6.866 | 45.255 |  | 6.939 |  | AC2 |  |  |  | 45.457
[8 empty] | 301.665 |  | 2.657 |  |  | 2.663 |  |  | Bury | 0.25
9 | AC | 36 | 51.5861 | N | 121 | 52.1804 | W |  | 36 |  | 9.523 | 42.598 |  | 9.602 |  | AC3 |  |  |  | 42.794
[8 empty] | 290.58 |  | 7.491 |  |  | 7.511 |  |  | Bury | 0.25
10 | AC | 36 | 53.0099 | N | 121 | 56.9002 | W |  | 40 |  | 17.014 | 35.107 |  | 17.113 |  | AC4 |  |  |  | 35.283
[8 empty] | 281.746 |  | 1.086 |  |  | 1.088 |  |  | Bury | 0.25
11 | AC | 36 | 53.1294 | N | 121 | 57.6156 | W |  | 40 |  | 18.1 | 34.021 |  | 18.201 |  | AC5 |  |  |  | 34.195
[8 empty] | 270.31 |  | 1.491 |  |  | 1.495 |  |  | Bury | 0.25
12 | EXIT Naval Operating Area | 36 | 53.1338 | N | 121 | 58.6191 | W |  | 44 |  | 19.591 | 32.53 |  | 19.696 | ng Area |  |  |  |  | 32.7
[8 empty] | 270.31 |  | 4.876 |  |  | 4.888 |  |  | Bury | 0.25
13 | AC | 36 | 53.1481 | N | 122 | 1.9011 | W |  | 60 |  | 24.467 | 27.654 |  | 24.584 |  | AC6 |  |  |  | 27.812
[8 empty] | 255.329 |  | 2.556 |  |  | 2.562 |  |  | Bury | 0.25
14 | AC | 36 | 52.7982 | N | 122 | 3.5649 | W |  | 71 |  | 27.023 | 25.098 |  | 27.146 |  | AC7 |  |  |  | 25.25
[8 empty] | 240.403 |  | 1.172 |  |  | 1.175 |  |  | Bury | 0.25
15 | 3NM LIMIT | 36 | 52.4852 | N | 122 | 4.2507 | W |  | 79 |  | 28.195 | 23.926 |  | 28.321 | [5 empty] | 24.075
[8 empty] | 240.403 |  | 5.172 |  |  | 5.185 |  |  | Bury | 0.25
16 | TR SAL/SA | 36 | 51.1041 | N | 122 | 7.2766 | W |  | 101 |  | 33.367 | 18.754 |  | 33.506 | [5 empty] | 18.89
[8 empty] | 240.403 |  | 1.437 |  |  | 1.441 |  |  | Bury | 0.25
17 | AC | 36 | 50.7203 | N | 122 | 8.1174 | W |  | 109 |  | 34.804 | 17.317 |  | 34.947 | [5 empty] | 17.449
[8 empty] | 240.885 |  | 0.726 |  |  | 0.728 |  |  | Bury | 0.25
18 | AC | 36 | 50.5292 | N | 122 | 8.5443 | W |  | 114 |  | 35.53 | 16.591 |  | 35.675 |  | AC8 |  |  |  | 16.721
[8 empty] | 258.155 |  | 0.308 |  |  | 0.309 |  |  | Bury | 0.25
19 | AC | 36 | 50.495 | N | 122 | 8.7471 | W |  | 116 |  | 35.838 | 16.283 |  | 35.984 |  | AC9 |  |  |  | 16.412
[8 empty] | 244.436 |  | 0.25 |  |  | 0.251 |  |  | Bury | 0.25
20 | PLUP | 36 | 50.4367 | N | 122 | 8.8987 | W |  | 120 |  | 36.088 | 16.033 |  | 36.235 |  | PLUP |  |  |  | 16.161
[8 empty] | 244.436 |  | 0.002 |  |  | 0.002 |  |  |  | 0.25
21 | SC 1.0% | 36 | 50.4362 | N | 122 | 8.8999 | W |  | 120 |  | 36.09 | 16.031 |  | 36.237 | [5 empty] | 16.159
[8 empty] | 244.436 |  | 0.096 |  |  | 0.096 |  |  |  | 1
22 | Smooth Ridge Start | 36 | 50.4139 | N | 122 | 8.958 | W |  | 122 |  | 36.186 | 15.935 |  | 36.333 | [5 empty] | 16.063
[8 empty] | 244.436 |  | 0.231 |  |  | 0.233 |  |  |  | 1
23 | AC | 36 | 50.3601 | N | 122 | 9.098 | W |  | 127 |  | 36.417 | 15.704 |  | 36.566 |  | AC10 |  |  |  | 15.83
[8 empty] | 245.901 |  | 0.546 |  |  | 0.553 |  |  |  | 1
24 | SJ 1 | 36 | 50.2395 | N | 122 | 9.4335 | W |  | 154 |  | 36.963 | 15.158 |  | 37.119 | Assy: Start of cable allowance | AC11 |  | JNT-A |  | 15.277
[8 empty] | 245.901 |  | 0.029 |  |  | 0.03 |  |  |  | 1
25 | AC | 36 | 50.2361 | N | 122 | 9.4528 | W |  | 157 |  | 36.992 | 15.129 |  | 37.149 |  | AC12 |  |  |  | 15.247
[8 empty] | 249.677 |  | 0.13 |  |  | 0.132 |  |  |  | 1
26 | AC | 36 | 50.2117 | N | 122 | 9.5348 | W |  | 175 |  | 37.122 | 14.999 |  | 37.281 |  | AC13 |  |  |  | 15.115
[8 empty] | 236.505 |  | 0.185 |  |  | 0.191 |  |  |  | 1
27 | AC | 36 | 50.1568 | N | 122 | 9.6381 | W |  | 214 |  | 37.307 | 14.814 |  | 37.472 |  | AC14 |  |  |  | 14.924
[8 empty] | 226.948 |  | 0.555 |  |  | 0.567 |  |  |  | 1
28 | AC | 36 | 49.9516 | N | 122 | 9.9113 | W |  | 294 |  | 37.862 | 14.259 |  | 38.039 |  | AC15 |  |  |  | 14.357
[8 empty] | 214.624 |  | 0.459 |  |  | 0.464 |  |  |  | 1
29 | AC | 36 | 49.7476 | N | 122 | 10.0865 | W |  | 309 |  | 38.321 | 13.8 |  | 38.503 |  | AC16 |  |  |  | 13.893
[8 empty] | 200.45 |  | 0.565 |  |  | 0.571 |  |  |  | 1
30 | AC | 36 | 49.4611 | N | 122 | 10.2194 | W |  | 324 |  | 38.886 | 13.235 |  | 39.074 |  | AC17 |  |  |  | 13.322
[8 empty] | 192.967 |  | 1.08 |  |  | 1.091 |  |  |  | 1
31 | AC | 36 | 48.8925 | N | 122 | 10.3822 | W |  | 365 |  | 39.966 | 12.155 |  | 40.165 |  | AC18 |  |  |  | 12.231
[8 empty] | 210.998 |  | 0.585 |  |  | 0.591 |  |  |  | 1
32 | AC | 36 | 48.6214 | N | 122 | 10.5848 | W |  | 383 |  | 40.551 | 11.57 |  | 40.756 |  | AC19 |  |  |  | 11.64
[8 empty] | 224.146 |  | 0.718 |  |  | 0.727 |  |  |  | 1
33 | AC | 36 | 48.3427 | N | 122 | 10.9212 | W |  | 422 |  | 41.269 | 10.852 |  | 41.483 |  | AC20 |  |  |  | 10.913
[8 empty] | 214.785 |  | 1.107 |  |  | 1.119 |  |  |  | 1
34 | AC | 36 | 47.851 | N | 122 | 11.346 | W |  | 445 |  | 42.376 | 9.745 |  | 42.602 |  | AC21 |  |  |  | 9.794
[8 empty] | 200.556 |  | 0.142 |  |  | 0.143 |  |  |  | 1
35 | Smooth Ridge End | 36 | 47.7793 | N | 122 | 11.3794 | W |  | 449 |  | 42.518 | 9.603 |  | 42.745 | [5 empty] | 9.651
[8 empty] | 200.556 |  | 0.075 |  |  | 0.076 |  |  |  | 1
36 | PLDN | 36 | 47.7412 | N | 122 | 11.3971 | W |  | 451 |  | 42.593 | 9.528 |  | 42.821 |  | PLDN |  |  |  | 9.575
[8 empty] | 200.556 |  | 0.002 |  |  | 0.001 |  |  | Bury | 1
37 | SC 0.25% | 36 | 47.7404 | N | 122 | 11.3975 | W |  | 451 |  | 42.595 | 9.526 |  | 42.822 | [5 empty] | 9.574
[8 empty] | 200.556 |  | 0.856 |  |  | 0.859 |  |  | Bury | 0.25
38 | AC | 36 | 47.3069 | N | 122 | 11.5997 | W |  | 481 |  | 43.451 | 8.67 |  | 43.681 |  | AC22 |  |  |  | 8.715
[8 empty] | 186.34 |  | 1.058 |  |  | 1.062 |  |  | Bury | 0.25
39 | TR SA/SAL | 36 | 46.7384 | N | 122 | 11.6782 | W |  | 528 |  | 44.509 | 7.612 |  | 44.743 | [5 empty] | 7.653
[8 empty] | 186.34 |  | 0.081 |  |  | 0.082 |  |  | Bury | 0.25
40 | AC | 36 | 46.6947 | N | 122 | 11.6842 | W |  | 533 |  | 44.59 | 7.531 |  | 44.825 |  | AC23 |  |  |  | 7.571
[8 empty] | 172.147 |  | 1.053 |  |  | 1.057 |  |  | Bury | 0.25
41 | AC | 36 | 46.131 | N | 122 | 11.5876 | W |  | 605 |  | 45.643 | 6.478 |  | 45.882 |  | AC24 |  |  |  | 6.514
[8 empty] | 158.025 |  | 0.135 |  |  | 0.137 |  |  | Bury | 0.25
42 | TW USA EXIT | 36 | 46.063 | N | 122 | 11.5535 | W |  | 617 |  | 45.778 | 6.343 |  | 46.019 | [5 empty] | 6.377
[8 empty] | 158.025 |  | 0.97 |  |  | 0.975 |  |  | Bury | 0.25
43 | AC | 36 | 45.5769 | N | 122 | 11.3097 | W |  | 693 |  | 46.748 | 5.373 |  | 46.994 |  | AC25 |  |  |  | 5.402
[8 empty] | 170.272 |  | 1.277 |  |  | 1.283 |  |  | Bury | 0.25
44 | AC | 36 | 44.8964 | N | 122 | 11.1647 | W |  | 760 |  | 48.025 | 4.096 |  | 48.277 |  | AC26 |  |  |  | 4.119
[8 empty] | 180.922 |  | 2.748 |  |  | 2.756 |  |  | Bury | 0.25
45 | PLUP | 36 | 43.4107 | N | 122 | 11.1944 | W |  | 822 |  | 50.773 | 1.348 |  | 51.033 | 1.5 x WD before NODE | PLUP |  |  |  | 1.363
[8 empty] | 180.922 |  | 0.002 |  |  | 0.002 |  |  |  | 0.25
46 | SC 1.0% | 36 | 43.4098 | N | 122 | 11.1945 | W |  | 823 |  | 50.775 | 1.346 |  | 51.035 | [5 empty] | 1.361
[8 empty] | 180.922 |  | 1.271 |  |  | 1.286 |  |  |  | 1
47 | CTA Tail Start SAH-20 | 36 | 42.7223 | N | 122 | 11.2082 | W |  | 880 |  | 52.046 | 0.075 |  | 52.321 | 75m tail on CTA Assy: 75m tail on TRF |  |  |  |  | 0.075
[8 empty] | 180.922 |  | 0.075 |  |  | 0.075 |  |  |  | 1
48 | NODE | 36 | 42.682 | N | 122 | 11.209 | W |  | 880 |  | 52.121 | 0 |  | 52.396 | [5 empty] | 0
Note on B3: 50m allowance Assy: 50 allowance
Note on B5: Start of cable allowance
Note on B49: Assy: Start of cable allowance
Note on B91: 1.5 x WD before NODE
Note on B95: 75m tail on CTA Assy: 75m tail on TRF

## SLD
BMH |  | SA |  | SJ 1 |  | SA |  | SAL |  | SAH-20 |  | NODE
| SAL |  | SA |  | SA |  | SA |  | SAL |  | SAH-20
| 33.506 |  | 3.613 |  | 0 |  | 7.624 |  | 7.578 |  | 0.075
0 |  | 33.506 |  | 37.119 |  | 37.119 |  | 44.743 |  | 52.321 |  | 52.396
WD 880m
CABLE SUMMARY | [5 empty] | BODIES
CABLE | SAL | SA | SA-C7 | TOTAL |  | JOINT | 1
[6 empty] | BU | 1
SYSTEM | 41.084 | 11.237 | 0.075 | 52.396
SPARE
TOTAL | 41.084 | 11.237 | 0.075 | 52.396
SPARES NOT INCLUDED

## Crossings
Comment | Cable Status | Cable Type | Method located/ Info Srce | Action Needed | Latitude |  |  | Longitude |  |  | Depth (m) | Cum KP Dist (km) | System Cable Type | Xing Angle (deg) | Crossed Cable type | Cable Owner | Sediment Type | Distance to SYSTEM RPTR (km) | Distance to Existing RPTR (km)
Pipeline | AF IS |  | SSS | PLB | 36 | 48.7424 | N | 121 | 48.0889 | W | 19 | 50.694 | SAL
| RC | Shelf (<xxxxm water depth - SUBJECT TO ROUTE CLEARANCE FOR BURIAL
| None | Shelf (<xxxxm water depth - NO BURIAL/SURFACE LAID (no RC needed)
| None | Deep Water (>xxxxm water depth = surface laid)
| PROP | Proposed Cable System
| OOS | Out-of-Service Cable
| IS | In-Service Cable / Pipeline
| PLB | Post lay burial required at in-service crossing
| MAGGIE | Identified by Magnetometer. In-service cables subject 250m PLUP & PLDN
| AF (SSS) | Identified by Side Scan Sonar. In-service cables subject 250m PLUP & PLDN
| AF (SBP) | Identified by Sub-Bottom Profiler. In-service cables subject 250m PLUP & PLDN
| ARCS | Admiralty Charts
| DB (ASN) | ASN Database. In-service cables subject 500m PLUP & PLDN
| DB (GMSL) | Global Marine Systems Limited Database (Date). In-service cables subject 500m PLUP & PLDN

## Route Eng
Start Position | End Position | Start KP | End KP | Leg Distance (km) | Cable Type | Average Slack (%) | Burial Type | Comments
NOT COMPLETED