## AsLaidRPL
SYSTEM: MARS
GEODETIC SYSTEM: WGS-84 |  |  |  | AS LAID ROUTE POSITION LIST (Final) |  |  | ISSUE: 1
NAVIGATION SYSTEM: DIFFERENTIAL GPS | [6 empty] | DATE: 03 Apr 07
LINE | VESSEL NAME | OPERATION DATE | POSITION |  | REMARKS | BURIAL | WATER
NO. |  |  | LATITUDE | LONGITUDE | SPLICES, ALTER COURSE, | DEPTH | DEPTH (m) | COMMENTS
[5 empty] | CABLE CROSSINGS ETC. | (cm)
1 | Global Sentinel | 2007-03-14 | 36° 48.369' N | 121° 47.277' W | HDD Start |  | 0
2 | Global Sentinel | 2007-03-14 | 36° 48.369' N | 121° 47.277' W | Cable allowance |  | 0 | 64m cable retained at beach manhole
3 | Global Sentinel | 2007-03-14 | 36° 48.607' N | 121° 47.912' W | HDD End |  | 20
4 | Global Sentinel | 2007-03-16 | 36° 48.650' N | 121° 48.025' W | Plow Down | 151 | 22 | PLIB completed 21 Mar 07
5 | Global Sentinel | 2007-03-16 | 36° 48.680' N | 121° 48.101' W | A/C | 79 | 22
6 | Global Sentinel | 2007-03-16 | 36° 48.706' N | 121° 48.159' W | A/C | 70 | 22
7 | Global Sentinel | 2007-03-16 | 36° 48.739' N | 121° 48.204' W | A/C | 110 | 21
8 | Global Sentinel | 2007-03-17 | 36° 50.769' N | 121° 50.585' W | Enter Naval Ops Area | 116 | 27
9 | Global Sentinel | 2007-03-17 | 36° 50.832' N | 121° 50.659' W | A/C | 69 | 27
10 | Global Sentinel | 2007-03-19 | 36° 51.585' N | 121° 52.181' W | A/C | 69 | 38
11 | Global Sentinel | 2007-03-17 | 36° 53.009' N | 121° 56.900' W | A/C | 116 | 34
12 | Global Sentinel | 2007-03-17 | 36° 53.127' N | 121° 57.611' W | A/C | 81 | 34
13 | Global Sentinel | 2007-03-19 | 36° 53.134' N | 121° 58.619' W | Exit Naval Ops Area | 83 | 43
14 | Global Sentinel | 2007-03-18 | 36° 53.144' N | 122° 01.901' W | A/C | 81 | 60
15 | Global Sentinel | 2007-03-18 | 36° 52.798' N | 122° 03.565' W | A/C | 135 | 75
16 | Global Sentinel | 2007-03-18 | 36° 52.479' N | 122° 04.263' W | Exit 3NM LIMIT | 141 | 83
17 | Global Sentinel | 2007-03-19 | 36° 51.093' N | 122° 07.302' W | Splice Box | 145 | 106
18 | Global Sentinel | 2007-03-19 | 36° 50.720' N | 122° 08.117' W | A/C | 96 | 113
19 | Global Sentinel | 2007-03-19 | 36° 50.609' N | 122° 08.313' W | A/C | 57 | 116
20 | Global Sentinel | 2007-03-20 | 36° 50.531' N | 122° 08.547' W | A/C | 93 | 118
21 | Global Sentinel | 2007-03-20 | 36° 50.494' N | 122° 08.746' W | A/C | 68 | 123
22 | Global Sentinel | 2007-03-20 | 36° 50.435' N | 122° 08.900' W | Plow Up | 63 | 123
23 | Global Sentinel | 2007-03-20 | 36° 50.356' N | 122° 09.095' W | A/C |  | 131
24 | Global Sentinel | 2007-03-20 | 36° 50.231' N | 122° 09.450' W | A/C |  | 171
25 | Global Sentinel | 2007-03-20 | 36° 50.221' N | 122° 09.482' W | Splice Box |  | 171
26 | Global Sentinel | 2007-03-20 | 36° 50.203' N | 122° 09.530' W | A/C |  | 191
27 | Global Sentinel | 2007-03-20 | 36° 50.149' N | 122° 09.631' W | A/C |  | 214
28 | Global Sentinel | 2007-03-20 | 36° 49.945' N | 122° 09.902' W | A/C |  | 303
29 | Global Sentinel | 2007-03-21 | 36° 49.743' N | 122° 10.076' W | A/C |  | 310
30 | Global Sentinel | 2007-03-21 | 36° 49.459' N | 122° 10.210' W | A/C |  | 332
31 | Global Sentinel | 2007-03-21 | 36° 48.892' N | 122° 10.382' W | A/C |  | 370
32 | Global Sentinel | 2007-03-21 | 36° 48.750' N | 122° 10.471' W | A/C |  | 383
33 | Global Sentinel | 2007-03-21 | 36° 48.623' N | 122° 10.587' W | A/C |  | 390
34 | Global Sentinel | 2007-03-21 | 36° 48.337' N | 122° 10.912' W | A/C |  | 429
35 | Global Sentinel | 2007-03-21 | 36° 47.846' N | 122° 11.335' W | A/C |  | 452
36 | Global Sentinel | 2007-03-21 | 36° 47.579' N | 122° 11.465' W | Plow Down |  | 465
37 | Global Sentinel | 2007-03-21 | 36° 47.306' N | 122° 11.592' W | A/C | 105 | 546
38 | Global Sentinel | 2007-03-21 | 36° 46.695' N | 122° 11.678' W | A/C | 122 | 630
39 | Global Sentinel | 2007-03-21 | 36° 46.662' N | 122° 11.672' W | Transition | 118 | 645
40 | Global Sentinel | 2007-03-21 | 36° 46.111' N | 122° 11.575' W | A/C | 117 | 739
41 | Global Sentinel | 2007-03-21 | 36° 46.063' N | 122° 11.553' W | Exit USA Territorial Waters | 118 | 739
42 | Global Sentinel | 2007-03-21 | 36° 45.574' N | 122° 11.318' W | A/C | 117 | 760
43 | Global Sentinel | 2007-03-21 | 36° 44.893' N | 122° 11.166' W | A/C | >80 | 787 | PLIB completed 01 Apr 07
44 | Global Sentinel | 2007-03-21 | 36° 43.442' N | 122° 11.195' W | Plow Up | 44 | 853 | PLIB completed 01 Apr 07
45 | Global Sentinel | 2007-03-30 | 36° 42.801' N | 122° 11.206' W | Splice Box | 75 | 880 | PLIB completed 01 Apr 07
46 | Global Sentinel | 2007-03-30 | 36° 42.740' N | 122° 11.210' W | TRF |  | 880