Friday, March 05, 2004

Attending: 

Raybould, Chavez, Graybeal, Nelson, O’Reilly, Gomes

Objective: 

Review status of MBARI-CIMT deployment 

Summary:

This was the kickoff for weekly MBARI-CIMT status meetings. With 3 months remaining until the deployment, it is time to begin holding weekly meetings to monitor project status and critical path items, and to facilitate communication between subsystem working groups.

To maintain focus on the approaching MTM deployment, only the group leads (Chaffey, Chavez, Gomes, Kelley, O’Reilly) will be required until the MTM deployment; design team members are welcome and encouraged to attend, and should communicate any critical information (especially changes to delivery schedule of long-lead items) to group leads.

The meetings are intended to be brief, especially those held prior to MTM deployment.

To make it easier for more people to attend, the meeting has been moved to every Thursday at 1:30 p.m. and will be held in Bldg G (immediately preceding the SIAM/SSDS user meetings on alternating weeks). 

Action Items:

Headley: 

send power budget to Francisco

get power supplies for CIMT (buy $400/$200)

get portal server (laptop corvina?)

Schedule Meetings: Thursdays 1:30 in bldg G

Chavez: 

send ADCP sampling parameters to headley

Charge codes: send email

Can data be sent to Orbcomm and SIAM?

OSG: 

order Compass, gps

confirm number of serial/inductive microcats (2/5), second smodem card

does metsys use windbird, sonic or both?

Status of ADCP wiring design

Status of cabling (deployment and bench test instrument cables)

SIAM: 

configure server

SSDS user interface: 


Prototyping meeting: broader group UCSD Friday 3/12


Chavez, Johnson, Ryan, SSDS

 Agenda:

General Objectives

Future Meeting Schedule

Project Schedule

Science

Budget to purchase acoustic release? 

Yes, do we have some here to use? 

ADCP sampling parameters 

(by mon, chfr)

SOON: internal battery powered? 

Yes, all. 

SSDS interface

Deploy SIAM service


Can data be sent to both orbcomm and SIAM?
Instruments (qty needed, qty in house, who has them):

Compass (2,0,not ordered) 

GPS (2,0,not ordered)

Metsys (1,1,OSG): Windbird,Sonic,both?

ADCP (1,2,OSG)WHS300

SBE37SM (1?,0,-) new ones ordered

SBE37IM (4,0,-) new ones

SMODEM1 (2,0,-)

ICC4  (1,0,-)

ISUS (1, 1, SIAM)

CO2/Orbcomm/SOON/antenna (1,1, SIAM)

OBS (1,1,SIAM)

Fluor (1,1,SIAM)

Radiometers (5,5,SIAM)

MOOS

Foam

Battery boxes

Power System

Solar panels

Panel mounts

Power cables

Power electronics

Batteries

Load dump resistors/mounting? 

Housings, connectors

MMC 

Housings

Chassis

Bulkhead connectors

End caps

Pucks (non-iso, molded) and housings

4GB Flash testing

OSG

Deployment cables and connectors

ADCP wiring

Test cable and connectors

Radio infrastructure

Freewaves (model, qty)

Antennas

Enclosures

Cable system

Anchor/Chain recovery

Cable, rope, chain, hose/sleeving

Hardware

Acoustics

Anchor

Brackets

ISUS, CO2/orbcomm/SOON, CTD, fluor, obs, radiometers

Pager reset, freewave, GPS, metsys, pucks

Radar reflector

Nav light

GPS

SIAM

Staging 

MTM mounting date (bench clear) (Mar 24)

Can CIMT be test bed?

Need more power supplies

power supplies

freewaves in bldg G OK
Power management

SSDS interface

Metadata handling

Portal server

Instrument services

Radiometers

ADCP whs300 service OK

SSDS

User interface design

