Thursday, March 11, 2004

Attending: 

Erickson, O’Reilly, Raybould, Kelley, Gomes

Coenen

Objective: 

Review status of MBARI-CIMT deployment 

Summary:

Action Items:

Headley: 

Power budget (pending ADCP sampling parameters)

Power supplies

Backup portal server

Have McBride send compass and gps PO info to Zorba

Revise schedule

Chavez: 

ADCP sampling parameters -> headley

OSG: 

Order compass, GPS

Confirm number of serial/inductive microcats (2/5) and order balance 

Kelley to meet w/ O’Reilly to determine what test cables are needed

Cabling and connector orders

SIAM: 

SSDS: 

 Agenda:

Pending Action Items

Chavez: 

send ADCP sampling parameters to headley

Charge codes: send email

Headley: 

get power supplies for CIMT (model? << spec O’Reilly)

get portal server (backup laptop pablito parkinglot server…has serial ports? MTM machine could support; need to modify portal—2 portals on same host; ~ 2days)

OSG: 

order Compass (McBride if for MMC), GPS (McBride>> PO info to Zorba)

confirm number of serial/inductive microcats (2/5), second smodem card (OSG check microcats they have 1/4)(we have 1 modem card; OSG will order a second)

does metsys use windbird, sonic or both? What other sensors? Where are they? (Zorba will provide metsys, can use both w/o wind generator or one w/ w.g.)

Status of ADCP wiring design (will use alk battery packs, same wiring scheme as mtm; 3 total packs, 2 are ext packs, 400 Wh/pack)

Status of cabling (deployment and bench test instrument cables)

(Kelley will meet w/ Tom off line to review and order)

SSDS: 


Prototyping meeting: broader group UCSD Monday 3/15 15:30

Project Schedule

Configuration Freeze (headley:send reminder)

Begin setup MMC and instruments Mar 28 week 

Buoy Standup Support (when available? Ferrara can modify existing stand) (April 12 stand up (after M2) better for OSG)

Need to get solar panels 

Between 1st and 19th  (buoy float assembly): tech time/MTM 

Could start in buoy room on 19th week…

Tower, cables (high bay) prior 

Buoy room door tall enough for all but masts… 

Buoy and electrical system parts due April 1 (check w/ ed about parts)

Begin buoy assembly April 4 week

General System Issues

Power Budget

Data Storage and Telemetry Budget


4GB CF: test status not known

Science

ADCP sampling parameters (follow up w/ Chavez)

SOON:  Can data be sent to both orbcomm and SIAM?
Instruments (qty needed, qty in house, who has them):

Compass (2,0,not ordered) 

GPS (2,0,not ordered)

Metsys (1,1,OSG): What sensors? Where are sensors?

ADCP (1,2,OSG)WHS300

SBE37SMP (1?,0,-) new ones ordered

SBE37IMP (4,0,-) new ones


Software changes? Power? (inductive use batteries;OSG check connectors and power consumption for serial)

SMODEM1 (2,0,-) (OSG will order 1)

ICC4  (1,0,-) (OSG will order one spare)

CO2/Orbcomm/SOON/antenna (1,1, SIAM?)

MOOS

Foam

Battery boxes: in progress arrive by april 1; need assy

Power System

Solar panels

Panel mounts 

Power cables

Power electronics

Batteries

Load dump resistors/mounting? Order out…

(panels need, as well as wind gen?) 

Housings, connectors: cases out for brazing

2 short cases on parking lot buoy;

Headley: finalize end cap design (OSG recommends leaving space for future expansion)

MMC 

Housings

Headley: finalize end cap design (OSG recommends leaving space for future expansion)

Chassis

Bulkhead connectors

End caps

Pucks (non-iso, molded) and housings

4GB Flash testing

OSG

Deployment cables and connectors

ADCP wiring (Using battery packs?)

Order deadlines approaching

Bench/test cable and connectors

Radio infrastructure

Freewaves (model, qty)

Antennas

Brackets for radiometers: need ME time 

Chavez/OSG: 5m collector occluded by buoy? 



 light

GPS

SIAM

Staging :

MTM mounting date (bench clear) (Mar 24)

Can we use SIAM MMC hardware for development until deployment

Power management:

SSDS interface:

 Metadata handling: 

Class versioning issues:

Portal server


Can we use same machine as MTM?

Instrument services

Radiometers

SSDS

User interface design

