Thursday, March 25, 2004

Attending: 

Objective: 

Review status of MBARI-CIMT deployment 

Summary:

· Meeting next week scheduled for 11:30

· Configuration Freeze: this week

· Begin setup MMC and instruments Mar 28 week 

· Wind generator will not be included on CIMT

· Begin buoy assembly April 4 week

· 2004M2 deployment April 8

· MTM Deployment April 22

· April 12 standup (pending float arrival)

· April 1-19:  (buoy float assembly)

· Could start in buoy room on 19th week…

Mechanical Parts Status:

Foam (e.t.a. ~April 11)

Battery boxes: 

out for brazing (1-2 weeks); need assembly

Power System

Solar panels: on order, e.t.a. April 1

Panel mounts:  

Power cables: on hand

Power electronics: on hand

Batteries: need to order

Load dump resistors/mounting? On order

Housings, connectors: cases out for brazing

2 short cases on parking lot buoy;

MMC endcaps out for fab ~ 2wks lead


MMC 

Housings

Chassis

Bulkhead connectors

End caps (starting today…~ 2 weeks + anodizing)

Instrument Status:

Compass, GPS: on hand for test, deployment article ordered

SBE37SMP: 1 serial on order, 4 on hand

SBE37IMP: on order

SMODEM, ICC4: on hand, spare ordered

Metsys: (bldg G)

Windbird, RH/Temp, Pressure: (OSG)

Where is CO2/SOON/Orbcomm?

WHS300 (bldg G/OSG, pending memory check)

ISUS (Bldg G)

OCR3000 Radiometers (5, Bldg G)

ECO-BB (1, Bldg G)

ECO-FL (1, Bldg G)

Radio Infrastructure:

Freewaves on order (arrive ~4/10)

There may be subtle differences in Freewaves: test early w/ Bob H.

Metadata capture: Need a tool for use with CIMT

Location Metadata: Need a meeting to discuss use/implementation of location metadata (SSDS/SIAM user stories)

SIAM:

Herlien, Headley to meet re radiometer service

Action Items:

Chavez:

ADCP sampling parameters -> headley

Charge codes: send mail/explain

5m collector occluded by buoy? 

Headley:

Hold meeting re ADCP wiring

Check MMC H/W delivery date

Verify use of isolated pucks in non-isolated mode

Inventory of isolated puck H/W

Verify molded puck connectors

Power budget (pending ADCP sampling parameters)

Power supplies 

Backup portal server (where is pablito?)

Revise schedule

OSG:

Cabling and connector orders (deployment, bench test)

Order MOOS batteries

Buoy Standup Support

Metsys sensors (Windbird, RH/temp, pressure)

Finalize ADCP wiring design (will use 1 internal, 2 external battery packs, 400 wH each)

Recovery of parking lot chassis: coordinate w/ MOOS

Check ADCP (bldg G) choose deployment instrument

(Eric) Verify Freewave performance w/ Bob H.

(Eric) Spec/Make housings, internal mounts for Freewaves

MOOS:

Coordinate with OSG to recover MMC from parking lot

Radiometer bracket design

Mechanical parts delivery

Power System delivery

MMC hardware delivery

4GB CF test status

SIAM: 

Hold meeting re CIMT deliverables and schedule

SSDS: 

