Thursday, April 15, 2004

Attending: 

Objective: 

Review status of MBARI-CIMT deployment 

Agenda:


Important Dates: 

· Deployment June 3 (6 Weeks!)

· Deployment Can due next week

· Deployment Cables, Pucks, Instruments due in 2 weeks

· Buoy mechanical assembly April 19-May 3

· Buoy electrical system wiring May 5-11

· Open Can Test: first week of May (2 weeks)

· Closed Can Test: second week of May

Administrivia:

Mooring Location (121 54.2 W, 36 50.0 N)

Status Reports:

Cable, Anchor and recovery system: 

· Dome order status

· Cable parts inventory 

MOOS Orders

· Pager Reset (use spare, replace eta? )

· Batteries (battery+solar panel order in? due this week)

· Power system parts (power cables not ordered, use MOOS spare set and replace)

· Battery boxes (ship from brazer Mon. (remachine flanges), eta Fri 23rd) 

· MMC housing end caps (any outstanding?)

· Foam (still shipping 14th)

MMC

· 4 GB CF testing (Siam review data volumes)

· Reset issue debugging plan  (Tim and Bob begin April 20)

· Awk doesn’t work on current “golden bits” (message out to Tim)

· Thttpd compiled w/o stats (Message out to Tim)

· Ethernet doesn’t work after sleep (must use console or radio)

Controller Build

· Wiring (cut to length for deployed, wait on spare, use connector blocks?)

· Any roadblocks?

· Deployment Chassis (status, due this week)

· Electronics (status, due this week)

· End caps, bulkhead connectors

Power Can Build

· Status (Tom is doing wiring…eta?)

Instruments

· Sensor Reps

· Serial Numbers, ISI Ids (SNs for deployment GPS, compass, deployment sidearm/MSP430)

· SOON/Orbcomm/CO2

· Connectors and cables (when needed? Eta?)

· Mechanical mounts (instrument, antenna, when needed, who is making)

· Data collection and telemetry (SSDS, status)

· Check overlapping frequencies (badger, okuda, nelson)

· CTDs (delivered this week, integrating)

· Metsys sensors (have windbird, need deployed RH/temp sensor)

· Radiometer bracket design (status, fab?)

· Radiometer power supply

Instrument Cables

· Order status

· Monster cable

Radio Infrastructure

· Radios, housings, brackets, antennas, cables: status

· Antenna height, gain

· OK to mount on ring w/ antennas on cans (verify)

· Other masts

· GPS

· Windbird

· Reset can

· orbcomm

· Radar reflector?

· Radiometer?

Mooring Build

· Staging plan

· Solar panel frames (done Mon, panels arrive next week? Req 2 weeks for assembly)

· Battery boxes (how much time to assemble? )

· Stand up support  (can use one from MOOS pjt, can’t use OASIS version)

· How soon can we start getting tower put together? Needed: power can, solar panels, batteries, power system cables, brackets (which?)

Pucks

· Puck bench test cables

· Puck build status (housings, connectors, boards, who is working on it)

· Confirm molded puck connector plan w/ OSG (connector compatible w/ molding tool?)

· Molded puck tooling (status, is there shop time?)

· Need to fix puck firmware issue

· Puck/system issues

· SWR doesn’t always start …times out on first sample and goes into shutdown

· Need to put more time on them in the lab

· Non-iso pucks

· Issues and debugging status

· can we use iso pucks as non-iso? (yes)

· is there enough iso puck h/w? (no)

· there is an ECO (power supply ATX mod) on isolated pucks

SIAM

· metadata handling

· power management

· radiometer service

· class versioning

· system configuration

· multiple copies of portal on one machine

· thread accumulation

· short haul and sleep

· reboot after wake

· awk broken

· thttpd compilation w/o stats

SSDS

· Mon-Wed IAG XP development days…emphasis on developing user stories, infrastructure elements, automated processing of data 

· Many QC plots require special processing (e.g. ADCP)

· data description (raw data and instruments)

· user interface design

· metadata capture tool 

· OSG user requirements meeting (headley set up meeting)

· Complexity of SOON data integration…(new “requirement”)

· Training on data interfaces (2 weeks)

· What are the priorities for user stories? (offline, gomes, graybeal, keith, chavez, Johnson)

Deployment System

· status

Other Issues:

· anyone pending on something from someone else?

· Critical path: deployment cables and pucks

· Review of SIAM/SSDS interface in light of new SSDS requirements

· Ethernet after sleep (SIAM)

· System schematic set

Action Items:

Chavez:

Headley:

OSG:

MOOS:

SIAM: 

SSDS: 










