Thursday, April 22, 2004

Attending: 

Objective: 

Review status of MBARI-CIMT deployment 

Agenda:


Important Dates: 

· Deployment June 3 (5 Weeks)

· Deployment Cables, Pucksdue next week

· Buoy mechanical assembly April 19-May 3

· Buoy electrical system wiring May 5-11

· Open Can Test: first week of May (1 week)

· Closed Can Test: second week of May (2 weeks)

· Final Readiness review Friday, May 14 (3 weeks)

· What is roll out date?

Administrivia:

· Permitting: open issues?

· CG Notices etc.?

· Ship Schedule

· Mooring Location (121 54.2 W, 36 50.0 N)

· Weather contingency plan

Status Reports:

Cable, Anchor and recovery system: 

· Dome order status

· Cable parts inventory

· Build status 

MOOS Orders

· Pager Reset (cable status, use spare and deploy)

· Batteries (battery+solar panel order in? due this week)

· Power system parts (outstanding items? No Build status)

· Battery boxes (build status Ed: start Tom/Jose to start battery boxes, load sinks)

· Chassis parts for spare MMC (need to make parts)

· Foam (e.t.a.? Friday or Monday Jon get tracking number)

· Elevator parts (location? All here? Parts here (machine shop, bins), need winch bracket (Jon), zinc holes in buoy bridle, need buoy stand up)

· SOON drifter batteries (2 wks)

· Cable parts incoming (Ken Heller will find someone to do. Several 4 days to wire and pot)

· Satlantic cable (part monster cable) , power cables for eval of satlantic power

MMC

· 4 GB CF testing (currently need more than 2 GB; review engr data requirements and SIAM node data volumes)

· Reset issue debugging plan  (Tim and Bob begin April 20) (CF disk issues after sleep  resolved, working on reboot after sleep)

· Awk doesn’t work on current “golden bits” (patch submitted)

· Thttpd compiled w/o stats (patch submitted)

· RMI exceptions in cloned images

· Golden bits version control (why clone? How are golden images created and stored?)

· Ethernet doesn’t work after sleep (must use console or radio, not scheduled to be fixed for CIMT, use work around)

· RFIO board bring MMC out of sleep early (not show stopper, but need to run down. Source unknown. (Tim))

Controller Build

· Any roadblocks?

· Deployment Chassis (status, due this week)

· End caps, bulkhead connectors

Power Can Build

· Status (Tom is doing wiring…eta? Needs ground fingers. Jim S. will provide)

· Cable location

Pucks

· Puck build status (housings (Jon deliver to Ken housings and endcaps), connectors (Carolyn), boards (Dick Littlefield has), who is working on it; headers; o-rings (Jon); Ken)

· Confirm molded puck connector plan w/ OSG (PVC molded w/ 6-pin whip+instrument-specific; scotchcast, heatshrink (Ken/Paul))

· Need to fix puck firmware issue (! Need to get Risi’s time)

· Puck/system issues

· SWR doesn’t always start …times out on first sample and goes into shutdown

· Need to put more time on them in the lab

· Non-iso pucks

· Issues  (None) and debugging status

· can we use iso pucks as non-iso? (yes)

· is there enough iso puck h/w? (no)

· there is an ECO (power supply ATX mod) on isolated pucks

· puck cables for bench test in progress (Duane T.)

Instruments

· Sensor Reps

· Serial Numbers, ISI Ids (SNs for deployment GPS, compass, deployment sidearm/MSP430)

· SOON/Orbcomm/CO2

· RF interference OK (software problem on retries may account for missing data; cable was OK, but not great)

· Connectors and cables (status, will change cable)

· Mechanical mounts (instrument, antenna, when needed, who is making: Gernot should handle)

· Data collection and telemetry (deliverables, responsible party, status: working w/SSDS to integrate GPS, CO2; where will data set reside? (easy to change) John, Kevin SSDS contact)

· (2 cans (one for battery), antenna mount Mark H work w/ Jon)

· Check overlapping frequencies (badger, okuda, nelson)

· Metsys  deployment RH/temp sensor (Zorba)

· Radiometer bracket design (status, fab? Need to be made; need to figure out plan for surface unit (new work for Jon))

· Radiometer power supply

· ISUS has grounds tied to case, isolated power is out of range (19-75 V). Will be sent back to Satlantic for mods (~1 week)

Instrument Cables

· Order status (somethings are arriving, Paul will hand off to Ken. Paul out next week)

· Monster cable (Priority to get built next week; Ken will do)

Radio Infrastructure

· Possible change: may go with one freewave (can we still use it for high speed data transfer?) (have two pair)

· Radios, housings, brackets, antennas, cables: status

· Integration testing (attenuation+handshaking; Bob and Eric will work the issues. Probably not til next week…maybe be able to use radio this weekend, if not, use eth w/o sleep)

· 3 Cables (12 pin to 2 pie) shipped

· Eric out Mon(4/26-28),Tue,Wed 

Mooring Build

· Buoy room status (clean up in progress)

· Crane, forklift other equipment needed (not to move in) (jackstands from MTM will be used for CIMT)

· When foam delivered, shop cut tie rods (.5 day), then can mount, standup and attach bridle

· Staging plan

· Solar panel frames (build status: frames done. Gluing begins today)

· Battery boxes (build status)

· Elevator (after stand-up)

· Stand up support 

· Tower Build: needed: power can, solar panels, battery boxes, power system cables, brackets (which?)…what else?

SIAM

· Compact flash supply (2 GB, 4 GB)

· ethernet after sleep

· disk writes and sleep (Fixed)

· thread accumulation (resolved by socket factory…Tom?)

· short haul and sleep (implement portal logic to wake up at some frequency and download at lower frequency)

· reboot after wake (tim working)

· testing, publishing to SSDS (maybe not for production machine; meet offline )

· metadata handling (portal mods required?)

· power management

· radiometer service

· ISUS service debugging

· class versioning

· system configuration

· multiple copies of portal on one machine

SSDS

· User story meeting results

· Many QC plots require special processing (e.g. ADCP)

· data description (raw data and instruments)

· user interface design

· metadata capture tool (no progress)

· OSG user requirements meeting

· SOON data integration (deliverables, who, when)

· Training on data interfaces (1 week)

· Priorities for user stories (are they clear? results, status; not clear yet)

Deployment System

· status

Other Issues:

· anyone pending on something from someone else?

· Critical path: deployment cables, pucks, SIAM software testing

· Review of SIAM/SSDS interface in light of new SSDS requirements

· System drawing set










