Thursday, April 29, 2004

Attending: 

Objective: 

Review status of MBARI-CIMT deployment 

Agenda:


Important Dates: 

· Deployment June 3 (4 Weeks)

· Deployment Cables, Pucks due this week

· Buoy mechanical assembly April 19-May 3

· Buoy electrical system wiring May 5-11

· Open Can Test: first week of May (next week)

· Closed Can Test: second week of May (1 week)

· Instrument Readiness review May 12-14 (end of closed can test)

· Final Readiness review Friday, May 14 (2 weeks)

· What is roll out date?

Administrivia:

· Permitting: open issues (done)

· CG Notices etc. (ntm submitted)

· Ship Schedule

· Mooring Location (121 54.2 W, 36 50.0 N) (~ 7 mi 70-75m)

· Weather contingency plan (Francisco scheduled weather day)

Status Reports:

Cable, Anchor and recovery system: 

· Dome order status (here)

· Cable parts inventory (cable eta 2 weeks)

· Chain here, rigging inventory needed (will do next week)

· Build status

MOOS Orders

· Pager Reset (cable…use spare and deploy)

· Batteries, solar panels (here)

· Power system parts (outstanding items? No Build status)

· Battery boxes (build status; Tom has all parts; out today; cables higher priority)

· Load sinks (build status; all wired jon filling with oil ; done 2+ 2 spares)

· Chassis parts for spare MMC (delivered yes; Zorba working maybe done tomorrow; change internal connectors?)

· Foam (delivered; tie rod status; half welded; plates in hibay)

· Elevator parts (location? All here? Parts here (machine shop, bins), need winch bracket (Jon, in shop), zinc holes in buoy bridle (in progress), need buoy stand up)

· SOON drifter batteries (2 wks)

· Cable parts incoming (Ken Heller will find someone to do. Several 4 days to wire and pot) (have all but one order from Newark; splicing start Friday…3-4 days to do all including pucks)

· Satlantic cable (part monster cable) , power cables for eval of satlantic power (iso input cable is what we have)

· ISUS (satlantic received today)

Mooring Build

· Buoy room status (clean up in progress, stand up next week)

· Tower, instruments, controller

· Solar panels 

· OSG needs time w/ tower on float, sensors, have platform; stack tower soon

· Crane, forklift other equipment needed (not to move in) (jackstands from MTM will be used for CIMT)

· When foam delivered, shop cut tie rods (.5 day), then can mount, standup and attach bridle

· Added lead ballast on bridle (optical sensor, pick weight for crane; see Francisco)

· Solar panel frames (2x90%, 2xglued done by Tues; hang on tower as soon as done)

· build status: frames done. Gluing begins today)

· Battery boxes (build status)

· Elevator (after stand-up)

· Stand up support 

· Tower Build: needed: power can, solar panels, battery boxes, power system cables, brackets (which?)…what else?

MMC

· What image is on Sidearm414,413?

· 4 GB CF testing (currently need more than 2 GB; review engr data requirements and SIAM node data volumes)(will run on node tomorrow; Tim tests OK)

· Reset issue debugging plan  (resolved)

· Awk doesn’t work on current “golden bits” (patch submitted)

· Thttpd compiled w/o stats (now using boa)

· RMI exceptions in cloned images (Tom working – date not set Mike found - fixed)

· Golden bits version control (why clone? How are golden images created and stored?)

· Ethernet doesn’t work after sleep (must use console or radio, not scheduled to be fixed for CIMT, use work around)

· RFIO board bring MMC out of sleep early (connected to serial port problem; maybe fixed (interrupt race))

· RFIO MSP430/power consumption (Tim working)

Controller Build

· Any roadblocks?

· Deployment Chassis (delivered)

· End caps, bulkhead connectors

Power Can Build

· Status (Ed has power can; testing done early next week)

· Test status, when available for SIAM bench test

· power budget verification (ed will help; plugging, unplugging)

· when needed for test with panels, batteries, etc.

· Cable location

Pucks

· Puck build status (housings (internal connectors in Newark order))

· GPS to puck cable (Ken will check)

· How much time needed for potting (overnight)

· Need to test molded pucks during closed can test?

· Confirm molded puck connector plan w/ OSG (PVC molded w/ 6-pin whip+instrument-specific; scotchcast, heatshrink (Ken/Paul))

· Puck/system issues

· SWR doesn’t always start …times out on first sample and goes into shutdown

· Need to put more time on them in the lab

· Non-iso pucks

· Issues  (intermittent failures, firmware issue) and debugging status

Instruments

· Sensor Reps

· Serial Numbers, ISI Ids (SNs for deployment GPS, compass, deployment sidearm/MSP430)

· SOON/Orbcomm/CO2

· RF interference OK (software problem on retries may account for missing data; cable was OK, but not great)

· Connectors and cables (status, will change cable)

· Mechanical mounts (three tubes OK?) (OSG has access issues; OSG prefers sensor on mid deck (gernot prefers nearer to h20))

· Mike, Mark, Gernot on Monday

· Data collection and telemetry (deliverables, responsible party, status: working w/SSDS to integrate GPS, CO2; where will data set reside? (easy to change) John, Kevin SSDS contact)

· Check overlapping frequencies (badger, okuda, nelson)

· Metsys  deployment RH/temp sensor cover (Zorba)

· Radiometer bracket design (in the shop)

· Only missing brackets are for SOON

· Radiometer power supply

· ISUS has grounds tied to case, isolated power is out of range (19-75 V). Will be sent back to Satlantic for mods (e.t.a.? loaner from Francisco?)

Instrument Cables

· Order status (delivery status)

· Monster cable (Priority to get built next week; Ken will do)

Radio Infrastructure

· Possible change: may go with one freewave (can we still use it for high speed data transfer?) (have two pair)

· Radios, housings, brackets, antennas, cables: status (all mechanicals, cables)

· Integration testing (status: working OK)

· 3 Cables (12 pin to 2 pie) shipped (status: here)

· Eric out Mon(4/26-28),Tue,Wed

· Will set up in cupola next week 

· Antennas came in today

SIAM

· Serial port hanging on sleep

· Compact flash supply (2 GB, 4 GB)

· ethernet after sleep

· disk writes and sleep (Fixed)

· thread accumulation (resolved by socket factory…Tom?)

· short haul and sleep vs single radio (eval work to make short haul work w/ sleep vs work to use single radio which requires ppp enabled box…console vs ppp)

· reboot after wake (tim working)

· testing, publishing to SSDS (maybe not for production machine; meet offline )

· metadata handling (portal mods required?)

· power management

· radiometer service

· ISUS service debugging

· class versioning

· system configuration

· multiple copies of portal on one machine

· Satlantic svc complete

· Metadata work complete

· Configuration scripts (lab vs deployed, siamPort.cfg)

SSDS

· Working on deployment SSDS machine for CIMT today

· Will give SIAM xml and publishing jar

· Feedback from Reiko and Tim

· External processing (John G)

· User story meeting results

· Many QC plots require special processing (e.g. ADCP)

· data description (raw data and instruments)

· user interface design

· metadata capture tool (no progress)

· OSG user requirements meeting

· SOON data integration (deliverables, who, when)

· Training on data interfaces (1 week)

· Priorities for user stories (are they clear? results, status; not clear yet)

Deployment System

· Status (buoy stayed horizontal)

· Will be using Pengo

Other Issues:

· anyone pending on something from someone else?

· Critical path: deployment cables, pucks, SIAM software testing

· Review of SIAM/SSDS interface in light of new SSDS requirements

· System drawing set










