Thursday, May 6, 2004

Attending: 

Objective: 

Review status of MBARI-CIMT deployment 

Agenda:


Important Dates: 

· Deployment June 3 (3 Weeks)

· Deployment Cables, Pucks due this week (Today)

· Buoy mechanical assembly April 19-May 3

· Buoy electrical system wiring May 5-11

· Open Can Test: in progess

· Closed Can Test: May 10-14 (next week)

· Instrument Readiness review May 12-14 (next week)

· Final Readiness review Friday, May 14 (1 week)

· What is roll out date 

· Memorial day May 31

· Instrument mount

· Roll out Jun 1

· Load sur Jun 2

Administrivia:

· Permitting: open issues (done)

· CG Notices etc. (ntm submitted)

· Ship Schedule

· Mooring Location (121 54.2 W, 36 50.0 N) (~ 7 mi 70-75m)

· Weather contingency plan (Francisco scheduled weather day? No not til August)

Status Reports:

MOOS Orders

· Chassis parts for spare MMC (pending vents, others?)

· Winch bracket (in shop)

· SOON drifter batteries (1 week)

· Cable parts incoming  (have everything but GPS cable and coupler are built; 3 potted pucks assembled)

· Puck internal connectors (pending Newark order status; here)

· Other puck parts? (none)

· Satlantic cable (cable for iso-power+non-iso-comms?)

Mooring Build

· Elevator (checking inventory, shafts not found – need to order (2-3 days – just tubing))

· Buoy room status (clean up in progress, stand up next week: ready)

· zinc holes in buoy bridle (in progress after painting)

· painting status (back early next week; kind of busy)

· Tower (3rd panel up this morning for fitting, wiring will be done this afternoon – overnight to pot junction boxes – done Monday morning), instruments, controller

· OSG needs time w/ tower on float, sensors, have platform; stack tower sooner rather than later 

· Jackstands OK (bending on supports--OK)?

· When will buoy be ready to stack tower? Solar panel testing ?

· Bridle ballast (bricks arrived w/ arrived this a.m. – no paint required)

· Solar panel status (potting junction boxes, panel mounting)

· Battery boxes (build status Tom doing number 4 or 5 of 8)

· Elevator (after stand-up)

· Stand up support 

Cable, Anchor and recovery system: 

· Cable parts inventory (cable eta 1 weeks)

· Chain here, rigging inventory needed (due this week)

· (chain inspection OK, can use existing stock of shackles from mooring support and pay back)

· Acoustic release (we have coastal shallow water version w/ low load rating – Andy needs to OK (marginal) load rating; there is another beefed up one somewhere (Mike talk to Dale?))

· Build status

MMC

· Top priority for CIMT (all promised except)

· reboot after wake (status resolved)

· 4 GB CF testing (testing on deployment article; so far so good)

· Ethernet doesn’t work after sleep (must use console or radio, not scheduled to be fixed for CIMT, use work around)

· RFIO board brings MMC out of sleep early (connected to serial port problem; maybe fixed (interrupt race masking out work around)

· RFIO MSP430/power consumption (Tim working, priority may be bumped up based on outcome of sleep manager issues)

Controller Build

· Deployment Chassis (delivered)

· End caps, bulkhead connectors

· Change internal connectors on spare

· Rewire secondary radio port to DPA’s before closed can?

Power Can Build

· Test status, when available for SIAM bench test (today?)

· power budget verification (Ed help interpret data?)

· power system staging/test plan

· tomorrow delivered

· can use next week for closed can test

· need one battery set of battery , use power supply to charge batteries

Pucks

· Puck intermittent failure debugging status (Risi and McBride trying to reproduce; trying to fix w/ retry mechanism)

· Puck build status (housings (internal connectors in Newark order) 8 pucks 4 housed (), 4 potted (done today))

· GPS to puck cab(started today )le (Ken will check)

· How much time needed for potting (overnight): when to do potting

· Isolation module on puck possible?

Instruments

· ISUS power/comms isolation

· Seabird power isolation

· SOON/Orbcomm/CO2

· Connectors and cables (status)

· Mechanical mounts (instrument on tower, batteries in elevator)

· Data collection and telemetry status (% complete)

· Metsys  deployment RH/temp sensor cover (Zorba)

· Radiometer bracket design (in the shop?)

· Only missing brackets are for SOON

· Radiometer power supply

Instrument Cables

· Build status

· Order status (delivery status)

· Monster cable (Priority to get built next week; Ken will do)

Radio Infrastructure

· Can we test end to end over weekend?

· Shore side installation status (putting antenna in cupola, can hit from bldg G)

· single radio looking more likely

· What handshaking signals are actually needed? Is it different for PPP vs console?

· Radios, housings, brackets, antennas, cables: status (all mechanicals, cables)

SIAM

· Portal machine (need dedicated machine-headley/o’reilly)

· Sleep manager (descope? When deciding?) (still in test; need prolonged test;)

· Serial port hanging on sleep(?)

· Compact flash supply (2 GB, 4 GB should order 1 4 GB)

· short haul and sleep vs single radio (eval work to make short haul work w/ sleep vs work to use single radio which requires ppp enabled box…console vs ppp)  ( will use one radio, need to test more, and test use w/ win PPP client; radio on ship must be configured and in call book of mooring. Need to power down portal ; must have call book of mooring radio set up.

· reboot/halt via wireless (intermittent problems; hard to reproduce. Solution is pager reset)

· SSDS/SIAM interface (done)

· radiometer service (done)

· class versioning (not for CIMT)

· system configuration scripts (made new config script)

· multiple copies of portal on one machine (install dedicated machine instead… may want to do if there is time)

· Satlantic svc complete

· MTM is functioning well

SSDS

· Deployment SSDS machine status (use Prey for data, docs)

· External access

· Will give SIAM xml and publishing jar (xml persistence debugging)

· (John G is filling creating metadata and getting feedback; )

· User story meeting

· External processing (John G) (ext processes are distributed; separate meeting)

· Many QC plots require special processing (e.g. ADCP)

· data description (raw data and instruments)

· user interface design

· APIs (meeting tomorrow at 9 am)

· metadata capture tool (no progress)

· SOON data integration (deliverables, who, when: 85% complete working on XML very; receiving data from SOON updateing file on tornado)

· Training on data interfaces (status: interfaces still evolving; can get together with people and discuss)

· Priorities for user stories (are they clear? results, status; not clear yet)

· SIAM/SSDS formal interface testing: Has been reviewed by Kevin and John (MD sequence number issue? Resolved) Meet offline to discuss 

· Multiple data records (OBS and FL: use one reading per sample; ISUS)

Deployment System

· Status (buoy stayed horizontal)

· Will be using Pengo

Other Issues:

· anyone pending on something from someone else?

· Critical path: 

· Deployment cables, pucks

· Instrument configuration 

· power consumption measurement

· SIAM software testing (power mgmt, comms config)

· Puck debugging

· Puck build

· ISUS, Seabird integration

· Battery boxes

· Power system testing










