Thursday, May 27, 2004

Attending:

Objective: 

Review status of MBARI-CIMT deployment 

Agenda:


Important Dates: 

· Deployment June 3 (1 Week)

· Buoy final assembly in progess

· Software “hands-off” testing in progress

· Roll out Jun 1 (or when ready….Fri?)

· Load sur Jun 2

Administrivia:

· Mooring Location (121 54.2 W, 36 50.0 N) (~ 7 mi 70-75m)

· We do have permit for anchor and 100 m of chain

Status Reports:

MOOS Orders

· None pending


Mooring Build

· Instrument painting (status) 

· Elevator (status of brackets (welding only), monster cable mount)

· PCO2 battery mounts (spacers cut, done today)

· Wiring (status)

· Instrument mount status (radiometers, pCO2, pCO2 batteries)(waiting for ISUS)

· Panels (roll out to sun? Still open/close OK after mount?) 

· Radar reflector (installed?)

· Logo painting (content, format; george coordinating;name “M0”)

· Pie connector marking

· What’s left to do? Timetable?

Cable, Anchor and recovery system: 

· Nilspin (order status)

· Bridle ballast (rigging status)

· Spool cable (pending shackles, due last week) 

· Cable parts inventory (cable eta last week)

· Acoustic release (tested?)

· Anchor parts (need plate made, large eye bolt due last week)

· What’s left to do? Timetable?

MMC

· Dummy plugs (order status: due last week)

· Spare can 

· vents

· housing, chassis fit (Ed has housing)

· golden bits version (will clone deployed article root fs)

· Install 4 GB CF

· Close can (do checklist)

· Use 10 min radio link opportunity; downloads occur every 20 min; available for 60 seconds (check power budget)

Power Can Build

· Power can Min-K cap (ROV crew may have)

Pucks

· No pending issues

Instruments

· OCR shutter shaft 

· ISUS (ready for mounting)

· ADCP testing (all self tests done, tank test pending, compass test  pending – today)

· SOON/Orbcomm/CO2 ()

· Battery clamps for SOON (status)

· SOON drifter batteries (status)

· Connectors and cables (status: pending telemetry cable configuration)

· Mechanical mounts (instrument on tower, batteries in elevator)

· Harlan working on antenna issues w/ Badger (antenna bulkhead connection)

· Radiometer bracket fab (due last week) 

· Painting required?

Instrument Cables

· No pending issues

Radio Infrastructure

· Deployment radio setup (test next week)

· Radio setup on Pt Sur

· Windows PPP setup (OK)

· (Update callbooks)

SIAM

· data outage (status)

· run clockCheck (after some hands-off run time)

· deployment laptop setup

· Clone deployed file system (status)

· Verify data budget

· SSDS/SIAM interface (needs formal test post deployment) 

SSDS

· External access to data  (predator; maybe done today; data available when on production machine)

· QC Plots (status)

· Any further planned changes to metadata?

· Any testing remaining w/ SIAM?

· User story implementation status

· External processing (status)

· APIs (status)

· SOON data integration (% complete)

· Linkage of externally processed QC plots with SSDS native (status)

· Readiness meeting results

· SIAM/SSDS formal interface testing: Has been reviewed by Kevin and John Meet offline to discuss

Deployment System

· Status

Other Issues:

· deployment plan

· anyone pending on something from someone else?

· Critical path: 

· Painting

· Buoy wiring

· Instrument mount

· Cable and anchor assembly










