Thursday, May 27, 2004

Attending:

Objective: 

Review status of MBARI-CIMT deployment 

Agenda:


Important Dates: 

· Deployment June 3 (1 Week) (on the boat @ 0700)

· Buoy final assembly in progess

· Software “hands-off” testing in progress

· Roll out Jun 1 (or when ready….Fri? Yes! Lay down Tues, load Wed.) 

· Load sur Jun 2

Administrivia:

· Mooring Location (121 54.2 W, 36 50.0 N) (~ 7 mi 70-75m)

· We do have permit for anchor and 100 m of chain

Status Reports:

MOOS Orders

· None pending


Mooring Build

· Instrument painting (status: only 1 OCR needs 3rd coat; done today) 

· Elevator (status of brackets (welding only), monster cable mount; welding done, longer ADCP standoff needed, Erickson working on it)

· PCO2 battery mounts (spacers cut, done today)

· Wiring (status: done, sea water gnd installed today)

· Instrument mount status (radiometers, pCO2, pCO2 batteries)(waiting for ISUS)

· Panels (roll out to sun? Still open/close OK after mount? )

· Panel doors: not structural problem, need to adjust (create bigger slot in hinge) 

· Radar reflector (installed)

· Logo painting (content, format; george coordinating;name “M0”; nelson will follow up with badger)

· Pie connector marking

· What’s left to do? Timetable?

· (after rollout, )

· rollout to dock, solar panel test, cable painting, logo painting (ladder/scaffold);

· Tues: laydown , connect bridle foot, place by Pt Sur

· Wed: load on Pt Sur

Cable, Anchor and recovery system: 

· Nilspin (order status)

· Bridle ballast (rigging status)

· Spool cable (pending shackles, due last week) 

· Cable parts inventory (cable eta last week)

· Acoustic release (tested?)

· Anchor parts (need plate made, large eye bolt due last week)

· What’s left to do? Timetable?

· Anchor done, chain done, 

MMC

· Dummy plugs (order status: due last week; on buoy)

· Spare can 

· vents

· housing, chassis fit (Ed has housing; test fit ok)

· golden bits version (will clone deployed article root fs)

· Install 4 GB CF

· Close can (do checklist)

· Use 10 min radio link opportunity; downloads occur every 20 min; available for 60 seconds (check power budget)

Power Can Build

· Power can Min-K cap (ROV crew may have)

Pucks

· No pending issues

Instruments

· ECO dummy plugs (in installed)

· OCR shutter shaft (resolved) 

· ISUS (ready for mounting; done)

· ADCP testing (all self tests done, tank test pending, compass test  pending – today; done)

· Mounts/brackets (none pending)

· SOON/Orbcomm/CO2 ()

· Battery clamps for SOON (status)

· SOON drifter batteries (status)

· Connectors and cables (status: pending telemetry cable configuration)

· Mechanical mounts (instrument on tower, batteries in elevator)

· Harlan working on antenna issues w/ Badger (antenna bulkhead connection)

· Radiometer bracket fab (due last week) 

· Painting required? (done)

· Antenna potted (ready to mount ;must lay down for roll out)

· Cables made; 

Instrument Cables

· No pending issues

Radio Infrastructure

· Deployment radio setup (test next week)

· Radio setup on Pt Sur

· Windows PPP setup (OK)

· (Update callbooks)

SIAM

· data outage (status)

· run clockCheck (after some hands-off run time)

· deployment laptop setup

· Clone deployed file system (status)

· Verify data budget

· SSDS/SIAM interface (needs formal test post deployment) 

· Final test in buoy room, fixed ADCP bug, portal publishing to production machine, mtm2 data outage (serial comms failure? Installed diagnostic script)

· Oversleep anomaly (bob investigating)

· Draft user guide published today

· Cloned deployed image failed

· Keep console in case we need to do more cloning? 

· Should test to make sure that it works w/o console cable (unplugged  at MMC)

SSDS

· External access to data  (predator; maybe done today; data available when on production machine) (up and running, can use API s and plots available: ssdspub.mbari.org. some features are slow e.g. SIAM Raw data access page (tunneling data thru firewall via HTTP) working on speed ups.)

· QC Plots (status: Andrew working on GPS plots)

· Any further planned changes to metadata? (none anticipated)

· Any testing remaining w/ SIAM? (want to move away from metadata seqNo (not before CIMT))

· User story implementation status (John has document?)

· External processing (status)

· APIs (status: GPS watch circle plot uses it, 5 developers)

· SOON data integration (85% complete: data there, can see on page, working on plotting by time)

· Linkage of externally processed QC plots with SSDS native (status: pending on input from external process developers)

· Readiness meeting results: will check

· SIAM/SSDS formal interface testing: Has been reviewed by Kevin and John Meet offline to discuss

· (building plots, external processes, external access)

· CIMT users are (quietly) using APIs to generate data for their external processes

· API docs: usage page from web page (need pointer from project library)

Deployment System

· Status

Other Issues:

· Rollout: no need for SIAM shutdown; may need to shutdown instruments.

· Ready early afternoon

· deployment plan

· microcat testing

· portal on ship?

· Meeting to discuss cruise-day schedule

· Friday is weather day

· post deployment plan:

· who will monitor watch circle, power budgets, data budgets? OSG+MOOS in parallel

· Mellinger: power

· McBride/Zorba: MSP430

· sensor reps watch data streams?

· anyone pending on something from someone else?

· Attaching big pieces fairly easy, can mounting, panels

· Critical path: 

· New 50 m nilspin (if it doesn’t show up deploy in 75 m; pre measured, not labeled)

· Cable and anchor assembly










