AUV Docking Project Meeting Notes

28 March, 2006
Attending: 

Brett Hobson, Jon Erikson, Lance McBride, Farley Shane, Thomas Hoover, Steve Rock 

1) AUV Website

a) Please check it out (http://www.mbari.org/auv) and provide suggested additions to Jim
2) Results from last mission 
a) Compass errors

i) Investigate external compass calibration routines. Jim
ii) Define a compass calibration check behavior to run immediately after a compass calibration.  Rob
iii) Check with Crossbow to see if there are calibration parameters we have access too as well as firmware upgrades available for our unit. Rob 
iv) Setup bore-sight corrections for alignment between DVL and Crossbow – Rob 
v) Drop AUV in the water and note changes in compass when thruster is under load. Thomas
b) USBL positioning drops out 5-7m from transponder

i) It appears gain can be lowered. Wait until Thursday to test offshore
c) There was a constant altitude tracking error as we travel up hill. Rob 

d) There was a constant 5 degree roll

e) Check static, in-water trim of vehicle – Thomas 

f) When docking payload + floatation is added, we’ll carefully adjust roll trim
3) Thursday’s mission (3-30-06)
a) Departure postponed until to allow Zephyr to pickup CTD vehicle
b) “8 for 8:30” departure
c) Work close to Moss Landing – weather permitting
d) Compass calibration runs
e) Anchor Zephyr

f) Deploy camera/transponder mooring
g) Run repeated mission on camera/transponder – using various control schemes – Rob
h) Simulation results - Rob
i) Watch video live on monitor, Record video on MiniDV – Brett to supply monitor and recorder
2) Dock
a) FAU

i) Potted inductive coil assembly leaked – no hermetic seal

ii) We don’t have a new date for delivery

b) Cone and Tube

i. Drawing check of Jon’s parts

ii. Wait for machine shop

b. Base and mast 

i. Ongoing discussion of docking dynamics and energy conversion - Farley
ii. 3m height, 510 lb train wheel, Aluminum tube frame, Astroturf for starfish resistance, screen covers, provision for leading floot screw and/or weight mounts
c. Camera
i. Internal diameter of the 1000m PhotoSea stills camera housing needs to be increased to fit the IP camera – Brett/Larry
ii. Camera recording software - Lance
d. Networking/NPS
i. IP setting issue - Lance
ii. Apply for NPS fixed IPs using forms provided - Lance
iii. Need a simple letter of understanding (scientific collaborators agreement) between MBARI and NPS regarding use of bldg. 510 – Brett/Jim
iv. It would be nice to establish a network connection to the dock from the Zehpyr

1. We don’t want to push our luck with NPS

2. Check price and availability of AeroComm radios. Lance
2. FAU

a. Docking station has been pressure tested, wired up and tested.

b. Payload is being pressure tested now

c. Resolver coils still need to be potted and a complete system test still needs to be completed before shipment.

d. They are still expecting to deliver the Inductive Charging system by April 

e. It would be nice if we could confirm full engagement of probe.
i. How difficult would it be to add a hall sensor to the probe to detect a magnet bonded in the vehicle probe receiver? - Lance
f. Jon needs the actual PCBs for the ethernet/serial converters – Lance
g. We need to design the docking section float – Jon, Brett
h. Get remaining parts in the machine shop – Brett, Farley, Jon

3. Operations – still don’t have “enough” operations scheduled
a. Zephyr schedule has opened up do to sharing with CTD opps

i. Need to install a second cradle on Zephyr

ii. April 11,12,13
iii. May 16,17,18

iv. June 20, 21,22 ( June 19th is already a Docking day)

v. July 26,27

b. Shana Rae

i. Available May and June; sooner we schedule the better

ii. Test LXT tracking for MF transponder – Brett, Thomas
c.  LCU as back up and emergency abort – needs to be tested – Brett, Thomas
4. Power and data transfer tests in tank 2nd week of April
5. Deploy dock May 24,25

6. Need to run a “Fast Cruise” that simulates the beginning-to-end steps of a mission.  We can run this in the lab, then the tank, before heading offshore.  It will help identify gaps.

7. Ongoing issues:

i. Identify other vessels and launch/recovery options

ii. Rebuild tail cone
1. Rudder position noise, probably from the position sensing potentiometer; watch closely during next operations, consider replacing.

2. Oil weeping from Elevator linear actuator.  Able to conduct daily operations.  Will monitor.

iii. Bore-sight alignment error between DVL and Compass; Rob will calculate error from existing data and code correction into guidance code

iv. Coupling of swell motion into altitude-following – Rob will work on removing the pressure measurement from the altitude- following controller.  Ready by March, maybe Feb.

8. Future Dates:

i. Weekly meetings: Tuesday 2 PM Ocean View

ii. March 27 – 30 Orion design meeting in Salt Lake City - Jim

iii. March 28 - 30 AUV Masterclass UK Hans

iv. March 30 Zephyr day * no Hans * homing tests at MISO
v. March 31; Abstracts due for Oceans

vi. April 17th Zephyr day – control development

vii. May 24, 25th  Zephyr day ** Deploy dock and test **
viii. May 23-26; AGU Joint meeting in Baltimore; Geochemical society, Microbeam Analysis Society, Mineralogical Society of America, Society of Exploration Geophysicists, Union Geofisica Mexicana
ix. June 19th 

x. June 20, 21,22 ( June 19th is already a Docking day)

xi. July 26,27

xii. Sept 12,13 Zephyr days

xiii. Sept 18 – 21; Oceans 2006 Boston; Lance, 

xiv. Sept 19, 20, 21; Zephyr days

xv. Dec 4, 5 – Dorado Low-Speed Control

xvi. Dec 11-15th; AGU Fall meeting; SF 

· Purpose of Preliminary Design Review 

· ensures that you have selected the best approach for meeting the requirements, and have considered merits of other viable options

· if done properly will avoid the “why don’t you do it this way?” comments that are frequently raised at Critical Design reviews when the design is completed

· limits the amount of resources to the minimum level needed to establish feasibility and performance of the best concept designs

· ensures that all Functional Requirements have been identified.  After the PDR a change in Functional Requirements can have a major impact on your project

· What is needed for a PDR

· evaluation of the relative performance of the selected concept design (or maybe 2/3 designs with most of the design work focused on the prefered design)

· performance predictions of the selected concept design, together with the engineering (bench-testing, analysis, layouts) that demonstrates that the selected concept will meet all of the Functional Requirements

· list of high risk items and how the risks will be mitigated

· list of Interfaces

· completed Functional Requirements

· draft System Design Requirements Documents 

