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[Less than 100 days effort]
	Development

	Research
	Infrastructure1
	Education
	Time Series


Project Manager/PI:

Alana Sherman




Project Title:

AUV Gulper

1) ABSTRACT (new projects only)

   [Paste abstract here]   


2) PROPOSAL

a) The problem addressed (new projects only)

N/A 
b) Approach to the problem (new and continuing projects)

Status of project

We proposed the following plan for 2005:

1. Continue evaluation of water sampling components and systems

2. Conduct hydrodynamic analyses to determine optimal water intake and sampling strategy

3. Hold a concept design review 

4. Build prototypes of key components for testing and evaluation. These components would probably consist of containers, valves, and an indexing mechanism.

5. Test prototype components in test tank

6. Test components on AUV

7. Analyze results of testing, modify components and system design accordingly

8. Preliminary design review

In January, the project team held a brainstorming session during which several system design options were presented and evaluated. A spring actuated sample bottle based design was selected as the most promising option. Over the next several months, prototype sample bottles were built and evaluated both in the test tank and on the ROV. In tests on Ventana, two of our sampler prototypes successfully collected 1.9 L of water in 4 seconds. 

Andy Hamilton complete a hydrodynamical analysis of drawing 2L of water from the skin of the AUV in a period of several seconds. We used his analysis as a basis for determining where to position the inlets.

We have completed preliminary designs for a mounting rack inside the AUV that will hold the sample bottles. We are currently working on a design for the mid-body foam pack.

In mid-July we held our preliminary design review. Our next milestone will be AUV testing. We have already successfully tested the electronic circuit that will trigger the sampler on the AUV. This circuit has been designed into a new drop weight board. AUV testing is tentatively scheduled for September.

Therefore, we have accomplished most of the tasks proposed for 2005 ahead of schedule. 

Results to date

Engineering results:

Successful acquisition of 1.9L of water in 4 sec on the ROV.

Science results:

John- summary of prelim. science testing

Publications (from the last 5 years)

No publications yet.

Plans for 2006


Engineering/technology development

With the sampler prototype built and tested this year, in the next year we will focus on putting together the complete system. A large portion of our efforts next year will be to test and validate the system.

We propose the following plan for 2006:

1. Complete ME design

2. Hold critical design review

3. Fabricate and assemble samplers, rack and foam pack

4. Build and test custom electronics 

5. Acquire/build cables and J-box 

6. Write and test software

7. Test system

8. Preliminary science testing

It is possible some of these tasks could be accomplished in the remainder of 2005. This is contingent upon the AUV testing going smoothly. 


Field programs

Our 2006 field programs will consist of engineering and science testing and validation of the instrument. The table below outlines the details of outlines the proposed testing regime, for the most part they are listed in the order which we expect to run them.

	User
	Mission
	Post-processing
	Who

Responsible
	Ship days
	Notes

	Project team
	Engineering tests
	Salinity, nutrients, bacteria
	Alana Sherman
	6 days
	See details in appendix

	Scholin/Ryan
	Test sample/ hold effects
	LISST, other
	Ryan lab
	0
	Further test effects of holding sample, can be piggy-backed on other missions

	Scholin lab/ Preston
	Deep water survey
	Bacteria
	Chris Preston
	1
	Preprogrammed survey

	Scholin lab/ Greenfield
	Sample based on data from earlier survey 
	Microscopy, Probes
	Dianne Greenfield
	3
	Target layers in shallow waters, coordinate with ESP deployment

	Vrijenhoek lab
	Exploratory transects
	SHA for green crab, etc.
	Joe Jones
	3
	Would like these days during the Fall

	Haddock lab
	
	
	
	
	

	BOG
	
	
	
	
	



Data (availability outside project team, uniqueness)

Dorado science data reduction is well developed and is being integrated with the data and metadata management of SSDS.

Significant changes from previous project proposal (continuing projects only)
There are no significant changes from last year’s proposal.

c) Specific deliverables (new and continuing projects)

1. Successful acquisition of a single water sample on the AUV

2. Critical design review

3. Fabrication of complete set of samplers, mounting rack and controller housing.

4. Successful testing of the complete water sampling system

5. Results from science testing of instrument

d) Project team (new and continuing projects)
· Alana Sherman: project manager, electrical/system engineering, testing of components.

· Farley Shane: mechanical engineer, mechanical design

· John Ryan & Chris Scholin: lead scientists 

· Gernot Friederich: provide expertise in water sampling
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Andy Hamilton: will use expertise to characterize hydrodynamic effects that may jeopardize sample integrity.

· Rob McEwen: analysis of the impact of the sampler on vehicle control and dynamics. Vehicle behavior software.

e) Project lab space (new and continuing projects)

Existing AUV and ME lab space will be sufficient.

3) BUDGET JUSTIFICATION (new and continuing projects)

The budget to build a working AUV Gulper system and mount it on the AUV is shown below.
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In addition to these components, we also ask for a general supplies budget of $5000, and $1000 for tools. We have included $1000 for miscellaneous computer hardware and $1500 to purchase any software needed to interface and control the device.

Finally, we request a travel budget of $5000, for domestic travel to a conference for two people, with an addition $1000 for conference fees.

4) MILESTONES (new and continuing projects)

	
	Milestone 1
	Milestone 2
	Milestone 3
	Milestone 4
	Milestone 5
	Total Resources
 for each resource category for all milestones listed here

	Milestone Date
	
	
	
	
	
	

	Milestone Description
	Complete ME design
	CDR
	Electronics & Software complete
	Fabrication and Assembly
	System testing and validation
	

	EE
	
	5
	15
	
	15
	35 +10 (proj. mgmt) =45

	SE
	
	
	12
	
	3
	15

	ME
	30
	4
	
	3
	3
	40

	Machine Shop
	
	
	
	28
	
	28


5) RISK MATRIX (development and infrastructure projects only)

Please carefully read Section 5.2.3 in the instructions for internal proposals for an explanation regarding the risk matrix. This table must be completed for ALL development and infrastructure proposals (new and continuing). The instructions can be found at http://mww.mbari.org/resources/2006_Proposal_Process/Internal-only_Instructions_2006.htm.

	
	Technical Risk
	Organizational Risk
	Tech Transfer Risk
	Labor Estimate Risk

	High
	
	
	
	

	Medium
	X
	
	X
	X

	Low
	
	X
	
	


� EMBED Excel.Sheet.8  ���
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� Development and infrastructure projects must complete the risk matrix (see item #5 at the end of the proposal form).


� This number should be the same number you entered on the resource requests for this particular resource.
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_1184571852.xls
Sheet1

		ITEM		QUANITY		COST MATERIALS		MACHINE TIME		MACHINE COST @ $ 70/HR		Total

		URETHANE POLYPAK SEAL		2		$24.13		0.00		0.00

		PISTON POLY CARBONATE		1		$3.12		0.30		21.00

		TITANIUM SHAFT		1		$15.02		0.40		28.00

		TITANIUM PACKING PLATE EXT		1		$16.23		0.50		35.00

		TITANIUM PACKING PLATE INT		1		$16.23		0.25		17.50

		TITANIUM SPRING PISTON		1		$1.56		0.25		17.50

		SHAFT STOP ACETAL		1		$0.20		0.20		14.00

		VALVE END CAP UHMW PE		1		$5.23		1.50		105.00

		OPEN END CAP UHMW PE		1		$2.81		0.50		35.00

		DIAPHRAGM SILICON		1		$0.56		0.10		7.00

		DIAPHRAGM PLATE TITANIUM		1		$2.35		0.25		17.50

		VALVE SPRING TITANIUM		1		$0.56		0.10		7.00

		VALVE SHAFT TITANIUM		1		$1.56		0.20		14.00

		VALVE SEAT TITANIUM		1		$1.03		0.10		7.00

		VALVE STOP TITANIUM		1		$1.29		0.10		7.00

		VALVE GASKET SILICON		1		$0.63		0.10		7.00

		CYLINDER BODY POLYCARBONATE		1		$18.25		0.20		14.00

		O RING END CAPS		2		$1.60		0.00		0.00

		O RING SHAFT		1		$0.12		0.00		0.00

				21		$112.48		5.05		353.50

		TOTAL COST PER SAMPLER (40 PART RUN)				$112.48				$353.50		$465.98





Sheet2

		ITEM		QNTY		COST 
MATERIALS (1 unit)		MACHINE 
TIME (HR)		MACHINE COST 
@ $ 70/HR		Total

		Sampler Set		24		$112.48		5.05		$353.50		$11,183.52

		AUV Mounting Rack		1		$500.00		16.00		$1,120.00		$1,620.00

		Foam		1		$15,000.00		0		$0.00		$15,000.00

		Electronics								$0.00

		Custom Electronics		1		$2,000.00				$0.00		$2,000.00

		Cabling		1		$7,500.00				$0.00		$7,500.00

		Electronics housing		1		$500.00		12		$840.00		$1,340.00

		Proximity switches		12		$150.00				$0.00		$1,800.00

		J-Box		1		$500.00		4		$280.00		$780.00

		Trigger								$0.00

		Trigger mech.		12		$60.00		4		$280.00		$4,080.00

		Solenoid		12		$540.00		0		$0.00		$6,480.00

										$0.00

										$0.00

										$0.00		$0.00

		TOTAL				$37,699.52		201.20		$14,084.00		$51,783.52

		Additional mid-body fairing would cost ~ $5000
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		ITEM		QUANITY		COST MATERIALS		MACHINE TIME		MACHINE COST @ $ 70/HR		Total

		URETHANE POLYPAK SEAL		2		$24.13		0.00		0.00

		PISTON POLY CARBONATE		1		$3.12		0.30		21.00

		TITANIUM SHAFT		1		$15.02		0.40		28.00

		TITANIUM PACKING PLATE EXT		1		$16.23		0.50		35.00

		TITANIUM PACKING PLATE INT		1		$16.23		0.25		17.50

		TITANIUM SPRING PISTON		1		$1.56		0.25		17.50

		SHAFT STOP ACETAL		1		$0.20		0.20		14.00

		VALVE END CAP UHMW PE		1		$5.23		1.50		105.00

		OPEN END CAP UHMW PE		1		$2.81		0.50		35.00

		DIAPHRAGM SILICON		1		$0.56		0.10		7.00

		DIAPHRAGM PLATE TITANIUM		1		$2.35		0.25		17.50

		VALVE SPRING TITANIUM		1		$0.56		0.10		7.00

		VALVE SHAFT TITANIUM		1		$1.56		0.20		14.00

		VALVE SEAT TITANIUM		1		$1.03		0.10		7.00

		VALVE STOP TITANIUM		1		$1.29		0.10		7.00

		VALVE GASKET SILICON		1		$0.63		0.10		7.00

		CYLINDER BODY POLYCARBONATE		1		$18.25		0.20		14.00

		O RING END CAPS		2		$1.60		0.00		0.00

		O RING SHAFT		1		$0.12		0.00		0.00

				21		$112.48		5.05		353.50

		TOTAL COST PER SAMPLER (40 PART RUN)				$112.48				$353.50		$465.98
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		ITEM		QNTY		COST 
MATERIALS (1 unit)		MACHINE 
TIME (HR)		MACHINE COST 
@ $ 70/HR		Total

		Sampler Set		24		$112.48		5.05		$353.50		$11,183.52

		AUV Mounting Rack		1		$500.00		16.00		$1,120.00		$1,620.00

		Foam		1		$15,000.00		0		$0.00		$15,000.00

		Electronics								$0.00

		Custom Electronics		1		$2,000.00				$0.00		$2,000.00

		Cabling		1		$7,500.00				$0.00		$7,500.00

		Electronics housing		1		$500.00		12		$840.00		$1,340.00

		Proximity switches		12		$150.00				$0.00		$1,800.00

		J-Box		1		$500.00		4		$280.00		$780.00

		Trigger								$0.00

		Trigger mech.		12		$60.00		4		$280.00		$4,080.00

		Solenoid		12		$540.00		0		$0.00		$6,480.00

										$0.00

										$0.00

										$0.00		$0.00

		TOTAL				$37,699.52		201.20		$14,084.00		$51,783.52

		Additional mid-body fairing would cost ~ $5000
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		ITEM		QUANITY		COST MATERIALS		MACHINE TIME		MACHINE COST @ $ 70/HR		Total

		URETHANE POLYPAK SEAL		2		$24.13		0.00		0.00

		PISTON POLY CARBONATE		1		$3.12		0.30		21.00

		TITANIUM SHAFT		1		$15.02		0.40		28.00

		TITANIUM PACKING PLATE EXT		1		$16.23		0.50		35.00

		TITANIUM PACKING PLATE INT		1		$16.23		0.25		17.50

		TITANIUM SPRING PISTON		1		$1.56		0.25		17.50

		SHAFT STOP ACETAL		1		$0.20		0.20		14.00

		VALVE END CAP UHMW PE		1		$5.23		1.50		105.00

		OPEN END CAP UHMW PE		1		$2.81		0.50		35.00

		DIAPHRAGM SILICON		1		$0.56		0.10		7.00

		DIAPHRAGM PLATE TITANIUM		1		$2.35		0.25		17.50

		VALVE SPRING TITANIUM		1		$0.56		0.10		7.00

		VALVE SHAFT TITANIUM		1		$1.56		0.20		14.00

		VALVE SEAT TITANIUM		1		$1.03		0.10		7.00

		VALVE STOP TITANIUM		1		$1.29		0.10		7.00

		VALVE GASKET SILICON		1		$0.63		0.10		7.00

		CYLINDER BODY POLYCARBONATE		1		$18.25		0.20		14.00

		O RING END CAPS		2		$1.60		0.00		0.00

		O RING SHAFT		1		$0.12		0.00		0.00

				21		$112.48		5.05		353.50

		TOTAL COST PER SAMPLER (40 PART RUN)				$112.48				$353.50		$465.98





Sheet2

		ITEM		QNTY		COST 
MATERIALS (1 unit)		MACHINE 
TIME (HR)		MACHINE COST 
@ $ 70/HR		Total

		Sampler Set		24		$112.48		5.05		$353.50		$11,183.52

		AUV Mounting Rack		1		$500.00		16.00		$1,120.00		$1,620.00

		Foam		1		$15,000.00		0		$0.00		$15,000.00

		Electronics								$0.00

		Custom Electronics		1		$2,000.00				$0.00		$2,000.00

		Cabling		1		$7,500.00				$0.00		$7,500.00

		Electronics housing		1		$500.00		12		$840.00		$1,340.00

		Proximity switches		12		$150.00				$0.00		$1,800.00

		J-Box		1		$500.00		4		$280.00		$780.00

		Trigger								$0.00

		Trigger mech.		12		$60.00		4		$280.00		$4,080.00

		Solenoid		12		$540.00		0		$0.00		$6,480.00

										$0.00

										$0.00

										$0.00		$0.00

		TOTAL				$37,699.52		201.20		$14,084.00		$51,783.52

		Additional mid-body fairing would cost ~ $5000
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		Component		Quantity		Cost per unit		Machine Time 
(Hr)		Machine Cost
(@ &70/Hr)		Total Cost

		Sampler Set		24		$112.48		5.05		$353.50		$11,183.52

		AUV Mounting Rack		1		$500.00		16.00		$1,120.00		$1,620.00

		Foam pack		1		$15,000.00		0.00		$0.00		$15,000.00

		Custom controller board		1		$2,500.00		0.00		$0.00		$2,500.00

		Proximity switches		15		$150.00		0.00		$0.00		$2,250.00

		Electronics housing		1		$500.00		12.00		$840.00		$1,340.00

		Trigger mech.		15		$60.00		4.00		$280.00		$5,100.00

		Solenoids		15		$540.00		0.00		$0.00		$8,100.00

		Cables		1		$7,500.00		0.00		$0.00		$7,500.00

		J-Box		1		$500.00		4.00		$280.00		$780.00

										$0.00		$0.00

										$0.00		$0.00

				TOTAL		$40,449.52		213.2		$14,924.00		$55,373.52
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		ITEM		QUANITY		COST MATERIALS		MACHINE TIME		MACHINE COST @ $ 70/HR		Total

		URETHANE POLYPAK SEAL		2		$24.13		0.00		0.00

		PISTON POLY CARBONATE		1		$3.12		0.30		21.00

		TITANIUM SHAFT		1		$15.02		0.40		28.00

		TITANIUM PACKING PLATE EXT		1		$16.23		0.50		35.00

		TITANIUM PACKING PLATE INT		1		$16.23		0.25		17.50

		TITANIUM SPRING PISTON		1		$1.56		0.25		17.50

		SHAFT STOP ACETAL		1		$0.20		0.20		14.00

		VALVE END CAP UHMW PE		1		$5.23		1.50		105.00

		OPEN END CAP UHMW PE		1		$2.81		0.50		35.00

		DIAPHRAGM SILICON		1		$0.56		0.10		7.00

		DIAPHRAGM PLATE TITANIUM		1		$2.35		0.25		17.50

		VALVE SPRING TITANIUM		1		$0.56		0.10		7.00

		VALVE SHAFT TITANIUM		1		$1.56		0.20		14.00

		VALVE SEAT TITANIUM		1		$1.03		0.10		7.00

		VALVE STOP TITANIUM		1		$1.29		0.10		7.00

		VALVE GASKET SILICON		1		$0.63		0.10		7.00

		CYLINDER BODY POLYCARBONATE		1		$18.25		0.20		14.00

		O RING END CAPS		2		$1.60		0.00		0.00

		O RING SHAFT		1		$0.12		0.00		0.00

				21		$112.48		5.05		353.50

		TOTAL COST PER SAMPLER (40 PART RUN)				$112.48				$353.50		$465.98





Sheet2

		ITEM		QNTY		COST 
MATERIALS (1 unit)		MACHINE 
TIME (HR)		MACHINE COST 
@ $ 70/HR		Total

		Sampler Set		24		$112.48		5.05		$353.50		$11,183.52

		AUV Mounting Rack		1		$500.00		16.00		$1,120.00		$1,620.00

		Foam		1		$15,000.00		0		$0.00		$15,000.00

		Electronics								$0.00

		Custom Electronics		1		$2,000.00				$0.00		$2,000.00

		Cabling		1		$7,500.00				$0.00		$7,500.00

		Electronics housing		1		$500.00		12		$840.00		$1,340.00

		Proximity switches		12		$150.00				$0.00		$1,800.00

		J-Box		1		$500.00		4		$280.00		$780.00

		Trigger								$0.00

		Trigger mech.		12		$60.00		4		$280.00		$4,080.00

		Solenoid		12		$540.00		0		$0.00		$6,480.00

										$0.00

										$0.00

										$0.00		$0.00

		TOTAL				$37,699.52		201.20		$14,084.00		$51,783.52

		Additional mid-body fairing would cost ~ $5000
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		ITEM		QUANITY		COST MATERIALS		MACHINE TIME		MACHINE COST @ $ 70/HR		Total

		URETHANE POLYPAK SEAL		2		$24.13		0.00		0.00

		PISTON POLY CARBONATE		1		$3.12		0.30		21.00

		TITANIUM SHAFT		1		$15.02		0.40		28.00

		TITANIUM PACKING PLATE EXT		1		$16.23		0.50		35.00

		TITANIUM PACKING PLATE INT		1		$16.23		0.25		17.50

		TITANIUM SPRING PISTON		1		$1.56		0.25		17.50

		SHAFT STOP ACETAL		1		$0.20		0.20		14.00

		VALVE END CAP UHMW PE		1		$5.23		1.50		105.00

		OPEN END CAP UHMW PE		1		$2.81		0.50		35.00

		DIAPHRAGM SILICON		1		$0.56		0.10		7.00

		DIAPHRAGM PLATE TITANIUM		1		$2.35		0.25		17.50

		VALVE SPRING TITANIUM		1		$0.56		0.10		7.00

		VALVE SHAFT TITANIUM		1		$1.56		0.20		14.00

		VALVE SEAT TITANIUM		1		$1.03		0.10		7.00

		VALVE STOP TITANIUM		1		$1.29		0.10		7.00

		VALVE GASKET SILICON		1		$0.63		0.10		7.00

		CYLINDER BODY POLYCARBONATE		1		$18.25		0.20		14.00

		O RING END CAPS		2		$1.60		0.00		0.00

		O RING SHAFT		1		$0.12		0.00		0.00

				21		$112.48		5.05		353.50

		TOTAL COST PER SAMPLER (40 PART RUN)				$112.48				$353.50		$465.98





Sheet2

		ITEM		QNTY		COST 
MATERIALS (1 unit)		MACHINE 
TIME (HR)		MACHINE COST 
@ $ 70/HR		Total

		Sampler Set		24		$112.48		5.05		$353.50		$11,183.52

		AUV Mounting Rack		1		$500.00		16.00		$1,120.00		$1,620.00

		Foam		1		$15,000.00		0		$0.00		$15,000.00

		Electronics								$0.00

		Custom Electronics		1		$2,000.00				$0.00		$2,000.00

		Cabling		1		$7,500.00				$0.00		$7,500.00

		Electronics housing		1		$500.00		12		$840.00		$1,340.00

		Proximity switches		12		$150.00				$0.00		$1,800.00

		J-Box		1		$500.00		4		$280.00		$780.00

		Trigger								$0.00

		Trigger mech.		12		$60.00		4		$280.00		$4,080.00

		Solenoid		12		$540.00		0		$0.00		$6,480.00

										$0.00

										$0.00

										$0.00		$0.00

		TOTAL				$37,699.52		201.20		$14,084.00		$51,783.52

		Additional mid-body fairing would cost ~ $5000
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